## Summary
CivicConnect manual test log
Run details
Test build URL | http://localhost:4200 (local build, team test Supabase)
Test build commit | a21dac1
Test database | Local / team test Supabase project
Prod URL
Prod commit
Run started | 16/10/2026 18:00
Testers | Clarissa Bierman, Eduard Herman
Applies to | main 6a198c4 = prod a21dac1. The later fix/m3-review-cleanup commit changes only a log line, tests and documents (no UI or API change), so these results also apply to it.
Results
Result | Test build | Prod | Total
Pass
Fail
Blocked
Not run
Total
Pass rate (of tests attempted: Pass, Fail, Blocked)
How to use
- Yellow cells are the ones to fill in. Everything else is the test definition.
- Run "Test build" on a local build or the team's test Supabase project, which has the dummy accounts.
- Run "Prod" after every deploy. It creates no data and cannot lock accounts.
- Result is a drop-down: Pass, Fail, Blocked (could not run, e.g. a page is missing) or Not run. The counts above update by themselves.
- For a Fail, write what happened in Actual result and the defect ID (D-xx) or issue link in Defect / notes.
- Also run on the test build: E2E_BASE_URL=<test url> npm run e2e (E2E-01 to E2E-03) and the k6 pilot.

## Test build
Manual tests - test build (local or test Supabase project)
Fill in the yellow columns. Result: Pass, Fail, Blocked or Not run.
ID | Requirement | Role / account | Before you start | Steps | Expected result | Actual result | Result | Defect / notes | Tester | Date | Commit / URL
Login and access
MT-01 | FR-014 | Requester, handler, manager | Dummy accounts exist (test database) | Log in as each role in turn. | Each lands on their own home page and sees only their own menu items. | Thabo on requester page (My Requests, New Request, Profile), Ayesha on staff queue (Requests, My account), Lerato on management (Activity, Requests, Categories, Staff, Audit, My account). Each only own menu. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-02 | FR-014 | Any | On the login page | Enter a valid email and a wrong password, then Log in. | An error message shows; you stay on the login page, logged out. | Error message shown, stayed on login page, not logged in. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-03 | FR-014 | Any (use a spare account) | Account not locked | Fail the login 5 times for one email, then try a 6th time. | The 6th attempt shows the "too many attempts" message. Wait for the lockout to end before reusing the account. | After 5 failed logins the 6th attempt showed the too many attempts message. | Pass | Used pieter.smit (spare account) | Clarissa Bierman | 16/10/2026 | a21dac1
MT-04 | FR-014 | Handler | Logged in | Log out. Press Back, then open /staff/requests directly. | You are sent to the login page; no request data shows. | After logout, Back and opening /staff/requests both sent me to login, no request data shown. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-05 | FR-014 | Requester | Logged in | Type /management/staff and /staff/requests in the address bar. | You are sent away from the page; no staff or management data shows. | As requester, /management/staff and /staff/requests both redirected away, no staff or management data shown. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-06 | ARC-03 | Requester | Logged in | Open /requests/mine and refresh the browser. | The page reloads normally (no 404 or blank page). | Refreshed /requests/mine, page reloaded normally, no 404 or blank page. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
Requester
MT-07 | FR-001 | New requester | Email not registered yet | Register a new account, then log in with it. | Registration succeeds; login works and shows the requester home page. | Registered cb.test1@example.com, logged in with it, requester home page shown. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-08 | D-25 | New requester | Email already used by another account | Register with that email and a new password. Try to log in with the new password. | Same message as a new registration; the new password does not log in. | Registering with existing email showed the same message as a new registration, new password did not log in. | Pass | Used fatima.adams. | Clarissa Bierman | 16/10/2026 | a21dac1
MT-09 | FR-001 | Requester | On New request | Submit with all fields empty. | Validation messages show next to the fields; no request is created. | Validation messages shown next to each required field, no request created. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-10 | FR-001, FR-003 | Requester | On New request | Fill in category, description and location, then submit. | Confirmation with a reference CC-yyyy-nnnnnn and status New; the request is at the top of My Requests. | Confirmation with reference CC-2026-000020 and status New, request at top of My requests. | Pass | - | Clarissa Bierman | 16/10/2026 | a21dac1
MT-11 | FR-002, FR-004 | Requester + handler | Handler has changed the status and added a visible and an internal note | As the requester, open the request. | New status, time and the visible note show; no staff names and no internal note. | Requester saw new status, time and visible note, no staff names and no internal note. | Pass | Handler steps done as Ayesha. | Clarissa Bierman | 16/10/2026 | a21dac1
MT-12 | FR-015 | Requester + manager | Manager has deactivated one category | Open New request and look at the category list. | The inactive category is not in the list. | Deactivated category was not in the requester category list. | Pass | Used Damaged Equipment. Category reactivated after the test. | Clarissa Bierman | 16/10/2026 | a21dac1
MT-13 | FR-002 | Requester | Logged in | On the profile page change the name and email. Log out and log in with the new email. | Changes are saved; login works with the new email. | Changed name and email on profile, saved, logged in with the new email. | Pass | Used zanele.mahlangu. | Clarissa Bierman | 16/10/2026 | a21dac1
Handler
MT-14 | FR-005 | Handler | Handler has some categories, not all | Open the queue. | Only requests in the handler's own categories are listed. | Queue showed only Damaged Equipment and IT Support requests; CC-2026-000001 (Facility Faults) and CC-2026-000004 (Security Concerns) not listed. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-15 | FR-006 | Handler | Queue has several requests | Use the status, category and date filters and each sort option. | The list changes to match every filter and sort. | Status, category, from/to date filters each narrowed the list correctly; Newest, Oldest and Priority sorts ordered it as expected. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-16 | FR-008 | Handler | A New request in scope | Accept the request. | It shows as assigned to you, with the time. | Accepted CC-2026-000002: status New → Assigned, handler shown as Ayesha, history shows Ayesha Patel with time. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-17 | FR-008 | Two handlers | Two browsers (one private window), same New request open | Both click Accept at the same moment. | One succeeds; the other gets an "already assigned" message. | Ayesha and MT Tester both had CC-2026-000021 open and clicked Accept within a second. MT-Tester got it; the other got "This request is already assigned." Only one handler in the history. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-18 | FR-009 | Handler | Own assigned request open | Look at the status options; try Update before choosing one. | Only valid next statuses are offered; Update stays disabled until one is chosen. | On assigned request CC-2026-000002, Update was disabled until a status was chosen; only In Progress and Rejected were offered. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-19 | FR-010 | Handler + requester | Own assigned request open | Add a visible note and an internal note. Check as the requester. | Requester sees only the visible note; neither note can be edited or deleted. | On CC-2026-000002 added an internal note and a requester-visible note. Requester #2 (Naledi) saw only the visible note, no staff name. No edit/delete on notes. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-20 | FR-011 | Handler | Own resolved request | Close the request, then reopen it. | Read-only: no status options and no comment box. | Moved CC-2026-000002 In Progress → Resolved → Closed. After reopening: no status options, no Update button and no comment box; read-only message shown; history kept. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-21 | FR-007 | Handler | A request with several changes | Open the request detail. | Full history: who, when, and from/to status for every step. | CC-2026-000002 history showed every step with actor and time: submitted (Requester #2), assigned, New→Assigned, 2 notes, Assigned→In Progress→Resolved→Closed with from/to status. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-22 | D-26 | Handler | Logged in | My account: change the password (current one required). Log out, log in with the new one. | Password changed; the new password works and the old one does not. | MT Tester changed password on My account (current password required, confirmation shown). After logout the old password was refused and the new one logged in. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
Manager
MT-23 | FR-016 | Manager + handler | A request open as manager | Set the priority to High. Check the handler's list and the request history. | The handler's list shows High; the history shows who set it. | Lerato set CC-2026-000003 to High on the Activity page ("Priority saved."). Ayesha's queue showed High; history showed "Lerato Nkosi - set the priority to High" with time. Handler cannot change priority. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-24 | FR-012 | Manager | Requests in different statuses, one older than 7 days | Open the activity page. | Open, overdue, resolved and closed counts show and match the data. | Activity (last 30 days) showed Open 9, Overdue 4, Resolved 2, Closed 2, Rejected 1. Category rows add up to the tiles; Closed matched the Requests list filtered by Closed (incl. CC-2026-000002); overdue ≤ open. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-25 | FR-013 | Manager | On the activity page | Change category, status and date range one at a time. | Counts and lists both change to match. (Lists fail until the FR-013 fix.) | Changing category, status and date range each updated both the counts and the request list. | Pass | Fixed in PR #32 (D-41). | Clarissa Bierman | 16/10/2026 | a21dac1
MT-26 | FR-015 | Manager + requester | On the categories page | Add a category; check as requester. Deactivate it; check again. | The requester sees the new category, then no longer sees it. | Lerato added "MT-26 test category"; it appeared in Thabo's New request category list. After Deactivate it stayed in the Categories table as Inactive and disappeared from the requester's list (Parking also not offered). | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-27 | FR-005 | Manager | On the staff page | Create a staff member, give them categories, log in as them. | The new staff member logs in and sees only those categories. | Lerato created staff member "MT Tester" and gave them only IT Support ("Categories saved."). MT Tester logged in and the queue showed only IT Support requests. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-28 | E2E-03 | Manager + handler | Handler logged in elsewhere with open requests | Deactivate the handler; handler clicks anything. | Handler is logged out on the next action; their open requests go back to the queue. | Lerato deactivated MT Tester while logged in elsewhere. MT Tester's next click went to the login page with an "account no longer active" message; re-login refused. CC-2026-000021 went from Assigned back to New with no handler; history shows removal + internal note by Lerato. | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
MT-29 | FR-014 | Manager | Only one active manager | Try to deactivate yourself. | Refused with a message. | Not executed: precondition not met. Test database has 2 active managers (Lerato, admin@gmail.com); the rule only blocks the last one, so running it would really deactivate Lerato on the shared test DB. | Blocked | Covered by automated tests EmployeeServiceTest.lastManagerProtected and ApiHttpIntegrationTest.lastManagerCannotBeDeactivated (CI, fresh DB). Can be run manually on a local DB with a single manager. | Eduard Herman | 16/10/2026 | a21dac1
MT-30 | FR-007, POPIA | Manager | Some activity exists | Open the audit page. | Entries show; client personal details are not shown in them. | Audit page listed entries with time, operation, record and actor (e.g. CC-2026-000002 status changes by Ayesha). Clients audit showed the POPIA notice and no name, email, phone, address or password; requesters shown as "Requester #N" | Pass |  | Eduard Herman | 16/10/2026 | a21dac1
Errors
MT-31 | NFR-005 | Any | Local build: stop the database (never on prod) | Use any page that loads data. | "Service temporarily unavailable" shows, not a blank page. | Backend running locally, Wi-Fi switched off so the test Supabase DB was unreachable. Requests page showed "Service temporarily unavailable." after ~30 s (connection timeout), no blank page. With Wi-Fi back on, the page loaded normally without a restart. | Pass | Simulated by cutting the network instead of stopping the shared DB. ~30 s wait before the message is the Hikari connection timeout. | Eduard Herman | 16/10/2026 | a21dac1
MT-32 | D-38 | Handler | Queue with several requests | Click quickly between two requests. | The details always match the selected request. (Fails until the D-38 fix.) | Clicked quickly between CC-2026-000020 and CC-2026-000013 about 10 times, details always matched the selected request. | Pass | Fixed in PR #32 (D-38). | Clarissa Bierman | 16/10/2026 | a21dac1
Usability
MT-33 | NFR-004 | 3 first-time users (not team members) | Each has never used CivicConnect and gets a dummy requester login; no instructions | Ask each user to log in and submit a request for a given problem without help. Time each from logging in to the confirmation. | At least 2 of the 3 submit successfully within 5 minutes, unaided. |  | Not run

## Prod
Smoke tests - prod (Render), after each deploy
Fill in the yellow columns. Result: Pass, Fail, Blocked or Not run.
ID | Requirement | Role / account | Before you start | Steps | Expected result | Actual result | Result | Defect / notes | Tester | Date | Commit / URL
After each deploy
P-01 | NFR-005 | None | Deploy finished on Render | Open https://<site>/api/v1/health. | Shows {"database":"UP","status":"UP"}. |  | Not run
P-02 | ARC-03 | None |  | Open the site; refresh on /login. | Loads over HTTPS; refresh works. |  | Not run
P-03 | D-31 | None |  | Try to log in as admin@gmail.com and one other dummy account. | Both refused; no dummy account exists on prod. |  | Not run
P-04 | D-31 | First manager | First deploy only | Log in with the temporary password; change it on My account. | Password changed; log in again with the new one. |  | Not run
P-05 | FR-012, FR-015 | Manager | Logged in | Open the activity, categories and staff pages. | All load; the 7 categories are listed. |  | Not run
P-06 | FR-014 | Manager | Logged in | Log out, then open /management/staff. | You are sent to the login page. |  | Not run
P-07 | R-15 | None | Site idle for 15+ minutes | Open the site. | It wakes and works within a minute or two. |  | Not run
Never on prod
- Login lockout and rate-limit tests (they lock real accounts)
- The k6 load test
- The Playwright E2E suite (uses dummy accounts)
- Registering test accounts or submitting test requests (audit rows cannot be deleted)
- Deactivating people
- Stopping the database (MT-31)