CiviCConnect Technology Project

SEN381

Chanri Du Randt 601635, Clarissa Bierman 602008, Eduard Bernard Kruger Herman 602125

Contents

1.	Document Control	6

2.	Change Request Register	13

2.1.	Controlled Design Changes (C-01 to C-09)	18

2.2.	Team Members & Work Allocation	22

3.	Acronyms & Abbreviations	22

4.	Problem Statement	24

4.1.	Business Need	24

5.	Stakeholder Analysis	24

5.1.	Client & User	24

5.2.	Development	25

5.3.	Other	25

5.4.	Stakeholder Conflicts	25

5.5.	Stakeholder Derived Requirements	26

6.	Scope Baseline	26

6.1.	In Scope	27

6.2.	Out of Scope	27

6.3.	Deferred / Future Scope	28

6.4.	Defended Exclusion: Automated Multi-Channel Intake	28

7.	Requirements & Acceptance Criteria	29

7.1.	Functional Requirements(FR)	29

7.2.	Non-Functional Requirements(NFR)	31

8.	Constraints	33

8.1.	Trade-off / Ripple-Effect Analysis	34

9.	Assumptions and Dependencies	35

9.1.	Exceptions and Differences from the above table:	35

Requirements Traceability Matrix (v3.0)	38

9.2.	Table 1 - Requirement baseline	38

9.3.	Table 2 - Engineering evidence	41

9.4.	Table 3 - M3 implementation and verification (RTM v3.0)	44

10.	End-to-End Traces	50

11.	Architecturally Significant Requirements	51

11.1.	Most Influential Drivers	54

11.2.	Quality Attributes Considered but Not Treated as ASRs	54

11.3.	M2 Architecture Review	54

11.4.	ASR Verification (M4)	55

12.	Risk Register	56

13.	Forward Engineering Considerations	63

13.1.	Auditing, Logging and Traceability of Request Handling	63

13.2.	Notification & Communication Between Requester and Handler	63

13.3.	Request Prioritization & Escalation	64

13.4.	Scalability and Concurrency	64

13.5.	System Integration & Legacy Data	64

13.6.	Definition of Digital Platform	64

14.	Engineering Decision Log	65

14.1.	Milestone 2 Updates to Engineering Decisions	66

14.2.	Milestone 3 Updates to Engineering Decisions	66

15.	Architecture Decision Record	67

15.1.	Architecture Alternatives Considered	67

15.2.	Architecture Decisions	67

15.3.	Architecture Diagrams	70

15.4.	Technology Stack	72

15.4.1.	Technology decision matrix	73

16.	Data & Persistence Baseline	76

16.1.	Persistence Model Decision	76

16.2.	Entities, Aggregates and Ownership	77

16.3.	Database ERD	78

16.4.	Entities	78

16.5.	Relationships	79

16.6.	Integrity and Validation Rules	79

16.7.	Transactions and Concurrency	81

16.8.	Append-only Audit Trail	82

16.9.	Schema Migrations and Configuration	83

16.10.	Access Patterns and Indexing	84

16.11.	Scalability, Availability, Single Points of Failure and Backup	85

16.12.	Data Sensitivity and POPIA	85

16.13.	Changes from the Initial ERD	86

17.	Initial Design Decisions	87

17.1.	Design Problem 1: Controlling Status Transitions	87

17.2.	Design Problem 2: Reacting to Status Changes	88

17.3.	Research-to-Decision Map	89

18.	Deployment Compatibility	90

19.	Implementation Status (Prototype)	91

19.1.	Repository Structure and Architecture Mapping	91

19.2.	What Is Built	91

19.3.	Known Gaps Between the PED and the Code	92

19.4.	Initial Verification	93

19.5.	Application Documentation	93

20.	API & Integration Design	94

20.1.	Interaction boundaries	94

20.2.	Interface Decisions (ADRs)	94

20.3.	API Conventions	96

20.4.	Endpoint Contract	97

20.5.	Error Model	99

20.6.	Example Interaction: a Handler Changes a Request's Status (FR-009)	101

20.7.	Validation and Security at the Boundary	101

20.8.	Versioning and Change	102

20.9.	Current Implementation Evidence vs Contract	102

20.10.	Integrations Deliberately Not Established	102

21.	User Interface Design	103

21.1.	Screen Map	103

21.2.	Wireframes	104

21.3.	Usability and Accessibility Rationale	106

22.	Process and Team Working Agreement	106

23.	GitHub & Team Governance	107

24.	AI Usage Register	108

25.	Baseline Sign Off	114

26.	Milestone 3 Evidence Index	115

26.1.	Submission Information	115

26.2.	M3 Overview	116

26.3.	M2 Baseline Conformance	116

26.4.	Controlled Changes	118

26.5.	Construction and Configuration	118

26.6.	CI and Automated Verification	119

26.7.	Quality Strategy Applied	120

26.8.	Black-box, Integration and System Validation	120

26.8.1.	Decision table: status changes offered (API-06 allowedTransitions)	121

26.8.2.	API / integration tests	121

26.8.3.	End-to-end / system tests (Playwright, civicconnect-frontend/e2e)	122

26.8.4.	Test evidence records (examples)	122

26.9.	Performance and Reliability	124

26.10.	Defects and Quality Interpretation	127

26.10.1.	Defect register	127

26.10.2.	Static analysis and security findings	132

26.10.3.	Technical debt register	132

26.11.	Release Readiness	134

26.11.1.	Release Evidence Summary	134

26.11.2.	Residual risks	135

26.11.3.	Staging and rollback	136

27.	Final Project (M4) Closure	137

27.1.	M1 Scope → Final Delivery	137

27.1.1.	In-scope commitments	137

27.1.2.	Non-functional requirements	138

27.1.3.	Out-of-scope and deferred items	139

27.1.4.	Scope changes since M1	140

27.2.	Scope Completion Percentage	141

27.3.	Schedule Performance and Variance	141

27.4.	Cost and Operational Cost	142

27.5.	Stakeholder Validation	143

27.6.	Decision Consequence Reflection	144

27.7.	Deployment, Rollback and Observability	145

27.8.	Final Quality and Security Summary	146

27.9.	Known Limitations and Future Evolution	147

27.10.	Test and Code Reference Index	148

28.	References	152

# Document Control

| Version | Date | Purpose | Owner | Approval | Date |
| --- | --- | --- | --- | --- | --- |
| 0.1 | 05/09/2026 | Create Document with correct layout. Setup shared document access on Microsoft Teams. Add problem & business need and stakeholder analysis sections. | Chanri Du Randt | Eduard Herman | 08/09/2026 |
|  |  |  |  | Clarissa Bierman | 09/09/2026 |
| 0.2 | 07/09/2026 | Added the GitHub & Team Governance section to the PED, set up branch protection on main requiring two reviewer approvals with self-approval disabled, and merged the first controlled pull request as evidence of the review process. | Clarissa Bierman | Chanri Du Randt | 08/09/2026 |
|  |  |  |  | Eduard Herman | 07/09/2026 |
| 0.3 | 07/09/2026 | Added Forward Engineering Considerations | Chanri Du Randt | Eduard Herman | 08/09/2026 |
|  |  |  |  | Clarissa Bierman | 08/09/2026 |
| 0.4 | 09/09/2026 | Added the Scope Baseline (in scope, out of scope, deferred/future scope, defended exclusion), Requirements & Acceptance Criteria (functional and non-functional requirements with IDs, sources, priorities and acceptance criteria), and Constraints sections (including trade-off/ripple-effect analysis) to the PED. | Eduard Herman | Chanri Du Randt | 09/09/2026 |
|  |  |  |  | Clarissa Bierman | 09/09/2026 |
| 0.5 | 09/09/2026 | Edited Forward engineering considerations and added engineering decision. | Chanri Du Randt | Eduard Herman | 09/09/2026 |
|  |  |  |  | Clarissa Bierman | 09/09/2026 |
| 0.6 | 09/09/2026 | Added the Initial RTM: all 15 functional and 9 non-functional requirements traced to their source stakeholder, with Design/Issue/Implementation/Test marked pending (expected at M1) and Acceptance evidence linked back to each requirement's acceptance criteria. Completed initial Risk Register | Clarissa Bierman | Eduard Herman | 09/09/2026 |
|  |  |  |  | Chanri Du Randt | 09/09/2026 |
| 1.0 | 09/09/2026 | Finalized the PED for Milestone 1 baseline sign-off - resolved the platform/website contradiction in Forward Engineering Considerations, added the Process & Team Working Agreement section, completed the AI Usage Register, and closed out the remaining compliance checks against the Master Brief. | Team | Clarissa Bierman, Eduard Herman, Chanri Du Randt | 09/09/2026 |
| 1.1 | 28/09/2026 | Added 3 constraints to time and cost | Eduard Herman | Chanri Du Randt | 29/09/2026 |
| 1.2 | 29/09/2026 | Added table for Milestone 1 review and fixes. Added Architecture Decision record. Added architecturally significant requirements. Added architecture diagram. | Chanri Du Randt | Eduard Herman | 30/09/2026 |
| 1.3 | 30/09/2026 | Finalized architecture decisions, ASR, and database persistence. Added tech stack as well. | Chanri Du Randt | Eduard Herman | 30/09/2026 |
|  |  |  |  | Clarissa Bierman | 30/09/2026 |
| 1.4 | 30/09/2026 | Added API & Integration Design section (interaction boundaries, DEC-009 REST API, DEC-010 JWT authentication, endpoint contract, error model, versioning, prototype gap table), moved status-change example into it. | Eduard Herman | Chanri Du Randt Clarissa Bierman | 30/09/2026 |
| 1.5 | 30/09/2026 | Filled in the Review of Milestone 1 (CR-001 to CR-006). Added FR-016 and updated the FR-008 and NFR-009 acceptance criteria under change control. Added Assumptions and Dependencies and three end-to-end traces (FR-009, FR-001, NFR-006). Extended the Risk Register with R-14 to R-23 and added M2 updates to the Forward Engineering Considerations. Added Initial Design Decisions (DEC-011 transition map, DEC-012 Observer), the Research-to-Decision Map, Deployment Compatibility and Implementation Status (Prototype). Added the GitHub & Team Governance M2 update and DEC-013 (CI). Aligned decision and risk IDs with the API & Integration Design section and removed duplicate acronyms. | Clarissa Bierman | Chanri Du Randt, Eduard Herman | 30/09/2026 |
| 1.6 | 30/09/2026 | Added the edited two-table RTM v2.0 and linked it to the API contract, design decisions and current risk IDs. Replaced the Review of Milestone 1 table with the Change Request Register (CR-001 to CR-010) and applied the changes to the requirements. Added citations and references, fixed ID and role inconsistencies, filled in placeholders, corrected team experience in DEC-004, completed the M2 baseline sign-off and added the User Interface Design section with three wireframes. | Chanri Du Randt | Clarissa Bierman, Eduard Herman | 30/09/2026 |
| 1.7 | 30/09/2026 | Fixed inconsistencies found in an adversarial review: CR version references, document control rows, RTM statuses and wording, R-22 status, the status-change walkthrough, integrity rule 1, the Reporting read-only exception in ARC-02, section cross-references, entity counts and the duplicated risk update. Redrew Figure 1 (database outside the application boundary, layers per module). Added CR-011 for the v1.1 constraint changes. Recorded that the team has no React experience in A-03, DEC-004 and the decision matrix. Added citations for licences, design pattern, CI, security and error-format sources. Second review fixes: CR-003 and CR-006 version references, credentials statements and R-22 reopened, A2 tasks named in DEC-006, DEC-007 and DEC-009, PRIORITY_CHANGE audit entry for FR-016, 409 ALREADY_ASSIGNED for FR-008, allowedTransitions in API-06, DEC-004 reassessment trigger, M2 Architecture Review record, known gaps in the baseline sign-off, corrected milestone dates (CR-012), repository link and alignment with the repository (Angular 21.2, local PostgreSQL 18.4, dependency names, contextLoads test, PR #1 to #3 evidence), heading numbering, acronyms, risk rating wording and migration file names. | Chanri Du Randt | Clarissa Bierman, Eduard Herman | 30/09/2026 |
| 2.0 | 30/09/2026 | Milestone 2 - Architecture, Technology & Initial Design Baseline: PED v1.7 approved as the M2 baseline, accepted with known gaps (see Baseline Sign Off). | Team | Team | 30/09/2026 |
| 3.0 | 16/10/2026 | Milestone 3 draft for team review. Added the Milestone 3 Evidence Index chapter; updated the API & Integration Design to the implemented API; recorded the M3 controlled changes C-01 to C-07; added RTM Table 3 (implementation and verification) and updated the RTM status columns; added risks R-24 to R-27 and M3 entries in the AI Usage Register. Drafted with AI assistance; every change is a tracked change. v3.0 draft update: rescored the technology decision matrix and updated DEC-004 (CR-013); recorded the M3 code review fixes D-18 to D-29 and controlled changes C-08 and C-09. v3.0 draft update (16/10/2026): fixed defects D-38 and D-40 recorded and D-41 and D-42 added; black-box API tests (ApiBlackBoxIntegrationTest) added to RTM Table 3 and the verification sections; README rewritten (TD-09, NFR-008); test, coverage and CI results updated to the run on main 6a198c4 and the release pull request #33; commit author alias noted under Construction and Configuration. Linked the manual test log (MT-01 to MT-33, P-01 to P-07). Final v3.0 (16/10/2026): all tracked changes accepted; Performance and Reliability extended with the k6 stress-probe table and its interpretation; ERD v3 (Figure 3) replaces ERD v2; release candidate v3.0.0-rc1, its CI run and the staging URL recorded. Prod smoke tests P-01 to P-07 recorded (7 of 7 Pass on 16/10/2026). Finalised in a Discord meeting; approved by all three members. | Team | Chanri Du Randt, Clarissa Bierman, Eduard Herman | 16/10/2026 |
| AI | 18/10/2026 | Final Project (M4) draft: Final Project (M4) Closure chapter (Eduard Herman, PR #37); change requests CR-014 to CR-019; risk statuses, R-28, R-29, TD-11, TD-12, ASR Verification and acronyms; milestone added to every change record and C-01 to C-09 moved to the Change Request Register chapter. Proposed as tracked changes for team approval. CR-020: persistence chapter updated to the schema as built; D-39 fixed (pool size 20). CR-021: M4 sections 27.3 to 27.9 drafted. 18/10/2026 (applied directly): End-to-End Traces, Implementation Status and Initial Design Decisions get M4 notes (the M2 cells are kept as history); auditTrailIsAppendOnly renamed to auditTrailAndNotesAreAppendOnly; client date of birth removed (CR-022, TD-03 resolved, ASR-005 met, ERD v3 redrawn); StatusChangeRollbackTest added; TD-13 frontend styling and TD-14 notifications added; DEC-013 M3 note; R-22, the CodeQL triage, approvals and milestone dates recorded; Test and Code Reference Index added (section 27.10). | Eduard Herman, Chanri Du Randt | Clarissa Bierman, Eduard Herman (PR #38, approved 18/10/2026); Final PED changes: PR [#number] | 18/10/2026 |

Milestone 3 (PED v3.0): the M3 evidence index - submission information, M2 baseline conformance, controlled changes, verification, performance, defects and release readiness - is the chapter "Milestone 3 Evidence Index" at the end of this document, before the References. All M3 edits are tracked changes, so they can be reviewed and accepted in Word.

# Change Request Register

This register replaces the Review of Milestone 1 table. Every change to baselined Milestone 1 content, and every new requirement or section added after the baseline, gets a change request (CR) with an impact analysis based on the Master Project Brief change request template (Section 14, Appendix E). Changed requirements keep their original wording as a "Was:" note, and each CR is referenced from the Requirements tables and the RTM.

| Change ID | Item(s) changed | Requested change | Reason / expected value | Impact analysis (requirements, design/data/API, security, testing, scope/schedule/cost, risk) | Raised by / date | Baseline affected | Recommendation / decision | Approved by / date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 (M2) | FR-015, NFR-009, Scope Baseline item 16, Relationships table | Replace "admin" with "Management": FR-015 "admin-defined / admin-maintained list" becomes "Management-defined / list maintained by Management users"; NFR-009 "categories admin-configurable" becomes "Management-configurable"; Scope item 16 "Admin-controlled" becomes "Management-controlled". | The system has no Admin role. Roles are REQUESTER, HANDLER and MANAGER (CR-008), so an "admin" requirement could not be implemented or tested. | Requirements: FR-015, NFR-009 wording. Design/API: API-14 and API-15 are Management only. Security: none (narrows who can change categories). Testing: category tests use a MANAGER token. Schedule/cost: none. Risk: none. | Eduard Herman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.6 | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-002 (M2) | FR-005 | Requirement becomes "Staff view requests in the categories assigned to them by Management." Acceptance adds that other requests cannot be opened through the API. | M1 said "assigned category/permission scope" without defining how scope is stored. Clients are identified by numbers and requests hold little personal data outside the request itself, so category-based visibility is enough. | Requirements: FR-005. Data: new EmployeeCategory table (ERD v2). API: API-07 filtered by scope, new API-16. Security: object-level check in the service layer (R-10). Testing: handler outside the category gets 403. Schedule: small (one table, one endpoint). Risk: R-10. | Eduard Herman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.6 | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-003 (M2) | New FR-016 | Add FR-016: Management sets the priority of a request (Low, Medium, High); saved, shown in staff lists and audited; other roles cannot change it. | DEC-003 decided managers assign priority and ERD v2 stores it, but no requirement existed to trace or test it. | Requirements: new FR-016, Stakeholder Derived Requirements. Data: Request.Priority. API: API-12 (MANAGER only). Security: role check. Testing: priority change audited; handler token rejected. Scope: small addition, Should priority. Schedule: low. Risk: R-01 (scope growth) - handled through this CR. | Eduard Herman, 30/09/2026 | No (new requirement) | Accept - applied in PED v1.5 | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-004 (M2) | FR-012 | Add to acceptance criteria: a request is overdue when it is not Resolved, Closed or Rejected within 7 calendar days of its CreatedAt date. | "Overdue" was never defined, so FR-012 could not be tested. 7 days is a team assumption until CivicConnect gives a service level. | Requirements: FR-012. Data: calculated from Status and CreatedAt (no new column). API: API-17 overdue count. Testing: boundary test at 7 days. Schedule/cost: none. Risk: R-09 (assumption not confirmed by a real client). | Eduard Herman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.6 | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-005 (M2) | FR-004, Scope Baseline item 4 | Status names in FR-004 and Scope Baseline item 4 change from "accepted/rejected/updated/completed" to "Assigned, In Progress, Resolved, Closed or Rejected". | Aligns FR-004 with the FR-009 state machine and the Status values in the database and API. | Requirements: FR-004 wording only. Design/data/API: none (uses existing statuses). Testing: requester sees each status. Schedule/cost: none. Risk: none. | Eduard Herman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.6 | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-006 (M2) | NFR-002, NFR-005, NFR-006, NFR-009 | Add M2 lines: NFR-002 BCrypt via Spring Security; NFR-005 health check the day before each demo; NFR-006 also logs submission and assignment; NFR-009 confirmed at the M2 architecture review. Original M1 wording is kept above the new line (NFR-002, NFR-005, NFR-009) or as a "Was:" note (NFR-006). | The technology and hosting decisions (DEC-004, ARC-03) and ERD v2 made these criteria concrete and testable. | Requirements: four NFRs. Data: AuditEntry.ClientId and FromStatus/ToStatus (NFR-006). Security: BCrypt (NFR-002). Testing: code review, health check, audit lifecycle test. Schedule: low. Risk: R-14 (Supabase pause). | Eduard Herman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.5 (NFR-009) and v1.6 (NFR-002, NFR-005, NFR-006) | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-007 (M2) | FR-008 | Add a second acceptance criterion: when two handlers accept the same unassigned request at the same time, exactly one succeeds and the other receives a conflict message. The original criterion is kept. | A2 Task 2 and ASR-002 showed that concurrent assignment was not covered. | Requirements: FR-008. Data: Request.Version and partial unique index on RequestHandler. Design: DEC-006 optimistic locking. API: API-08 returns 409. Testing: ConcurrentAssignmentTest. Schedule: low. Risk: R-17. | Eduard Herman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.5 | Chanri Du Randt, Clarissa Bierman, 30/09/2026 |
| CR-008 (M2) | Stakeholder roles | System roles named REQUESTER (Client), HANDLER (Service Handler) and MANAGER (CivicConnect Management). Requirement wording unchanged. | Clarification so the requirements, ERD v2 and Spring Security roles use the same names. Prototype V1 still uses STAFF and MANAGEMENT. | Requirements: none. Data: Employee.Role values (V2 migration). Security: role names in JWT claims (DEC-010). Testing: role tests. Schedule/cost: none. Risk: none. | Chanri Du Randt, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.5 | Clarissa Bierman, Eduard Herman, 30/09/2026 |
| CR-009 (M2) | New section: Assumptions and Dependencies | Added A-01 to A-05 and D-01 to D-02. | M2 decisions depend on assumptions that were not written down in M1. | Requirements: none. Design: links to ARC-03, DEC-004, DEC-008. Risk: R-09, R-14, R-15, R-19, R-20. | Chanri Du Randt, 30/09/2026 | No (new section) | Accept - applied in PED v1.5 | Clarissa Bierman, Eduard Herman, 30/09/2026 |
| CR-010 (M2) | Initial RTM, Initial Risk Register, Forward Engineering Considerations | RTM renamed and extended with M2 columns (split into Table 1 and Table 2). Risk Register renamed and extended with R-10 to R-23. M2 update lines added to Forward Engineering Considerations. Original content kept. | The M2 brief requires these artefacts to evolve. | Traceability only - no requirement, design or scope change. | Clarissa Bierman, 30/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.5 to v1.6 | Chanri Du Randt, Eduard Herman, 30/09/2026 |
| CR-011 (M2) | Constraints table (Time, Cost / Resources) | Added constraint rows after the M1 baseline: Time (M2 due date and presentation, final project dates, other SEN381 deliverables) and Cost / Resources (no budget for premium tools, commercial notification services, paid hosting tiers). | The M1 constraints did not show the real milestone dates or the cost limits that later drove the technology and hosting choices (DEC-004, ARC-03). Recorded here because the change was made to baselined content in v1.1 without a change request at the time. | Requirements: none. Design: supports ARC-03, DEC-004 and the Out of Scope notification exclusion. Scope: none. Schedule: confirms the short M2 and final timelines. Cost: confirms free tiers only. Risk: R-08. | Eduard Herman, 28/09/2026 | Yes (M1 v1.0) | Accept - applied in PED v1.1 (recorded retrospectively in v1.7) | Chanri Du Randt, 29/09/2026 |
| CR-012 (M2) | Constraints table (Time) | Correct the milestone dates: M1 due 9 September (presented 10 September), M2 due 30 September (presented 1 October), M3 due 14 October (presented 15 October), final presentation 18 October, defence 19 to 23 October 2026. | The v1.1 wording said M2 left "only 2 days after Milestone 1 submission" and placed the final presentation before the due date. Both were wrong. | Requirements, design, data/API, security: none. Schedule: confirms two weeks from M2 to M3 and under three weeks to the final presentation, which supports the Time constraint and R-08. Risk: none new. | Chanri Du Randt, 30/09/2026 | Yes (M1 v1.0, via v1.1) | Accept - applied in PED v1.7 | Clarissa Bierman, Eduard Herman, 30/09/2026 |
| CR-013 (M3) | Technology decision matrix; A-03; DEC-004; R-20 | Correct the Angular + Spring Boot team capability score from 1 to 2 (the team has used Java, not Spring Boot or Angular). Add two criteria taken from the ASRs, transaction management and database schema management (10% each), scored for all four options, and scale the original weights to 80%. Move the transaction wording out of the requirement fit row so it is not counted twice. Add learning value to the DEC-004 rationale. | A-03 understated the team's experience: Java was one of the team's university modules; Spring Boot and Angular were not covered. The original criteria did not measure two needs the ASRs depend on: keeping the status change and audit write in one transaction (ASR-002, ASR-003) and versioned SQL migrations for roles, triggers and functions (DEC-008). The ranking does not change: React + ASP.NET Core still scores highest (4.20 against 4.12). | Requirements: none. Design: DEC-004 rationale and trade-offs reworded; the decision itself is unchanged. Data/API, security, testing: none. Scope, schedule and cost: none. Risk: R-20 wording narrowed to Spring Boot and Angular. | Chanri Du Randt 15/10/2026 | Yes (M2 v1.7) | Accept - applied in PED v3.0 | Clarissa Bierman, Eduard Herman, 16/10/2026 |
| CR-014 (M4) | NFR-004 (RTM Table 1 and Table 3; M4 Tables B and E) | Record the NFR-004 informal usability test (MT-33) as deferred: it is not run until the staging site can be prepared so testers can start unaided. | The free Render instance sleeps and takes about 90 seconds to wake (P-07), so a tester cannot start without a developer waking the site first, which would break the "unaided within 5 minutes" criterion. | Requirements: NFR-004 wording unchanged; status Deferred. Scope: NFR-004 (Should) is not verified, so the M4 Scope Completion counts it as Not met (0.0) unless MT-33 is run before submission. Testing: MT-33 stays Not run. Design/data/API, security, cost: none. Risk: R-09, R-15. | Chanri Du Randt, 18/10/2026 | Yes (M1 v1.0 NFR-004; verification planned for M3) | Accept - applied in PED v4.0 | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #38) |
| CR-015 (M4) | Residual risks: AI-assisted code (R-27) | Add a team meeting the day before the presentation to coordinate the presentation, next to the code walkthrough. | Every member must be able to defend all of the work (R-27); a coordination meeting lowers the chance of gaps or contradictions at the defence. | Requirements, design, data/API, security, testing: none. Schedule: one meeting before the presentation. Risk: lowers R-27. | Chanri Du Randt, 18/10/2026 | No (M3 residual-risk table) | Accept - applied in PED v4.0 | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #38) |
| CR-016 (M4) | Team Members & Work Allocation (M1 section) | Record that after M1 the work allocation is tracked in GitHub (commits, pull requests and reviews) instead of in the table. | The table was not kept up to date after M2; GitHub history shows who changed what and when. | Requirements, design, data/API, security: none. Traceability: contribution is read from GitHub; the git alias (CoffeeLover) is recorded under Construction and Configuration; the PED is a binary file that Git cannot merge. Risk: new R-29. | Chanri Du Randt, 18/10/2026 | Yes (M1 v1.0 section; table last updated in M2) | Accept - applied in PED v4.0; see R-29 | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #38) |
| CR-017 (M4) | Assumptions and Dependencies: A-05, D-01 | Add "Exceptions and Differences" under the table: A-05 - the application is staged on Render (prod branch, deployed automatically) and production deployment is on hold; D-01 - two Supabase databases exist, one for testing and one controlled database for staging. | A-05 and D-01 were written in M2, before hosting was chosen, and no longer describe the environment. | Requirements: none. Design: ARC-03 deployment (C-07). Deployment: staging on the Render free plan; the release is still intended as a fixed jar. Risk: R-15 closed; R-14 and R-26 unchanged. | Chanri Du Randt, 18/10/2026 | Yes (M2 v1.5, CR-009) | Accept - applied in PED v4.0 | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #38) |
| CR-018 (M4) | Quality Attributes Considered but Not Treated as ASRs: Independent / elastic scalability; Technical debt register | Replace the M2 revisit trigger: the attribute was revisited in M3 and stays deferred because the free-tier hosting cannot run a realistic load test. Recorded as TD-12. | The M2 trigger ("if load testing at M3 shows one module slowing down the others") could not be applied: the load test only ran locally (R-26). | Requirements: none. Design: ARC-02 unchanged (one deployable). Testing: no representative load test. Risk: R-26. Debt: new TD-12. | Chanri Du Randt, 18/10/2026 | Yes (M2 v1.7) | Accept - applied in PED v4.0 | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #38) |
| CR-019 (M4) | Risk Register (statuses, R-28, R-29); Technical debt register (TD-11, TD-12); ASR Verification (new); Acronyms; change records (milestone added, C-01 to C-09 moved to section 2); RTM Table 3 evidence note; Document Control v4.0 | Bring the registers up to date for the final PED. | Most risks were still marked Open although M3 had closed or mitigated them; attachment links were not recorded as a security risk or as debt; ASR-006 and ASR-007 had no linked evidence; several abbreviations were not defined; change records were spread across the document. | Requirements: none. Traceability: each ASR now links to its tests and result. Security: R-28 records the attachment-link risk. Process: R-29 records the shared-document risk. Scope, schedule, cost: none. | Chanri Du Randt, 18/10/2026 | Yes (M1 v1.0 Risk Register; M2 v1.7 ASRs; M3 v3.0 registers) | Accept - applied in PED v4.0 | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #38) |
| CR-020 (M4) | Data & Persistence Baseline (17.2, 17.4 to 17.12); D-39 | Update the persistence chapter to the schema as built (build scripts plus Flyway V3 to V7) and record the Supabase pool size that fixed D-39. | The chapter still described the M2 design (Version column, AuditEntry fields, EmployeeCategory composite key, migration file names that were never used), so it contradicted the code, ERD v3 and the build scripts. D-39 was confirmed with the Supabase settings and fixed by raising the pool size to 20. | Requirements: none. Design: describes C-01, C-02, C-03 and C-08 as built. Data: documentation only. Security: documents the roles, row level security and audit masking. Testing: none. Risk: D-39 fixed (pooler pool size 20, no code change). | Chanri Du Randt, 18/10/2026 | Yes (M2 v1.7 Data & Persistence Baseline) | Accept - applied in the Final PED | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #39) |
| CR-021 (M4) | Final Project (M4) Closure: new sections 27.3 to 27.9 | Add schedule performance and variance, cost and operational cost, stakeholder validation, decision consequence reflection, deployment/rollback/observability, the final quality and security summary, and known limitations and evolution. | The Master Brief (sections 20.4, 21 and 22) requires these for the final project; the M4 chapter only covered scope. | Requirements, design, data/API: none. Documentation only; items only the team knows are marked [Team to complete]. Risk: none new. | Chanri Du Randt, 18/10/2026 | No (new sections) | Accept - applied in the Final PED | Clarissa Bierman, Eduard Herman, 18/10/2026 (PR #39) |
| CR-022 (M4) | Data & Persistence Baseline (Entities); ERD v3; API-18; ASR-005; TD-03 | Drop the client date of birth: Flyway migration V8__drop_client_date_of_birth.sql, and remove the field from the Client entity, API-18 (GET / PATCH /clients/me) and the requester profile page. Keep the employee date of birth and address. | No requirement uses a requester's date of birth, so POPIA data minimisation says not to keep it (ASR-005, TD-03). The scenario does not mention an existing HR or employee database, so the employee fields are the only staff record and keep their purpose. | Requirements: none. Data: V8 drops client.date_of_birth; the values on the test and production databases are deleted when V8 runs on deploy; audit rows from before V8 keep the old value (append-only) and the audit_log view masks it. API: API-18 no longer returns dateOfBirth; a client that still sends it is not refused (unknown fields are ignored). Security/POPIA: less personal data held. Testing: tests updated; 251 backend and 38 frontend tests pass. Risk: none new. | Chanri Du Randt, 18/10/2026 | Yes (M2 v1.7 ERD v2 change 1; M3 v3.0 TD-03) | Accept - applied in the Final PED and V8 | Clarissa Bierman, Eduard Herman, PR [#39] |

## Controlled Design Changes (C-01 to C-09)

Design changes made during construction (M3). They change how a requirement is met, not the requirement, so they are controlled changes (C-xx) rather than change requests. Moved here from the Milestone 3 Evidence Index (Controlled Changes) in v4.0 so that every change record is in one place; each record shows the original decision, the evidence, the revised decision and the consequence.

| ID | Original decision | Evidence / problem | Revised decision | Consequence |
| --- | --- | --- | --- | --- |
| C-01 (M3) | DEC-006: optimistic locking with a Version column; clients send the version on API-08, API-09 and API-12. | Every write is already re-checked against the current state (state machine, handler check) and the partial unique index guards double assignment. A version adds client state for little gain. R-17 named pessimistic locking as its contingency. | Each change loads the request with SELECT ... FOR UPDATE, so concurrent changes run one after the other and are re-checked. No version field in the API. | Two accepts at once: exactly one succeeds, the other gets 409 ALREADY_ASSIGNED. Priority and reassignment are last-write-wins with no "updated by someone else" message (TD-05). VERSION_CONFLICT is unused. |
| C-02 (M3) | DEC-012: RequestStatusChangedEvent and an AuditListener write AuditEntry rows. | Audit written by application code is skipped by any code path or SQL that forgets the event. | A SECURITY DEFINER trigger on each audited table writes old and new row JSON into audit_entry in the same transaction; append-only triggers block UPDATE and DELETE. | Every change is audited, including changes outside the API. The request history is built from row JSON in AuditService. Requesters see status changes only through the V5 function. |
| C-03 (M3) | M2: one database login for the application. | Defence in depth for ASR-001 and ASR-005: a bug in a Java check should not expose other data. | V3 adds roles civicconnect_client, _staff and _management; each transaction switches to the user's role. Management can read client contact columns only, never date of birth or password. | More grants to maintain when tables change. Tested by databaseRoleBlocksRequester. M3 review: the audit table and missing row level security still exposed data (D-21); fixed by C-08. |
| C-04 (M3) | API & Integration Design 21.7: rate limiting deferred. | Login could be brute-forced and one client could flood the API. | Login lockout per email (5 failures / 15 min); per-IP login limit (20/min); per-account (120/min) and per-IP (300/min) API limits; registrations per email (5/h). 429 with Retry-After. | Counters are in memory: correct for one instance (R-24, TD-02). Load tests from one machine must raise the per-IP limit. |
| C-05 (M3) | CR-008: roles HANDLER and MANAGER. | The database, backend and API already used STAFF and MANAGEMENT; the frontend translated between them. | One set of names everywhere: REQUESTER, STAFF, MANAGEMENT. The UI shows "Staff" and "Manager". | Breaking change to the role values in API-02/API-03 (recorded in the Endpoint Contract). Saved sessions log in again once. |
| C-06 (M3) | DEC-008: first manager password from an environment variable. | No bootstrap existed: a clean database had no manager. | The build script creates a default manager (admin@gmail.com) with a BCrypt-hashed password. | Known default credential: change it at first login on any shared database (R-25). |
| C-07 (M3) | ARC-03: one jar serving Angular and the API; no CORS in production. | Development works through the ng serve proxy, so the CORS rule is unused. The single jar was built in M3. | Keep ARC-03. Trade-off: frontend and backend deploy and scale together; static files can move to a CDN later. | Built in M3: the Dockerfile packages the Angular build into the jar; Angular routes fall back to index.html; static files are public and all data stays under /api; a public health check (API-27). The CI "Deployment image" job builds and starts the image on every push. Render's free plan deploys the prod branch only after the checks pass (render.yaml). Free-plan trade-off: the instance sleeps after 15 minutes without traffic and takes a minute or more to wake (R-15). |
| C-08 (M3) | C-03 / DEC-007: table and column grants per role; staff and management read audit_entry directly; the app login role may create objects (for Flyway's history table). | The M3 code review found that staff and management could read client personal values through audit_entry, the requester role could read every client, request and internal note, and the app role could create a to_jsonb overload that the audit trigger would run as the owner (D-19, D-21). | V6: the app role cannot create objects; SECURITY DEFINER functions search pg_catalog first; staff and management read the audit trail through the audit_log view (client personal values hidden, staff only see request history); row level security limits requesters to their own account, requests and visible notes; staff may update only their own password. | The database now holds for requesters and audit reads even if a Java check is missed. Staff can still read every request at the database level (the application limits them to their categories). More policies to maintain. Tested by DatabaseRolesIntegrationTest. |
| C-09 (M3) | API-01 returns 201 with the new account, or 409 if the email exists. Staff passwords are set only by Management (API-21). | A 409 tells anyone whether an email address has an account, which undoes the login timing protection (D-25). Staff and the default manager had no way to change their own password in the app (D-26, R-25). | API-01 returns 202 with the same message for a new and an existing email; nothing changes for an existing account. API-26 PATCH /employees/me/password lets staff and managers change their own password (current password required). | Someone who forgot they registered is told to log in instead of "already registered". The default manager can change the password from the My account screen. |

## Team Members & Work Allocation

| Team Member | Document part |
| --- | --- |
| Chanri Du Randt | M1: Problem & Business Need, Stakeholder Analysis, Forward Engineering Considerations, Engineering Decision Log M2: Architecturally Significant Requirements, Architecture Decision Records, Technology Stack, Data & Persistence Baseline, Change Request Register, User Interface Design |
| Clarissa Bierman | M1: Initial RTM, Initial Risk Register, Github and team governance, Team Working Agreement M2: Assumptions and Dependencies, End-to-End Traces, Risk Register (R-14 to R-23), Initial Design Decisions, Deployment Compatibility, Implementation Status, GitHub & Team Governance update (DEC-013) |
| Eduard Bernard Kruger Herman | M1: Scope Baseline, Requirements & acceptance criteria, Constraints M2: API & Integration Design (DEC-009, DEC-010), constraint updates (v1.1) |

Note: GitHub commits can be used to track who did which parts in the code base and any document updates after Milestone 1, therefore no further work allocation is recorded in this document (CR-016).

# Acronyms & Abbreviations

The following terms are needed to understand this document.

| Acronym | Full name |
| --- | --- |
| RTM | Requirements traceability matrix |
| POPIA | Protection of Personal Information Act |
| PED | Project Engineering Document |
| PR | Pull Request |
| NFR | Non-Functional Requirement |
| FR | Functional Requirement |
| CI | Continuous Integration |
| RBAC | Role-Based Access Control |
| API | Application Programming Interface |
| UI | User Interface |
| MVP | Minimum Viable Product |
| MoSCoW | Must / Should / Could / Won't-this-round |
| AI | Artificial Intelligence |
| REST | Representational State Transfer |
| JSON | JavaScript Object Notation |
| HTTP | Hypertext Transfer Protocol |
| HTTPS | Hypertext Transfer Protocol Secure |
| JWT | JSON Web Token |
| DTO | Data Transfer Object |
| CORS | Cross-Origin Resource Sharing |
| SPA | Single-Page Application |
| RFC | Request for Comments (the IETF's numbered standards documents, such as RFC 7519) |
| OWASP | Open Worldwide Application Security Project |
| ACID | Atomicity, Consistency, Isolation, Durability |
| ADR | Architecture Decision Record |
| ASR | Architecturally Significant Requirement |
| CR | Change Request |
| ERD | Entity Relationship Diagram |
| JDK | Java Development Kit |
| JPA | Jakarta Persistence API |
| LTS | Long-Term Support |
| SPOF | Single Point of Failure |
| SQL | Structured Query Language |
| TLS | Transport Layer Security |
| CLI | Command Line Interface |
| HS256 | HMAC with SHA-256 (JWT signing algorithm) |
| IDE | Integrated Development Environment |
| IETF | Internet Engineering Task Force |
| ORM | Object-Relational Mapping |
| XSS | Cross-Site Scripting |
| ASP.NET | Active Server Pages .NET (Microsoft web framework) |
| BI | Business Intelligence |
| CDN | Content Delivery Network |
| CPU | Central Processing Unit |
| CRLF | Carriage Return + Line Feed (Windows line endings) |
| DB | Database |
| E2E | End-to-End (system tests through the browser) |
| EF | Entity Framework (.NET ORM) |
| FK | Foreign Key |
| GB / MB | Gigabyte / Megabyte |
| GPL | GNU General Public License |
| IP | Internet Protocol (address) |
| JDBC | Java Database Connectivity |
| JSONB | PostgreSQL binary JSON type |
| M1 to M4 | Milestone 1 to Milestone 4 |
| MIT | MIT License (open-source licence) |
| MVC | Model-View-Controller |
| PK | Primary Key |
| RAM | Random Access Memory |
| SDK | Software Development Kit |
| SMS | Short Message Service |
| SSO | Single Sign-On |
| UQ | Unique (constraint, in the ERD) |
| URI | Uniform Resource Identifier |
| URL | Uniform Resource Locator |
| UTC | Coordinated Universal Time |
| XML | Extensible Markup Language |

# Problem Statement

CivicConnect currently has a manual, slow and disconnected process for managing service requests from their clients. Overall handling of the service requests include emails, telephone calls, WhatsApp messages, spreadsheets and paper records. Their current process results in duplicated, overlooked or incorrectly assigned requests. Due to the manual handling of service requests, there is poor visibility on request handling including the current state of the request (received, assigned, delayed, resolved and closed), the request handler and their actions as well as trouble conducting audits and reporting on service requests. Currently, CivicConnect is struggling to view the progression of the requests and therefore management cannot track and manage outstanding, overdue and resolved work. Furthermore, CivicConnect is struggling to prioritize their requests and manage the confidentiality and personnel access of the requests and client information.

## Business Need

They want a digital platform to help manage their service requests. They want to trace, log and manage their requests, and personnel accessing the request and request issuer. The solution will allow central supervision and data collection regarding requests to inform audits and reporting. It will also manage communications between the request handler and request issuer. It will also manage the entire request register in a way that minimizes user error by using validation and automating request management where possible.

# Stakeholder Analysis

## Client & User

| Stakeholder | Description | Need | Priority | Influence | Interest |
| --- | --- | --- | --- | --- | --- |
| Service Requester | They are CivicConnect’s clients that requests services. | Must be able to create and log in to an account, be able to issue a request easily and track the progression of the request, and contact CivicConnect with queries regarding the service. | High | High | High |
| Service Handler | They are the CivicConnect employees handling the request. | Must be able to view the assigned request, log details regarding the request, change the status of the request and contact the issuer of the request if needed. | Medium | Medium | High |
| CivicConnect Management | They are the upper management of CivicConnect that need to audit service requests and report on requests. | Must be able to issue requests to staff, manage personnel with access to the request, track the requests’ lifecycle, alter requests, view report details and generate reports on requests. | High | High | High |

## Development

| Stakeholder | Description | Need | Priority | Influence | Interest |
| --- | --- | --- | --- | --- | --- |
| Developers | The software engineers building the digital platform requested by CivicConnect. | Must have thorough description of the digital platform CivicConnect wants including detailed requirements and process flows involved with the request lifecycle. Must also have access to the necessary technology and resources to create the digital platform and support documents. | Low | Medium | Medium |

## Other

| Stakeholder | Description | Need | Priority | Influence | Interest |
| --- | --- | --- | --- | --- | --- |
| Government | Laws regarding software and privacy. | All client data must comply to the laws and regulations set by the governing bodies of the countries CivicConnect conducts business in. Specifically, the POPIA law (National Treasury, no date) regarding data privacy and usage of people’s personal information. | High | High | Low |

## Stakeholder Conflicts

Management wants to control and report on all requests while some service requesters may want confidentiality surrounding a request. Furthermore, management control of sensitive requests will necessitate reduced visibility into requests they are not authorized to view on request handlers’ side, might complicate or slow down their work.

There may be conflicts between the service requesters and CivicConnect’s managers as the Service Requesters want to be able to easily issue requests while CivicConnect’s management wants validation of users and requests that may make usage of the digital platform more complicated.

There could also be conflict between the service handlers and upper management of CivicConnect as the validation and request lifecycle oversight the digital platform must enforce could impede service handling by increasing overhead involved with request handling and limiting handler autonomy.

There also exists a conflict between management’s desire for comprehensive reports and the South African government’s POPIA law that strictly regulates the use of personal information. This means that reports generated on service requests should prioritize privacy over comprehensiveness.

The software engineers designing the digital platform desired by CivicConnect need detailed requirements from their management. However, limitations may have to be placed on the management’s desired features and changes in the desired features, due to project constraints.

## Stakeholder Derived Requirements

The following functional requirements were derived from the needs captured by the stakeholder analysis: FR-001 to FR-013 (covering Requester, Staff and Management capabilities). FR-014 and FR-015 are derived from platform/security and scope constraints rather than a specific stakeholder need. FR-016 (Management sets priority) was added at M2 through CR-003, based on DEC-003.

The following non-functional requirements were derived from the needs captured by the stakeholder analysis: NFR-004 (Service Requester) and NFR-006 and NFR-009 (both CivicConnect Management). The remaining NFRs are derived from quality, security, team-capability or milestone constraints rather than a specific stakeholder need.

# Scope Baseline

The scope baseline defines exactly what CivicConnect v1 commits to delivering across the SEN381 milestones. It is derived from the Minimum Business Capabilities in the Master Project Brief (Section 3) and is deliberately controlled: additional features are not added unless justified against schedule, cost, quality, security and risk (Master Brief, Section 3.1).

## In Scope

The following items are explicitly included in the CivicConnect v1 commitment. They represent the essential functionality required to prove the business problem is solved within the project’s constraints. Each capability has been selected to deliver clear value while remaining achievable within the agreed schedule, cost, quality, security, and risk boundaries. Together, they form the baseline set of features that requesters, staff, and management can rely on to interact through a controlled, auditable platform without introducing unnecessary complexity or scope creep.

Requester capabilities

- Submit a new service request with category, description, location and optional attachment.

- View the current status of a submitted request.

- View a history/list of previously submitted requests (own requests only).

- Receive feedback in-app when a request's status changes (Assigned, In Progress, Resolved, Closed or Rejected) (CR-005).

Staff capabilities

- View service requests relevant to the staff member's authorised scope.

- Search, filter and sort requests by status, category and date.

- View full request detail, including the audit trail of prior actions.

- Assign or accept responsibility for a request.

- Update request status through controlled state transitions.

- Record comments, actions taken and resolution information (append-only).

- Resolve or close requests where authorised to do so.

Management / oversight capabilities

- View aggregate service activity (open, overdue, resolved, closed).

- Filter activity by category, status and date range.

- Access information sufficient to support accountability and basic service-performance review.

Platform-wide controls

- Authentication and Role-Based Access Control (RBAC) for Requester, Staff and Management roles.

- Management-controlled, fixed category schema (CR-001) (requesters select from a controlled list, not free text).

- An audit trail recording who changed what and when, for every status change.

## Out of Scope

The following are explicitly excluded from the CivicConnect v1 commitment. They are not required to demonstrate the business problem is solved and each carries schedule, cost, security or integration risk disproportionate to its value within the project's constraints.

- Automated multi-channel intake (WhatsApp, email parsing) - all requests enter through a single controlled web form.

- Native mobile applications (iOS/Android) - a responsive web interface only.

- Payment processing or billing functionality.

- Multi-organization / multi-tenant support.

- Real-time chat/messaging between requester and staff.

- Automated SMS/push notifications (in-app status feedback only, see FR-004).

- Predictive analytics or business intelligence dashboards.

- A public API for third-party integration.

- Multi-language/localisation support.

## Deferred / Future Scope

These items are recognised as valuable but are deliberately deferred because the evidence needed to commit to them (cost data, platform research, or downstream design decisions) is not yet available. They may be reconsidered through formal change control (Master Brief, Section 14) once that evidence exists.

- SMS/email notification channel, once a low-cost provider and its limits have been evaluated.

- Exportable/advanced reporting for management, once core reporting needs are validated with users.

- Attachment hardening - file-size limits and virus/malware scanning.

- Automated escalation workflow for overdue requests.

- Single sign-on (SSO) or self-service password reset.

- Migration of historical data from existing spreadsheets/email records.

## Defended Exclusion: Automated Multi-Channel Intake

Exclusion: automated ingestion of requests from WhatsApp, email or telephone into CivicConnect is deliberately excluded from v1, all channels are consolidated into one controlled web-based intake point instead.

Rationale: each additional channel introduces a third-party API dependency (e.g. WhatsApp Business API approval and cost), unstructured-message parsing risk (accuracy of extracting category, location and description), and a wider security surface for handling externally-sourced personal data. None of these are necessary to resolve the root business problem - duplication, lost visibility and weak accountability - which is solved as soon as every request, regardless of its origin, is logged once into a single controlled record.

Ripple effects avoided by excluding it: schedule risk from external API approval delays and an unfamiliar integration's learning curve, recurring cost from message-platform tiers, additional security review for storing third-party message content and additional test surface for channel-specific failure modes. This is consistent with the Master Brief's scope-discipline principle that "a smaller, controlled, high-quality solution may demonstrate stronger Software Engineering than a larger unfinished solution."

# Requirements & Acceptance Criteria

Requirements are derived directly from the Minimum Business Capabilities (Master Brief, Section 3) and the Scope Baseline above. Each functional requirement carries a unique ID, a source, a MoSCoW priority and testable acceptance criteria so it can be carried into the Initial RTM without rework. Priorities follow MoSCoW (Must / Should / Could / Won't-this-round).

## Functional Requirements(FR)

| ID | Requirement | Source | Priority | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| FR-001 | Requester submits a new service request (category, description, location, optional attachment). | Requester capability | Must | Given a logged-in requester, when a request is submitted with all required fields, then the system creates it with a unique reference number, status "New" and a timestamp, and confirms submission on-screen. |
| FR-002 | Requester views the current status of a specific request. | Requester capability | Must | Given a requester opens "My Requests" and selects a request, then current status, last-updated time and any staff-visible comments are displayed. |
| FR-003 | Requester views a history/list of previously submitted requests. | Requester capability | Must | Given a requester views their request list, then only their own requests are shown, sorted by date submitted (most recent first). |
| FR-004 | System gives the requester feedback when status changes (Assigned, In Progress, Resolved, Closed or Rejected). CR-005. Was: "(accepted/rejected/updated/completed)". | Requester capability | Should | Given staff change a request's status, then the requester sees the updated status and any resolution note the next time they view the request or an in-app indicator. |
| FR-005 | Staff view requests in the categories assigned to them by Management. CR-002. Was: "Staff view requests within their authorised scope." | Staff capability | Must | Given a staff member logs in, then only requests in the categories assigned to them by Management are listed; other requests are not visible and cannot be opened through the API. CR-002. Was: "...only requests within their assigned category/permission scope are listed, other requests are not visible." |
| FR-006 | Staff search, filter and sort requests. | Staff capability | Must | Given a staff member applies a status/category/date filter or sort, then the list updates to match the criteria within 2 seconds under normal load. |
| FR-007 | Staff view full request detail, including audit history. | Staff capability | Must | Given a staff member opens a request, then all submitted fields and a historical log of prior actions are displayed. |
| FR-008 | Staff assign or accept responsibility for a request. | Staff capability | Must | Given an unassigned request within scope, when a staff member accepts it, then the request is marked assigned to that staff member with a timestamp. Given two handlers attempt to accept the same unassigned request at the same time, then exactly one succeeds and the other receives a message that the request is already assigned. (Added by CR-007.) |
| FR-009 | Staff update request status through controlled transitions. | Staff capability | Must | Given a defined status state machine (New - Assigned - In Progress - Resolved - Closed; New/Assigned - Rejected), an attempted transition outside this set is rejected with an explanatory message. |
| FR-010 | Staff record comments/resolution notes against a request. | Staff capability | Must | Given a staff member adds a comment, then it is stored with author and timestamp and cannot subsequently be edited or deleted (append-only). |
| FR-011 | Staff resolve or close authorised requests. | Staff capability | Must | Given a staff member with close permission, when they close a request, then it becomes read-only and no further status changes are accepted. |
| FR-012 | Management view aggregate service activity. | Management capability | Should | Given a management user opens the activity view, then counts of open, overdue, resolved and closed requests are displayed, current as of the last refresh. A request is overdue when it is not Resolved, Closed or Rejected within 7 calendar days of its CreatedAt date. (Added by CR-004.) |
| FR-013 | Management filter activity by category/status/date range. | Management capability | Should | Given a management user applies a filter, then displayed counts and lists recalculate to match the selected criteria. |
| FR-014 | System enforces role-based access control on all functionality. | Platform / Security constraint | Must | Given an unauthenticated or wrongly-roled user attempts to access a staff/management URL directly, then access is denied without exposing the underlying data. |
| FR-015 | System maintains a controlled, Management-defined category schema. CR-001. Was: "admin-defined". | Platform / Scope baseline | Must | Given a requester submits a request, then the category must be chosen from a list maintained by Management users; free-text category entry is not permitted. CR-001. Was: "an admin-maintained list". |
| FR-016 | Management sets the priority of a request (Low, Medium, High). | Management capability (CR-003) | Should | Given a manager opens a request, when they set its priority, then the new priority is saved, shown in staff request lists and recorded in the audit trail. Other roles cannot change priority. |

## Non-Functional Requirements(NFR)

Non-functional requirements are defined so they can be verified with objective evidence during later milestones. Targets marked as design-stage are established now as baseline commitments, with the expectation that they will be validated through testing and monitoring.

| ID | Category | Requirement | Acceptance Criteria / Measurable Target | Priority |
| --- | --- | --- | --- | --- |
| NFR-001 | Performance | Standard pages (request list, dashboard) respond promptly under normal project load. | 95th-percentile page response ≤ 3 seconds at ≤ 20 concurrent users, measured and evidenced. | Should |
| NFR-002 | Security - Authentication | All users authenticate before accessing role-specific functionality, credentials are never stored or transmitted in plain text. | Passwords stored using an industry-standard hashing algorithm (e.g. bcrypt), verified by code/config review. M2 (CR-006): passwords are hashed with BCrypt (Spring Security) and stored only in the PasswordHash column; verified by code review. | Must |
| NFR-003 | Security - Authorisation | RBAC is enforced at both the interface and the server/API layer, not the UI alone. | A direct request to a staff/management endpoint by a requester-role account is rejected (e.g. 403) rather than returning data. | Must |
| NFR-004 | Usability | A first-time requester can submit a request without external instructions. | In an informal test with 3 non-team users, at least 2 of 3 complete request submission unaided within 5 minutes. | Should |
| NFR-005 | Availability | The system is available without unplanned downtime during scheduled demonstrations and milestone presentations. | No unplanned outage during rehearsal or live presentation windows, evidenced by uptime/log check beforehand. M2 (CR-006): the database and application are health-checked the day before each rehearsal and presentation. | Should |
| NFR-006 | Auditability | Every submission, status change, assignment and resolution action is logged with actor, timestamp and before/after state. CR-006. Was: "Every status change and resolution action is logged..." | For a sample request, the audit log reconstructs its full lifecycle end-to-end without gaps. | Must |
| NFR-007 | Data Integrity | A request record cannot be altered outside a controlled status transition without leaving an audit entry. | Any change to a request's core fields outside the defined workflow is either blocked or logged for review. | Must |
| NFR-008 | Maintainability | The codebase follows a documented, consistent structure a new contributor can navigate. | Repository README documents structure, a team member unfamiliar with a module can locate the relevant code within a reasonable, agreed time. | Could |
| NFR-009 | Scalability (design-stage) | The data model anticipates growth beyond the pilot dataset (no hard-coded limits, categories Management-configurable, not hard-coded). CR-001. Was: "categories admin-configurable". | Confirmed at architecture review in Milestone 2, referenced now as a Forward Engineering Consideration. Confirmed at the M2 architecture review (CR-006): no hard-coded limits, categories stored as data, lists paged, and the database size monitored against the Supabase 500 MB limit (Data & Persistence Baseline). | Could |

# Constraints

Constraints are treated as active engineering inputs, not administrative background - they must visibly influence scope, requirements and later architecture decisions (Master Brief, Section 4).

| Constraint | CivicConnect-Specific Description | Engineering Implication |
| --- | --- | --- |
| Scope | The team commits to a controlled MVP covering the three capability groups (Requester, Staff, Management) defined in the Scope Baseline, nothing beyond that is committed without change control. | Any proposed addition must be assessed for schedule/cost/security/risk impact before acceptance (Master Brief, Section 14) - it cannot be silently added mid-build. |
| Time | Delivery is fixed to SEN381 milestones within 2 months, with no built-in flexibility beyond formally accepted exceptional circumstances. | Requirements and scope must be substantially settled at M1 so M2 architecture work is not delayed, unfamiliar technologies carry disproportionate schedule risk and must be flagged early. |
| Time | Milestone 1 was due on 9 September 2026 (presented 10 September 2026). Milestone 2 is due on 30 September 2026 with a presentation on 1 October 2026, leaving three weeks after Milestone 1 submission for architecture and initial implementation work. | Architecture decisions must be finalized quickly and major requirement changes cannot be accommodated after M1. |
| Time | Milestone 3 is due on 14 October 2026 (presented 15 October 2026), the final project presentation is on 18 October 2026 and the project defence runs from 19 to 23 October 2026, leaving two weeks between M2 and M3 and under three weeks to the final presentation. M4 (study guide v3.0): M1 and M2 were presented the day after the due date (Thursday 10 September and Thursday 1 October 2026). M3 was presented as a video, submitted on Friday 16 October 2026 instead of the live presentation on 15 October. The final project is due on 18 October 2026 and the final project defence is in week 7 (19 to 22 October 2026). | Only essential functionality should be implemented; lower-priority features may need to be deferred to future scope. |
| Time | Team members must simultaneously complete other SEN381 deliverables, including Assignments 2 and 3, during the project period. | Development activities must be planned around academic workload, reducing available development hours and increasing schedule risk. |
| Cost / Resources | A 3-student team with no dedicated budget, the project must rely on free-tier or low-cost tooling and hosting. | Technology and hosting choices at M2 must be checked against free-tier limits (storage, compute, request caps), limits must be documented as a Forward Engineering Consideration now. |
| Cost / Resources | The project has no dedicated budget for premium development software, enterprise tools, or commercial services. | Free and open-source software such as GitHub, Visual Studio Code, and free database solutions must be used wherever possible. |
| Cost / Resources | Commercial notification services such as SMS gateways, WhatsApp Business APIs, or paid email platforms may require subscription fees. | Automated external notification features are excluded from the MVP and replaced with in-platform notifications. |
| Cost / Resources | Paid cloud hosting tiers and managed database services may exceed the team's available budget. | Hosting and deployment must remain within free-tier limits, and system design must consider storage, bandwidth, and compute restrictions. |
| Quality | Quality claims must ultimately be backed by measurable test/defect evidence at M3, not by assertion. | Acceptance criteria must be written in testable form now (see Requirements & Acceptance Criteria), vague criteria cannot later produce credible quality evidence. |
| Security | Requests and accounts contain personal data (contact details, request descriptions), security is a lifecycle-wide responsibility from M1, not a late add-on. | RBAC and audit-trail requirements (FR-014, NFR-002/003/006) must be baselined now - reworking access control after the data/UI layer is built is high-effort and high-risk. |
| Team capability | All three members are individually examinable on the full system, no member may specialise to the exclusion of understanding the whole. | Documentation, requirement ownership and code must be reviewed across the team, not siloed - this also underpins the two-reviewer GitHub approval control. |

## Trade-off / Ripple-Effect Analysis

Selected interaction: Security constraint versus Schedule constraint.

Baselining RBAC and an audit trail from Milestone 1 (NFR-002, NFR-003, NFR-006) commits M2 development time to authentication and access-control work before any request-management feature can be demonstrated. This reduces the schedule available for additional functionality within a fixed timeline.

The alternative - deferring access control to a later milestone to move faster now - was considered and rejected. Reworking authorisation into a data model and UI that were not designed for it is a well-understood source of rework: routes, queries and views built without role checks typically require re-architecture, not incremental patching, once RBAC is added. Given CivicConnect handles personal requester data, deferring this control also creates an unacceptable window of unmanaged risk.

Consequence accepted: a smaller initial feature set, in exchange for an auditable, access-controlled foundation that will not need to be re-architected later. This directly trades Scope against Security and Quality under a fixed Schedule constraint, consistent with the Master Brief's principle that a smaller, controlled, high-quality solution can demonstrate stronger Software Engineering than a larger, unfinished one (Section 3.1).

# Assumptions and Dependencies

These assumptions and dependencies were identified during Milestone 2. Each is linked to the decision or risk it affects so it can be revisited when evidence changes.

| ID | Assumption / Dependency | Why it matters | Link |
| --- | --- | --- | --- |
| A-01 | Pilot load stays at or below 20 concurrent users and under 10 000 requests a year. CivicConnect has not supplied real figures. | Justifies one application instance and one database. | ASR-004, R-09 |
| A-02 | Attachments are stored as a URL only (AttachmentUrl). File storage and hardening stay in deferred scope. | Keeps the database small and avoids storing files on a free host. | Deferred Scope, Data & Persistence |
| A-03 | The team has used Java, but no team member has used Spring Boot or Angular before (corrected in v3.0, CR-013). The team has C#/ASP.NET and JavaScript/Node.js experience, but no one has used React either. The learning curve is accepted and managed through R-20 and D-02. | Drives the technology choice and the learning-curve risk. | DEC-004, R-20 |
| A-04 | The Supabase free plan stays available with the current limits (500 MB, pause after 1 week of inactivity, no automatic backups) (Supabase, 2026a). | The database tier depends on it. | ARC-03, R-14 |
| A-05 | A free application host that can run a Java 21 jar with about 512 MB of memory can be found before the final demo. | The application tier depends on it. | ARC-03, R-15 |
| D-01 | Supabase PostgreSQL 17 via the Supavisor session pooler. Not connected yet: the prototype runs against a local PostgreSQL 18.4 database, so Flyway SQL must stay compatible with PostgreSQL 17. | Flyway runs on start-up, so the application cannot start without the database. | ARC-03, DEC-008 |
| D-02 | Spring Boot 4.1 official documentation for configuration (many tutorials are still for Spring Boot 3). | Wrong configuration from old tutorials breaks Flyway and security set-up. | DEC-004, R-19 |

## Exceptions and Differences from the above table:

A-05: deployment is not yet implemented, and current project is halted on the staging phase until further instruction. The staging phase software is staged on Render (https://civicconnect-pxjj.onrender.com/login). The website is built from the branch “prod” and is updated automatically. However, future deployment is still intended to be a fixed jar release.

D-01: Supabase databases have been set up. There is one for testing that the main branch and all personal coding branches use and then a separate controlled one for staging. User login is not committed in the SQL build query for the prod database setup, instead queries to make users for log in and testing purposes is run in Supabase directly and the details are sent to team members.

(CR-017)

# Requirements Traceability Matrix (v3.0)

The RTM was extended at M2 with ASR, architecture, data, design/interface, technology, implementation and verification columns. M1 requirement IDs and wording are unchanged unless a change request (CR) is referenced. Because the matrix is too wide for one page, it is split into Table 1 (the requirement baseline) and Table 2 (the engineering evidence), both keyed on the same Requirement ID.

Status values: Prototyped (unsecured prototype code exists that does not yet match the API contract) / Approved (baselined, no code yet) / Changed (CR-xxx) / New (CR-xxx) / In Development / Implemented / Confirmed. "Not Yet Implemented" and "Planned" are used where evidence legitimately does not exist yet. Endpoints marked "planned" are the intended interface and will be confirmed when built.

M3 (v3.0): Table 3 extends the matrix with the M3 trace - acceptance criterion, implementation, test cases, expected result, execution evidence and status/defect. Tables 1 and 2 keep their M2 content; only their status and evidence cells were updated, as tracked changes.

## Table 1 - Requirement baseline

| Req ID | Requirement (current wording) | Source / Stakeholder | Priority | Acceptance criteria (measurable) | Status | Change / ADR ref |
| --- | --- | --- | --- | --- | --- | --- |
| FR-001 | Requester submits a new service request (category, description, location, optional attachment). | Service Requester | Must | Request created with a unique reference number, status "New" and a timestamp; submission confirmed on-screen. | Implemented and verified (M3) - see Table 3 | DEC-005, DEC-008 |
| FR-002 | Requester views the current status of a specific request. | Service Requester | Must | Current status, last-updated time and staff-visible comments displayed. | Implemented and verified (M3) - see Table 3 | ARC-01 |
| FR-003 | Requester views a history/list of previously submitted requests. | Service Requester | Must | Only own requests shown, most recent first. | Implemented and verified (M3) - see Table 3 | DEC-002 |
| FR-004 | System gives the requester feedback when status changes (Assigned, In Progress, Resolved, Closed or Rejected). | Service Requester | Should | Updated status and any resolution note shown the next time the requester views the request or an in-app indicator. | Implemented and verified (M3) - see Table 3 | CR-005, DEC-001 |
| FR-005 | Staff view requests in the categories assigned to them by Management. | Service Handler | Must | Only requests in assigned categories are listed; other requests are not visible and cannot be opened through the API. | Implemented and verified (M3) - see Table 3 | CR-002, DEC-002 |
| FR-006 | Staff search, filter and sort requests. | Service Handler | Must | List updates to match status/category/date filter or sort within 2 seconds under normal load. | Implemented (M3) - filter/sort verified; keyword search open (TD-04) | ASR-004 |
| FR-007 | Staff view full request detail, including audit history. | Service Handler | Must | All submitted fields and a historical log of prior actions displayed. | Implemented and verified (M3) - see Table 3 | DEC-007 |
| FR-008 | Staff assign or accept responsibility for a request. | Service Handler | Must | Request marked assigned to that staff member with a timestamp; when two handlers accept at the same time, exactly one succeeds and the other receives a message that the request is already assigned. | Implemented and verified (M3) - see Table 3 | CR-007, DEC-006 |
| FR-009 | Staff update request status through controlled transitions. | Service Handler | Must | Transition outside New - Assigned - In Progress - Resolved - Closed (New/Assigned - Rejected) is rejected with an explanatory message. | Implemented and verified (M3) - see Table 3 | ARC-02, DEC-006, DEC-011 |
| FR-010 | Staff record comments/resolution notes against a request (append-only). | Service Handler | Must | Comment stored with author and timestamp; cannot be edited or deleted. | Implemented and verified (M3) - see Table 3 | DEC-007 |
| FR-011 | Staff resolve or close authorised requests. | Service Handler | Must | Closed request becomes read-only; no further status changes accepted. | Implemented and verified (M3) - see Table 3 | DEC-006 |
| FR-012 | Management view aggregate service activity (open, overdue, resolved, closed). | CivicConnect Management | Should | Counts displayed as of last refresh; overdue = not Resolved/Closed/Rejected within 7 calendar days of CreatedAt. | Implemented and verified (M3) - see Table 3 | CR-004 |
| FR-013 | Management filter activity by category, status and date range. | CivicConnect Management | Should | Counts and lists recalculate to match the selected criteria. | Implemented and verified (M3) - see Table 3 | ASR-004 |
| FR-014 | System enforces role-based access control on all functionality. | Platform / Security constraint (POPIA) | Must | Unauthenticated or wrongly-roled direct URL/API access is denied without exposing data. | Implemented and verified (M3) - see Table 3 | DEC-002, DEC-004, DEC-010 |
| FR-015 | System maintains a controlled, Management-defined category schema. | Platform / Scope Baseline | Must | Category chosen from a list maintained by Management; no free-text category. | Implemented and verified (M3) - see Table 3 | CR-001, DEC-008 |
| FR-016 | Management set the priority of a request (Low / Medium / High). | CivicConnect Management (DEC-003) | Should | Priority saved, shown to staff in the request list and recorded in the audit trail; staff and requesters cannot change it. | Implemented and verified (M3) - see Table 3 | CR-003, DEC-003, DEC-012 |
| NFR-001 | Standard pages respond promptly under normal project load. | Quality constraint | Should | 95th-percentile response 3 seconds or less at up to 20 concurrent users. | Measured (M3) - local run passed; staging run open | ASR-004 |
| NFR-002 | All users authenticate; credentials never stored/transmitted in plain text. | Government (POPIA) / Security | Must | Passwords hashed with BCrypt (Spring Security) and stored only in PasswordHash; verified by code review. | Implemented and verified (M3) - see Table 3 | CR-006, DEC-004, DEC-010 |
| NFR-003 | RBAC enforced at interface and server/API layer, not UI alone. | Security constraint | Must | Direct staff/management endpoint call with a requester-role token returns 403 and no data. | Implemented and verified (M3) - see Table 3 | ARC-01 |
| NFR-004 | First-time requester can submit a request without external instructions. | Service Requester | Should | 2 of 3 non-team users complete submission unaided within 5 minutes. | Deferred- current staging environment needs to be prepared for testers due to slow startup time, making completely unaided request impossible as coordination is needed between developer and tester. | CR-014 |
| NFR-005 | System available without unplanned downtime during demonstrations. | Milestone/presentation constraint | Should | No unplanned outage during rehearsal/live windows; database and app health-checked the day before each. | Partly implemented (M3) - 503 handling done; health check is a team step | CR-006, ARC-03, R-14 |
| NFR-006 | Every submission, status change, assignment and resolution action is logged with actor, timestamp and before/after state. | CivicConnect Management | Must | Audit log for a sample request rebuilds its full lifecycle without gaps. | Implemented and verified (M3) - see Table 3 | CR-006, DEC-007, DEC-012 |
| NFR-007 | A request record cannot be altered outside a controlled transition without an audit entry. | Security / Quality constraint | Must | Out-of-workflow change is blocked or logged. | Implemented and verified (M3) - see Table 3 | DEC-006, DEC-007 |
| NFR-008 | Codebase follows a documented, consistent structure a new contributor can navigate. | Team capability constraint | Could | README documents structure; module code can be located within an agreed time. | Open (M3) - README needs updating (TD-09) | ARC-02 |
| NFR-009 | Data model anticipates growth beyond the pilot dataset. | CivicConnect Management | Could | No hard-coded limits, categories Management-configurable, lists paged, database size monitored against the Supabase 500 MB limit. | Implemented and verified (M3) - see Table 3 | CR-001, CR-006, DEC-005 |

## Table 2 - Engineering evidence

| Req ID | ASR link | Architecture / module | Data / persistence impact | Design / interface decision | Technology decision | Implementation evidence | Verification evidence | ADR / risk ref |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FR-001 | ASR-002, ASR-005 | Requests (RequestController, RequestService) | Insert Request (Status New, RefNum unique, CatId and RequesterId FKs) and AuditEntry CREATED (ClientId) in one transaction. | API-04 POST /api/v1/requests (DEC-009); DTO validated server-side; RefNum generated by the service. | Spring Web, Spring Data JPA, Bean Validation, PostgreSQL (DEC-004, DEC-005) | Implemented (M3) - see Table 3 | See Table 3 | DEC-005, DEC-006, DEC-008, DEC-009, R-22 |
| FR-002 | ASR-001 | Requests | Read Request by id where RequesterId = logged-in client. | API-06 GET /api/v1/requests/{id} with ownership check; another client's request returns 404 (DEC-009). | Spring Web, JPA | Implemented (M3) - see Table 3 | See Table 3 | ARC-01, DEC-002, DEC-009, DEC-010, R-10 |
| FR-003 | ASR-001, ASR-004 | Requests | Index on (RequesterId, CreatedAt); paged in the database. | API-05 GET /api/v1/requests/mine?page=&size= (DEC-009). | Spring Data Pageable | Implemented (M3) - see Table 3 | See Table 3 | DEC-005, DEC-009 |
| FR-004 | ASR-006 | Requests + Angular request-detail view | Reads Request.Status and AuditEntry. | API-06 shows status and requester-visible comments on the next view (no push - out of scope). RequestStatusChangedEvent is the extension point for later notifications (DEC-012). M4: no status-change event exists since C-02; see TD-14. | Angular | Implemented (M3) - see Table 3 | See Table 3 | DEC-001 M2 update, DEC-012, CR-005 |
| FR-005 | ASR-001 | Access + Requests | EmployeeCategory junction table; list queries filter CatId in the handler's categories. | API-07 GET /api/v1/requests limited to the handler's categories; API-16 GET/PUT /api/v1/employees/{id}/categories (Management). Requests calls the Access module service to check category scope; never reads Access tables directly. | Spring Security, JPA | Implemented (M3) - see Table 3 | See Table 3 | DEC-002, DEC-009, DEC-010, ARC-01, ARC-02, CR-002, R-10 |
| FR-006 | ASR-004 | Requests | Composite index (CatId, Status, CreatedAt); paging in the database. | API-07 GET /api/v1/requests?status=&categoryId=&from=&to=&page=&size=&sort= (DEC-009). | Spring Data Pageable | Implemented (M3) - see Table 3 | See Table 3 | DEC-005, DEC-008, DEC-009 |
| FR-007 | ASR-003 | Requests | AuditEntry read by index (ReqId, CreatedAt). | API-06 request detail plus API-11 GET /api/v1/requests/{id}/audit. | JPA | Implemented (M3) - see Table 3 | See Table 3 | DEC-007, DEC-009, DEC-012 |
| FR-008 | ASR-002 | Requests | RequestHandler row; partial unique index (one active handler); Request.Version. | API-08 POST /api/v1/requests/{id}/assignment with {version}; stale version returns 409 VERSION_CONFLICT, an existing active handler returns 409 ALREADY_ASSIGNED. Publishes RequestAssignedEvent (DEC-012). | JPA @Version, @Transactional | Implemented (M3) - see Table 3 | See Table 3 | DEC-006, DEC-012, CR-007, R-17 |
| FR-009 | ASR-002, ASR-003 | Requests (state machine in RequestService) | CHECK on Request.Status; Version; AuditEntry with FromStatus/ToStatus written in the same transaction. | TransitionPolicy - table-driven transition map (DEC-011), which also supplies allowedTransitions to API-06. API-09 PATCH /api/v1/requests/{id}/status; invalid transition 422, conflict 409. | Spring Boot, JPA, PostgreSQL | Implemented (M3) - see Table 3 | See Table 3 | ARC-02, DEC-006, DEC-007, DEC-011, DEC-012, R-16, R-17, R-18 |
| FR-010 | ASR-003 | Requests | AuditEntry type COMMENT, insert only; trigger blocks UPDATE/DELETE. | API-10 POST /api/v1/requests/{id}/comments; no edit/delete endpoint. | JPA @Immutable, Flyway trigger | Implemented (M3) - see Table 3 | See Table 3 | DEC-007, DEC-009 |
| FR-011 | ASR-002 | Requests | ClosedAt set; service rejects changes when Closed/Rejected. | API-09 PATCH /api/v1/requests/{id}/status (MANAGER or authorised HANDLER); Closed and Rejected are terminal in TransitionPolicy (DEC-011). | JPA | Implemented (M3) - see Table 3 | See Table 3 | DEC-006, DEC-011 |
| FR-012 | ASR-004, ASR-005 | Reporting (read-only) | Aggregate counts only, no personal fields; index (Status, CreatedAt). | API-17 GET /api/v1/reports/activity (counts only). | JPA queries | Implemented (M3) - see Table 3 | See Table 3 | DEC-009, R-03, CR-004 |
| FR-013 | ASR-004 | Reporting (read-only) | Same aggregate queries with filters. | API-17 GET /api/v1/reports/activity?from=&to=&categoryId=&status= | JPA queries | Implemented (M3) - see Table 3 | See Table 3 | DEC-009, ASR-004 |
| FR-014 | ASR-001 | Access (Spring Security filter chain) | Employee.Role; clients are REQUESTER. | API-02 POST /api/v1/auth/login and API-03 GET /api/v1/auth/me; JWT bearer token validated on every call (DEC-010); role rules per path; Angular route guards are UI only. | Spring Security, OAuth2 Resource Server (JWT) | Implemented (M3) - see Table 3 | See Table 3 | ARC-01, DEC-002, DEC-004, DEC-010, R-10, R-11 |
| FR-015 | ASR-002 | Requests (reference data) | Category table, Active flag, CatName unique, FK from Request; seeded by Flyway. | API-13 GET, API-14 POST, API-15 PATCH /api/v1/categories; create/update Management only; no delete - categories are deactivated. | Flyway, JPA | Implemented (M3) - see Table 3 | See Table 3 | DEC-008, DEC-009, CR-001, R-13 |
| FR-016 | ASR-003 | Requests | Request.Priority; AuditEntry of type PRIORITY_CHANGE written by AuditListener (DEC-012). | API-12 PATCH /api/v1/requests/{id}/priority (MANAGER only). | Spring Security, JPA | Implemented (M3) - see Table 3 | See Table 3 | DEC-003, DEC-009, DEC-012, CR-003 |
| NFR-001 | ASR-004 | All modules | Indexes and paging above. | Paging on all list endpoints (API conventions: maximum page size 100). | HikariCP, PostgreSQL | Implemented (M3) - see Table 3 | See Table 3 | ARC-02, DEC-009 |
| NFR-002 | ASR-001 | Access | PasswordHash column only. | API-01 POST /api/v1/auth/register and API-02 POST /api/v1/auth/login; BCrypt hash; signed JWT (DEC-010). | Spring Security BCrypt, OAuth2 Resource Server (JWT) | Implemented (M3) - see Table 3 | See Table 3 | DEC-004, DEC-010, R-11 |
| NFR-003 | ASR-001 | Access | - | URL/role rules plus @PreAuthorize, and object-level checks in the service layer (API & Integration Design, the "Validation and Security at the Boundary" section). | Spring Security | Implemented (M3) - see Table 3 | See Table 3 | ARC-01, DEC-010, R-10 |
| NFR-004 | - | Angular front end (User Interface Design) | - | Wireframe 1: one short form, plain labels, inline validation messages (Figure 4). | Angular | Requester screens built (M3) | Informal 3-user test not run yet | User Interface Design, DEC-009 |
| NFR-005 | ASR-007 | Deployment (ARC-03) | Supabase free plan: pauses after 1 week idle; manual pg_dump backups. | 503 SERVICE_UNAVAILABLE when the database is unreachable (error model). | Supabase; app host deferred | Implemented (M3) - see Table 3 | See Table 3 | ARC-03, R-14, R-15 |
| NFR-006 | ASR-003 | Requests | AuditEntry actor (EmpId or ClientId, CHECK), FromStatus/ToStatus. | AuditListener (Observer through Spring application events) writes the audit entry inside the same transaction as the change (DEC-012). | Spring application events, JPA | Implemented (M3) - see Table 3 | See Table 3 | DEC-006, DEC-007, DEC-012, R-18 |
| NFR-007 | ASR-002, ASR-003 | Requests | CHECK constraint, audit trigger, Version. | All writes only through RequestService; transitions checked by TransitionPolicy (DEC-011). | JPA, PostgreSQL | Implemented (M3) - see Table 3 | See Table 3 | DEC-006, DEC-007, DEC-011, R-18 |
| NFR-008 | - | All modules (packages per module) | - | Modules call each other only through public services; CI build check on every PR (DEC-013). | Maven, README | Implemented (M3) - see Table 3 | See Table 3 | ARC-02, DEC-013, R-16 |
| NFR-009 | ASR-004 | Requests, Reporting | No hard-coded limits; Category table; size monitored vs 500 MB. | Paging on all list endpoints (API conventions). | PostgreSQL, Flyway | Implemented (M3) - see Table 3 | See Table 3 | DEC-005, DEC-008, M2 Architecture Review |

## Table 3 - M3 implementation and verification (RTM v3.0)

File locations and line numbers for every test and class named in this document are listed in the Test and Code Reference Index (section 27.10), taken from the final release commit.

Each row continues the requirement in Tables 1 and 2. Test names are JUnit test methods or display names in civicconnect-backend/src/test, Angular specs in civicconnect-frontend/src, and Playwright tests in civicconnect-frontend/e2e (E2E-01 to E2E-03). Defects (D-xx) and technical debt (TD-xx) are in the Milestone 3 Evidence Index (Defects and Quality Interpretation). Execution evidence: "CI Backend job (surefire + JaCoCo report)" is the Backend job of the CI workflow - Maven Surefire runs the unit and integration tests and JaCoCo measures coverage; both reports are uploaded with the run as the artifact backend-test-reports. "CI End-to-end job (Playwright report)" is the End-to-end job; its Playwright report is the artifact e2e-reports. Release run for v3.0.0-rc1: https://github.com/ClarissaBierman/SEN381-Project-CivicConnect/actions/runs/38951977445. M4: “Final outcome(M4) column gives each acceptance criterion its final release [tag e.g. v4.0.0] (commit[hash], confirmed by CI run [#number] on that commit and the manual test log (Summary ant Test build sheets). Earlier columns are kept unchanged as the M3 record.

| Req ID | Acceptance criterion (short) | Implementation / component | Test case(s) | Expected result | Execution evidence | Status / defect | Final outcome (M4) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| FR-001 | Request created with unique reference, status New and time; confirmed on screen | RequestService.create; requester page | RequestServiceTest (submit sets ref, requester, status); fullLifecycleIsAudited; E2E-01; descriptionBoundaries; locationBoundaries | Ref CC-yyyy-nnnnnn, status NEW, createdAt in UTC, confirmation shown | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified | Met - MT-09, MT-10; E2E-01 |
| FR-002 | Current status, last updated and staff-visible comments shown | RequestService.get; CommentViews | RequestServiceTest (requesters only receive visible comments); E2E-01 | Only comments marked visible; no staff names | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified | Met - MT-11; E2E-01 |
| FR-003 | Only own requests, newest first | RequestService.mine (paged); requester page with pager | requesterSeesOnlyOwnRequests; mineHasNoHandler; E2E-02 | Another requester's request never listed or opened (404) | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified | Met - E2E-02; requesterSeesOnlyOwnRequests |
| FR-004 | Updated status and resolution note shown on the next view | statusHistory from V5 request_status_history; requester updates list | statusHistory; statusHistoryAndAllowedTransitions; request-api.service.spec; E2E-01 | Every status with its time, visible notes, newest first | CI Backend job (surefire + JaCoCo report); Frontend job; CI End-to-end job (Playwright report) | Verified (D-12 fixed) | Met - MT-11; E2E-01 (in-app only, CR-005) |
| FR-005 | Only requests in assigned categories; others not openable through the API | RequestAccess.checkStaffScope; category scope in list | staffListIsScoped; RequestServiceTest (outside categories); removingCategoryReleasesRequests | 403 outside scope; list limited to scope | CI Backend job (surefire + JaCoCo report) | Verified | Met - MT-14, MT-27; staffListIsScoped |
| FR-006 | Filter/sort result within 2 s | RequestSpecs (filters, priority order); queue page | managerListAppliesFiltersAndNames; prioritySortOrder; openAndUnassignedFilters; k6 pilot run | Correct rows and order; p95 under 2 s at 20 users | CI Backend job (surefire + JaCoCo report); perf/README.md | Verified for filter/sort (D-07 fixed); search open (TD-04) | Met (filter/sort ≤ 2 s: k6 p95 29.8 ms; MT-15). Requirement partially implemented: free-text search not built (TD-04) |
| FR-007 | All fields and a log of prior actions shown | AuditService.forRequest (from the audit trigger) | priorityAndHistory; fullLifecycleIsAudited; E2E-01 | Actor, time and before/after status for every step | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified | Met - MT-21; fullLifecycleIsAudited |
| FR-008 | Assigned with time; two simultaneous accepts: one succeeds, the other is told | RequestService.assign; row lock; partial unique index | databaseAllowsOneActiveHandler; RequestServiceTest (already assigned, lost race); E2E-01 | Second accept gets 409 ALREADY_ASSIGNED | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified (ConcurrencyIntegrationTest.concurrentAcceptsOneWins: two accepts at once, the second gets ALREADY_ASSIGNED – MT-17) | Met (both criteria) - ConcurrencyIntegrationTest; MT-16, MT-17 |
| FR-009 | Transitions outside the state machine rejected with a message | TransitionPolicy; changeStatus | TransitionPolicyTest; RequestServiceTest (cannot skip steps); allowedTransitionsDependOnTheUser; E2E-01; statusChangePartitions | 422 INVALID_TRANSITION; only allowed statuses offered | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified (D-08, D-11 fixed) | Met - MT-18; E2E-01; statusChangePartitions |
| FR-010 | Comment stored with author and time; cannot be edited or deleted | CommentService; append-only trigger | CommentServiceTest; fullLifecycleIsAudited; E2E-01 | Comment saved; UPDATE/DELETE refused by the database | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified (D-13 fixed) | Met - MT-19. Limitation: staff notes list does not label visible vs internal notes |
| FR-011 | Closed and rejected requests are read-only | Terminal checks in RequestService and CommentService | RequestServiceTest (read-only); cannotCommentOnClosedRequest; deactivationTakesEffectImmediately | 422 REQUEST_CLOSED; handler removal leaves closed requests unchanged | CI Backend job (surefire + JaCoCo report) | Verified (D-05 fixed) | Met - MT-20 |
| FR-012 | Open, overdue, resolved, closed counts (overdue = 7 days) | ReportService; ReportRepository | ReportRepositoryTest; ReportServiceTest; activityReport; overdueBoundary | Counts only, no personal fields; open exactly 7 days is not overdue, one second later it is | CI Backend job (surefire + JaCoCo report) | Verified (D-42 found by overdueBoundary and fixed) | Met (both criteria) - MT-24; overdueBoundary |
| FR-013 | Counts and lists follow the selected filters | Report filters; activity page lists | ReportServiceTest; openAndUnassignedFilters; activity-page.spec (status filter) | Counts and open-request lists match the filters | CI Backend job (surefire + JaCoCo report); Frontend job | Verified (D-10 and D-41 fixed) | Met - MT-25; activity-page.spec (D-41 fixed, PR #32) |
| FR-014 | Users log in; each role reaches only its screens | AuthService; JwtService; role guard | AuthServiceTest; JwtSecurityTest; defaultManagerCanLogIn; E2E-01 to E2E-03 | Token with role; wrong role 403 | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified | Met - MT-01 to MT-06; E2E-02 |
| FR-015 | Management-controlled category list; inactive hidden from requesters | CategoryService; categories page | CategoryServiceTest; inactiveCategoryHidden; categoryPartitions | Inactive categories not offered and not openable by requesters | CI Backend job (surefire + JaCoCo report) | Verified | Met - MT-12, MT-26; categoryPartitions |
| FR-016 | Priority set by Management only, shown in lists, audited | RequestService.setPriority; V4 migration | priorityAndHistory; prioritySortOrder; priorityPartitions | Staff get 403; history shows who set it | CI Backend job (surefire + JaCoCo report) | Verified | Met - MT-23; priorityPartitions |
| NFR-001 | p95 at most 3 s at up to 20 users | Paging in the database; (cat_id, status, created_at) index | k6 request-list pilot run | p95 below 2 s (stricter FR-006 target) | perf/results/*.json; perf/README.md | Met locally (p95 29.8 ms, repeated on a second machine); staging run open (R-26) | Partially met - local k6 p95 29.8 ms at 20 users; not measured on Render (R-26) |
| NFR-002 | Passwords hashed with BCrypt, never returned | BCryptPasswordEncoder; @MaxBytes(72) | AuthServiceTest; registrationNeverLeaksPassword; ResponsesNeverContainPasswordsTest; MaxBytesValidatorTest | Hash stored; no password in any response or audit row | CI Backend job (surefire + JaCoCo report) | Verified | Met - AuthServiceTest; ResponsesNeverContainPasswordsTest |
| NFR-003 | A requester calling a staff endpoint gets 403, not data | @PreAuthorize; database roles (C-03) | requesterCannotUseStaffEndpoints; databaseRoleBlocksRequester; E2E-02 | 403 FORBIDDEN; database refuses too | CI Backend job (surefire + JaCoCo report); CI End-to-end job (Playwright report) | Verified | Met - E2E-02; MT-05; databaseRoleBlocksRequester |
| NFR-004 | 2 of 3 first-time users submit unaided within 5 minutes | Requester page (one short form) | MT-33 in the manual test log | - | - | Deferred (CR-014): the staging site must first be prepared so testers can start unaided (slow start-up of the free instance); MT-33 not run | Not met - MT-33 |
| NFR-005 | No unplanned outage during demos | 503 for database outages (D-06); health check | FilterErrorHandlerTest; ErrorHandlingTest | 503 SERVICE_UNAVAILABLE instead of 500 | CI Backend job (surefire + JaCoCo report) | Verified (M3): 503 handling tested; both Supabase databases health-checked on 16/10/2026 (staging /api/v1/health: database UP) | Met - health check before the final demo (to be done the morning of the demo, 20/10/2026); 503 handling tested. D-39 fixed 18/10/2026 (pooler pool size 20) |
| NFR-006 | The audit log rebuilds a request's full lifecycle | Audit trigger (C-02); AuditService | fullLifecycleIsAudited; priorityAndHistory; statusHistory | Every step with actor and time | CI Backend job (surefire + JaCoCo report) | Verified | Met - MT-21; fullLifecycleIsAudited |
| NFR-007 | Changes outside the workflow are blocked or logged | Append-only triggers; state machine; row lock | auditTrailAndNotesAreAppendOnly; TransitionPolicyTest; databaseRoleBlocksRequester | Database refuses UPDATE/DELETE of audit rows | CI Backend job (surefire + JaCoCo report) | Verified | Met - auditTrailAndNotesAreAppendOnly; databaseRoleBlocksRequester |
| NFR-008 | README documents the structure | Module packages (access, requests, reporting, common) | README.md checked against the repository (16/10/2026) | README describes the structure, setup, tests, CI and release flow of the code | README.md | Implemented - README rewritten (TD-09) | Met - README.md (TD-09) |
| NFR-009 | No hard-coded limits; lists paged | Paging on every list (max 100); categories as data | SortGuardTest; k6 run with 10,000 requests; pageSizeCap | Paged responses; no size limits in code | CI Backend job (surefire + JaCoCo report); perf/README.md | Verified | Met - pageSizeCap; k6 with 10,000 requests |

# End-to-End Traces

M4 status: these traces are the M2 baseline and are kept unchanged as history. Every step marked Planned has since been built and tested, except two that were replaced through controlled change: the AuditListener became database triggers (C-02, V2__align_with_entities.sql lines 137 to 158) and the Version check became a row lock (C-01). TransitionPolicy and TransitionPolicyTest (FR-009), the request controller and submission tests (FR-001), contextLoads in CI and the forced audit failure test (StatusChangeRollbackTest, trace 3) are all in place. The current trace for each requirement is RTM Table 3.

The M2 brief requires at least one trace from requirement to implementation and verification. We show three so that each team member can present one, and so that they cover the three most important behaviours: changing status, submitting a request and keeping the audit trail. Only steps marked Done are claimed as evidence.

Trace 1: FR-009 controlled status transitions

| Step | Evidence | Status |
| --- | --- | --- |
| Requirement | FR-009 (Requirements table) | Done |
| ASR / constraint | ASR-002 integrity of state, ASR-003 auditability | Done |
| Architecture responsibility | Requests module service layer owns all status changes (ARC-02) | Done |
| Data decision | Status CHECK constraint (V1), one transaction per state change with Version check (DEC-006) | Done (design), V2 migration Planned |
| Design / interface decision | Table-driven TransitionPolicy (DEC-011). PATCH /api/v1/requests/{id}/status (API-09) returns 422 on an illegal move (DEC-009) | Done (design), code Planned |
| Technology | Java 21, Spring Boot 4.1.1, Spring Data JPA, PostgreSQL (DEC-004, DEC-005) | Done |
| Application artefact | ServiceRequest.Status enum, V1__init_schema.sql, TransitionPolicy.java (planned) | Schema only: Status enum and V1 CHECK constraint Done; TransitionPolicy Planned |
| Initial verification | TransitionPolicyTest covering every from/to pair (planned) | Planned |

Trace 2: FR-001 submit a service request

| Step | Evidence | Status |
| --- | --- | --- |
| Requirement | FR-001 | Done |
| ASR / constraint | ASR-001 access control, ASR-005 POPIA (only needed fields stored) | Done |
| Architecture responsibility | Requests module controller and service (ARC-02) | Done |
| Data decision | Request table with RefNum UNIQUE, NOT NULL fields, FK to active Category (DEC-005, integrity rules 6 to 8) | Done (V1) |
| Design / interface decision | POST /api/v1/requests (API-04), DEC-009 | Done (design), endpoint Planned |
| Technology | Spring Web, Bean Validation, Spring Data JPA, Flyway (DEC-004, DEC-008) | Done / Validation to add |
| Application artefact | ServiceRequest.java, Category.java, Client.java, V1__init_schema.sql, RequestController (planned) | Entities and schema Done, controller Planned |
| Initial verification | contextLoads with Flyway and ddl-auto=validate (proves entities match the schema). Submission integration test (planned) | contextLoads exists (not run in CI); submission test Planned |

Trace 3: NFR-006 audit of every change

| Step | Evidence | Status |
| --- | --- | --- |
| Requirement | NFR-006, with FR-010 and NFR-007 | Done |
| ASR / constraint | ASR-003 auditability | Done |
| Architecture responsibility | Requests module owns AuditEntry as part of the Request aggregate (ARC-02) | Done |
| Data decision | AuditEntry with FromStatus, ToStatus and one actor (ERD v2). Trigger blocks UPDATE and DELETE (DEC-007) | V1 table Done, V2 columns and trigger Planned |
| Design / interface decision | Observer: AuditListener writes the entry inside the same transaction as the status change (DEC-012) | Done (design), code Planned |
| Technology | Spring application events, Spring Data JPA, PostgreSQL trigger | Done (design) |
| Application artefact | AuditEntry.java, V1__init_schema.sql, AuditListener.java (planned), V3__audit_append_only.sql (planned) | AuditEntry.java and V1 Done, listener and trigger Planned |
| Initial verification | Integration test: forced audit failure rolls back the status change. SQL check: UPDATE on audit_entry fails | Planned |

# Architecturally Significant Requirements

The following table identifies the requirements and quality attributes that influence CivicConnect's architecture the most. We only listed drivers that actually change how the system is structured. Quality attributes that do not change an architecture decision at our scale are listed separately below with the reason they were left out. Every driver has a measurable target so it can be tested and traced in the RTM, and every driver links to the ADRs it shaped.

| Driver ID | Driver and measurable target | Source / Evidence | Quality Attribute | Why it Drives Architecture | Decisions influenced | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| ASR-001 | Every page, URL and API endpoint must be restricted to the correct role, and staff may only see requests in their assigned categories. Target: 100% of staff/management endpoints return 403 to a requester-role token in the access tests, with no data returned. | FR-005, FR-014, NFR-002, NFR-003, Security constraint, R-03 | Security (authorisation) | Access control cannot only live in the Angular UI, since anyone can call the API directly. It requires one server-side access-control layer that every request passes through. This is much easier to enforce inside one deployable than across several. | ARC-01, ARC-02, DEC-002, DEC-004, DEC-010 | High |
| ASR-002 | A request's status may only change through the defined state machine (New - Assigned - In Progress - Resolved - Closed; New/Assigned - Rejected), and two staff members may not accept the same request at the same time. Target: 100% of invalid transitions are rejected with a message. A concurrent-accept test results in exactly one assignment. | FR-008, FR-009, FR-011, NFR-007 | Integrity and consistency of data and state | The state transition logic must live in one place (the Requests module service layer), and the status update and its audit entry must be saved in one database transaction. This points to one strongly consistent relational store rather than data split across services. | ARC-02, DEC-005, DEC-006 | High |
| ASR-003 | Every status change, assignment and comment is recorded with the actor, timestamp and before/after state, and can never be edited or deleted. Target: for a sample request the audit log rebuilds the full lifecycle without gaps, and an UPDATE or DELETE on the audit table fails. | FR-007, FR-010, NFR-006, NFR-007, Management stakeholder | Auditability | Requires the persistence layer, not just the UI, to block updates and deletes on audit data, and the audit write to be part of the same transaction as the change it records. | DEC-006, DEC-007 | High |
| ASR-004 | Staff search, filter and sort must return results quickly under normal project load. Target: filter/sort results in 2 seconds or less (FR-006) and standard pages in 3 seconds or less at the 95th percentile with up to 20 concurrent users (NFR-001). | FR-006, NFR-001 | Performance | Influences data access design (indexes on status, category and date, and paging done in the database rather than in memory) and rules out architectures that add network hops between services for a single page load. | ARC-02, DEC-005, DEC-008, DEC-009 | Medium |
| ASR-005 | Requester data and requests must comply with POPIA - personal information is only collected and shown where it is needed. Target: management reports contain aggregate counts only (no personal fields), and every personal field in the data model has a stated purpose. | Government stakeholder, Stakeholder Conflicts, FR-012, R-03 | Privacy and compliance | Influences what the data model stores and who can access it. Keeps reports on aggregate queries inside the Reporting module, and means passwords are only ever stored as hashes. It led to removing date of birth and home address fields in ERD v2. M4: as built, the employee fields are kept as the staff record and the client date of birth was removed (V8, CR-022). | DEC-005, Data Sensitivity & POPIA | High |
| ASR-006 | The client cannot yet confirm the final platform form (website, mobile app and/or desktop app). Target: all business rules are reachable through the REST API only, with no business logic in Angular components, so a second client (e.g. mobile) could be added without changing the backend. | DEC-001, Forward Engineering: Definition of Digital Platform | Modifiability and reusability | Pushes to an architecture that separates the presentation layer (Angular SPA) from the business logic (Spring Boot REST API), so a future platform change needs minimal changes to existing code. | ARC-01, ARC-03, DEC-004, DEC-010 | Medium |
| ASR-007 (constraint) | The system must run on free/open-source software and free-tier hosting, and be built and maintained by 3 students in under 3 weeks after M2. Target: R0 licensing and hosting cost. One application deployable plus one database to run and support. | Cost/Resources, Time and Team capability constraints, R-02, R-08 | Deployability and cost | Every extra deployable adds hosting cost, configuration, secrets and failure points. This favours one application and one managed database over several services. | ARC-01, ARC-02, ARC-03, DEC-004 | High |

## Most Influential Drivers

ASR-001 and ASR-002 influenced the architecture the most. ASR-001 is the main reason we chose one application with one shared, server-side access-control layer (ARC-01) instead of separate public and staff applications. ASR-002, together with ASR-003, is the main reason we chose one relational database with transactions (DEC-005, DEC-006) instead of splitting data across independently deployed services, where keeping a status change and its audit entry consistent would need distributed transactions. ASR-007 then kept the solution proportionate - it is the reason we did not add more moving parts than the requirements need.

## Quality Attributes Considered but Not Treated as ASRs

To avoid a generic list of every quality attribute, the following were considered and deliberately not treated as architecture drivers at this stage:

| Quality attribute | Why it is not an ASR now | When we would revisit it |
| --- | --- | --- |
| High availability / redundancy | NFR-005 only requires the system to be up during demonstrations and presentations, with up to 20 users. Redundant servers or database replicas would cost money with no requirement behind them. | If CivicConnect confirms real uptime targets or traffic figures (Forward Engineering: Scalability and Concurrency). |
| Independent / elastic scalability | There is no evidence that one module (e.g. Reporting) needs to scale separately from the rest. This is also why microservices were rejected in ARC-02. | Deferred (revisited in M3): the free-tier hosting cannot run a realistic load test, so there is still no evidence that one module needs to scale on its own (R-26, TD-12, CR-018). |
| Interoperability / public API | A public API for third parties is out of scope for v1. | Through change control if integration becomes a requirement. |
| Real-time responsiveness (push) | Real-time chat and push/SMS notifications are out of scope. FR-004 only needs in-app feedback the next time the requester views the request. | When the deferred notification channel is picked up. |

## M2 Architecture Review

Held on 30/09/2026 with Chanri Du Randt, Clarissa Bierman and Eduard Herman. The team reviewed the ASRs, ARC-01 to ARC-03, the technology stack (DEC-004) and the data model (ERD v2, DEC-005 to DEC-008). Outcome: all accepted for the M2 baseline. NFR-009 was confirmed: no hard-coded limits, categories stored as data, paging on all list endpoints, and the database size monitored against the Supabase 500 MB limit. Open items were recorded as deferred decisions (application host, attachment storage, retention period).

## ASR Verification (M4)

Each ASR above is linked to the tests that show whether its target was met. The full requirement-level trace is in RTM Table 3; this table answers the question per architecture driver.

| ASR | Target (short) | Verification evidence | Result (M4) |
| --- | --- | --- | --- |
| ASR-001 | Staff and management endpoints return 403 to a requester token, with no data | requesterCannotUseStaffEndpoints; noTokenIs401; databaseRoleBlocksRequester; E2E-02; MT-04, MT-05 | Met for the endpoints tested; no test lists every endpoint automatically |
| ASR-002 | Every invalid transition rejected; two simultaneous accepts give exactly one assignment | TransitionPolicyTest; statusChangePartitions; concurrentAcceptsOneWins; databaseAllowsOneActiveHandler; MT-17, MT-18 | Met |
| ASR-003 | The audit log rebuilds a full lifecycle; UPDATE and DELETE on audit rows fail | fullLifecycleIsAudited; auditTrailAndNotesAreAppendOnly (as the schema owner); priorityAndHistory; MT-21 | Met |
| ASR-004 | Filter/sort within 2 s, pages within 3 s at p95, up to 20 users | k6 pilot run (perf/results): p95 29.8 ms, repeated on a second machine; stress probe without failures | Partly met: measured locally only, not on the hosting (R-26) |
| ASR-005 | Reports hold counts only; every personal field has a purpose | activityReport (counts only); clientContactVersusAudit; ResponsesNeverContainPasswordsTest; MT-30 | Met. Employee date of birth and address are kept on purpose: the CivicConnect scenario does not mention an existing HR or employee database, so this application is the only record of its staff. The client date of birth had no purpose in any requirement and was removed in M4 (V8, CR-022, TD-03 resolved). Reports hold counts only, and Management never sees client passwords (C-03); audit rows from before V8 that still hold a client date of birth are masked in the audit_log view (C-08). |
| ASR-006 | All business rules reachable through the REST API only, none in Angular | All rules are enforced in the Spring services and tested over HTTP without the UI (ApiHttpIntegrationTest, ApiBlackBoxIntegrationTest); the UI shows the allowedTransitions the API returns | Met by design and API tests; no automated check that Angular holds no rules |
| ASR-007 | R0 licensing and hosting; one deployable plus one database | Dockerfile (one jar); CI Deployment image job runs it with 512 MB; staging on the Render and Supabase free plans; P-01 to P-07 | Met; free-tier limits remain: the instance sleeps (P-07) and pauses after a week idle (R-14) |

# Risk Register

| Risk ID | Description | Cause | Probability | Impact | Priority | Mitigation | Contingency | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R-01 | CivicConnect management requests a major new feature after the baseline is signed off, without the deadline moving. | Stakeholder pressure combined with no formal change-control process agreed yet. | Medium | High | High | Formal change-request process logged through the Engineering Decision Log; scope baseline explicitly signed off before M2 starts. | Defer non-critical additions to future scope; only pull forward if team capacity allows. | Team | Closed (M4) - every change after the baseline went through the Change Request Register (CR-001 to CR-019) |
| R-02 | Only 3 team members are covering the full SE lifecycle workload ( analysis, requirements, governance, later architecture and build). | Small team as size is fixed by module rules. | Medium | High | High | With weekly check-ins, task ownership tracked visibly through GitHub Issues, so gaps are caught early. | Redistribute tasks between members. Escalate to the lecturer if a member becomes consistently unavailable. | Team | Accepted- decisions are made knowing this risk as nothing can be done to avoid, mitigate or transfer the risk as it is borne from a fixed constraint. |
| R-03 | Reports generated for management could end up including more personal information about clients than POPIA actually allows. | Management wants full, detailed reporting, which works against POPIA's requirement to keep personal data use to a minimum. | Low | High | Medium | Reports will only pull the fields that are actually needed, and who can see the rest will depend on their role. | Check the report fields against POPIA before design work starts for M2. | Team | Mitigated (M3) - reports return counts only (activityReport); the audit_log view masks client fields (clientContactVersusAudit) |
| R-04 | The conflict between handlers wanting autonomy and management wanting oversight could resurface once requirements are locked in. | The two groups want different things, and the stakeholder analysis only partly worked through it. | Medium | Medium | Medium | We've written down how we're resolving it in the Stakeholder Analysis, and prioritized the requirements with a reason attached. | If it comes up again, go back and re-baseline whichever requirements are affected. | Team | Open - further discussion is needed with CivicConnect is needed to address this and usage reports from CivicConnect is needed as well to understand this risk and inform further action. |
| R-05 | Under deadline pressure, someone might be tempted to skip the branch protection or review process. | Time pressure close to the deadline makes shortcuts tempting. | Medium | Medium | Medium | The rule is enforced through the actual repository settings, not just something we agreed to follow, so it can't be skipped even by accident. | Any bypass gets picked up and logged in the Decision Log afterward. | Clarissa | Mitigated (M3) - rulesets on main and prod require the CI checks and two approvals; one direct push to prod during the staging set-up (15/10/2026) |
| R-06 | Requirement or trace IDs in the RTM could end up inconsistent since none of us have built one of these before. | No prior experience with formal traceability matrices. | Medium | Medium | Medium | Agreed on one ID format upfront (FR-0xx, NFR-0xx), with one person responsible for keeping the RTM consistent. | Proper check of it before each milestone gate to catch anything that doesn't line up. | Clarissa | Realised (M4): new change requests were first numbered CR-01 to CR-04, which clashed with CR-001 to CR-004; renumbered CR-014 to CR-018. Open |
| R-07 | AI-assisted drafting could be submitted without being properly checked first. | Time pressure makes it tempting to accept AI output without verifying it. | Low | High | Medium | The AI Usage Register requires us to record what was checked, changed, or rejected for anything AI helped with. | Spot-check AI-assisted sections against the brief standards before each submission. | Team | Mitigated - AI Usage Register; every AI-assisted change reviewed in a PR |
| R-08 | This milestone deadline overlaps with deadlines from other modules, cutting into the time we actually have. | Academic calendar, not something the team controls. | Medium | Low | Low | Draft sections early instead of leaving them for the last week, and use GitHub Issues to see what's actually falling behind. | If time runs short, decide which sections get the most attention and let the rest be good enough. | Team | Accepted – team can try to plan around this but deadlines are out of our control. |
| R-09 | Requirements and assumptions can't be checked with an actual CivicConnect stakeholder, since this is a coursework scenario rather than a real client. | Academic project structure, no real organization to go back to for clarification. | High | Medium | Medium | Base requirements directly on what the brief states, and document assumptions clearly wherever it doesn't say enough. | Mark assumption-based requirements in the RTM so they can be revisited if anything gets clarified later | Team | Accepted – this is a university project and is meant as a simulation of a real word scenario. |
| R-10 | A requester reads or changes another client's request by changing the id in the URL | Role checks without object-level checks | Medium | High | High | Ownership / category-scope checks in the service layer; access tests (ASR-001) | Fix before M3; log as security defect | Team | Mitigated and tested (M3) - object-level checks, database roles, E2E-02 |
| R-11 | JWT or signing secret stolen | XSS, or secret committed / logged | Low | High | Medium | Env-var secret, 60-min expiry, Angular escaping, HTTPS | Rotate the secret (invalidates all tokens) | Team | Mitigated (M3) - JWT_SECRET is an environment variable generated by Render; gitleaks scans every push |
| R-12 | Angular and API contract drift apart | Endpoints changed without updating the contract | Medium | Medium | Medium | Contract table updated in the same PR; one jar deploys both | Fix via PR; add contract tests at M3 | Team | Mitigated (M3) - the E2E tests run the Angular app against the real API in CI |
| R-13 | Unsecured prototype endpoints reach a deployed environment | Security not added before first deployment | Medium | High | High | Prototype gap table tracked; security added before any deployment | Take the deployment down | Team | Closed (M3) - security was added before the Requests module was built |
| R-14 | The Supabase database is paused or data is lost right before a demo. | Free plan pauses after 1 week of inactivity and has no automatic backups (Supabase, 2026a). | Medium | High | High | Health check the day before each demo. Manual pg_dump before each milestone and before any migration. | Run the demo against a local PostgreSQL restored from the backup. | Team | Mitigated (M3) - 503 when the database is down (D-06); health check before each demo |
| R-15 | No free host runs the Spring Boot jar reliably. | Memory limits, IPv4/IPv6 support and cold starts on free hosts. | Medium | High | High | Check host limits against the ARC-03 criteria before choosing. Use the Supavisor session pooler. | Demo from a team laptop. Reconsider separate Angular hosting (ARC-03 Alternative 2). | Team | Closed (M3) - the Render free plan runs the jar (staging; P-01 to P-07 pass); it sleeps when idle (P-07) |
| R-16 | Module boundaries erode (for example Reporting reading Requests entities directly). | Boundaries are only enforced by discipline and review. | Medium | Medium | Medium | Module rule checked in every PR review. | Refactor in M3. Add an ArchUnit test (Forward Engineering). | Team | Mitigated – team reads and reviews code to ensure boundaries are properly maintained using Pull Requests on GitHub and integrated review tools on GitHub. |
| R-17 | Users hit optimistic-lock conflicts, or a missing Version check allows a lost update. | Optimistic locking (DEC-006). | Low | Medium | Low | Global exception handler returns a clear 409. Concurrent-accept test. | Pessimistic lock for the assignment step only (DEC-006 later consequence). | Team | Closed (M3) - contingency applied: row lock (C-01); the remaining effect is TD-05 |
| R-18 | A write method runs outside a transaction and breaks atomicity. | Missing @Transactional or a call inside the same class that skips the Spring proxy. | Medium | High | High | All writes through public RequestService methods. Rollback integration test. | Fix and add a regression test. | Team | Mitigated (M3) - every service method runs in a transaction with the user's database role (C-03) |
| R-19 | Spring Boot 4 configuration errors from Spring Boot 3 tutorials. | Spring Boot 4 is a recent major version. | Medium | Medium | Medium | Use the official Spring Boot 4.1 documentation first (D-02). | Pin an earlier 4.x patch release. | Team | Closed (M3) - the application builds and runs on Spring Boot 4.1 (Flyway modules in pom.xml) |
| R-20 | No team member has used Spring Boot, Spring Security or Angular before, so the learning curve delays FR-014, NFR-002 and NFR-003. | Spring Boot and Angular are new to the whole team (A-03). Security and front end not started yet. | High | High | High | Add Spring Security early, keep the configuration minimal, pair on it. | Session-based login with role checks as a fallback. | Team | Realised and managed (M3) - absorbed through reviews and recorded AI assistance (R-27) |
| R-21 | Code and documentation disagree: the prototype still uses the ERD v1.2 schema while the PED describes ERD v2. | ERD v2 was designed after V1__init_schema.sql was written. | High | Medium | Medium | V2 migration and entity updates to match ERD v2. RTM marks V2 items as Planned. | Present V1 as built and ERD v2 as the approved target. | Team | Closed (M3) - the V2 migration aligned the schema; ERD v3 is drawn from the schema as built |
| R-22 | Database credentials committed to the repository. | The prototype had a local password in application.properties. | Realised | High | High | Environment variables only (DEC-008). Secrets check in PR reviews. | Change the password and clean the history if a real secret was exposed. | Clarissa | Closed (M3) - the only committed password was the local development password of the postgres user on a developer's own machine (localhost), in the prototype's application.properties (commit c052658, 30/09/2026). Commit 7ac7b9a (10/10/2026) replaced it with ${DB_PASSWORD}; all credentials have been environment variables since. It never protected a shared or hosted database, and the Supabase and Render databases have their own passwords, so the history was not rewritten. |
| R-23 | The audit trigger blocks test clean-up, or Flyway clean runs against Supabase. | Append-only trigger (DEC-007). | Low | High | Medium | Flyway clean only enabled on the test profile, never on Supabase. | Restore from the latest pg_dump. | Team | Mitigated (M3) - integration tests roll back and only run against a local database (D-33); Flyway clean is disabled by default |
| R-24 | Rate-limit and login-lockout counters are reset on restart and only count per instance. | Counters are kept in memory (C-04). | Low | Medium | Low | One instance only (A-01); recorded as TD-02. | Move the counters to a shared store before running more than one instance. | Team | Open |
| R-25 | The default manager password from the build script is used on a shared database. | The password is in the repository (C-06). | Medium | High | High | Change the password at the first login; the script says so. | Deactivate the default account and create a named manager. | Team | Mitigated (M3) - the production database has no default account (D-31, P-03) and the first manager changed the temporary password (P-04); the default account exists on the test database only |
| R-26 | Response times on Supabase are worse than measured locally. | The load test ran on one machine without network latency. | Medium | Medium | Medium | Large margin locally (p95 29.8 ms against 2 s); paging and indexes. | Repeat the k6 test against staging and tune the connection pool. | Team | Open |
| R-27 | Team members cannot explain AI-assisted code or tests at the defence. | Large M3 changes were drafted with AI assistance. | Medium | High | High | AI Usage Register; every change reviewed in a PR; tests document the behaviour. | Walk through each module together before the presentation. | Team | Open |
| R-28 | Attachment links point to content the system does not control: a phishing or malware page, or a requester's own cloud storage holding personal data. | Only a link is stored (A-02). The server checks that it starts with http:// or https:// and is at most 500 characters; nothing checks where it points, and plain http is allowed. | Medium | High | High | The link is shown as text ("Attachment link") and opens in a new tab with noopener and noreferrer; it is never loaded into the page; only http and https are accepted (API-04 validation). | Allow only https links (or only approved storage domains); build file upload with size limits and malware scanning (deferred attachment hardening, TD-11). | Team | Accepted and recorded as technical debt. |
| R-29 | Contribution is only visible in GitHub history, and three people edit one Word PED, so who did what is harder to trace and concurrent edits can overwrite each other. | CR-016: no work-allocation table after M1. Git cannot merge a .docx line by line. A git alias (CoffeeLover) and merge commits hide authors. | High | Medium | High | Pull main before editing the PED; one person edits it at a time and says so; every PED change goes through a PR; the git alias is recorded under Construction and Configuration. | If two copies diverge, compare their text and re-apply one person's edits onto the latest main version. | Team | Realised 18/10/2026: a local PED copy was missing two members' changes; the edits were moved onto the main version before commit. Accepted, Pull Requests mitigate the risk of errors and the time constraint of the project is the justification for reducing some admin for speed to meet the deadlines. |
| Note | Caching the request status on the write path was considered and declined. | A2 Task 2: stale status risk. | n/a | n/a | n/a | Not adopted by design. | n/a | Team | Closed |

Milestone 2 updates to existing risks: R-01 is now controlled through the Change Request Register (for example CR-003 added FR-016 without moving the deadline). R-03 now has a concrete mitigation, because management reports return aggregate counts only (ASR-005). R-05 will gain an automated gate once the CI build check (DEC-013) is added. R-09 still stands, and the traffic figures are an assumption (A-01).

Milestone 3 updates to existing risks: R-10 is mitigated and tested (object-level checks, database roles and E2E-02). R-13 is closed: security was added before the Requests module was built. R-14 now has a coded response: a database outage returns 503 SERVICE_UNAVAILABLE (D-06). R-17's contingency was applied: pessimistic row locking replaced optimistic locking (C-01). R-18 is mitigated: every service method runs in a transaction with the user's database role (C-03). R-22: credentials are now environment variables only; the team confirms the password committed in the prototype history was changed before staging.

# Forward Engineering Considerations

## Auditing, Logging and Traceability of Request Handling

Management needs to be able to track and manage the entire lifecycle of a request as well as audit a request. The process and states of the request must be detailed ahead of time as refitting audit and tracking features into the system after production has started risks slowing down the project.

M2 update: addressed by DEC-006, DEC-007 and DEC-012. Every status change, assignment and comment is written to AuditEntry in the same transaction and cannot be changed afterwards. Still open: the audit retention period under POPIA.

## Notification & Communication Between Requester and Handler

The software solution must manage communication. The exact mechanism for communication needs to be decided ahead of time to ensure compatibility with the chosen software architecture and language. Not deciding on this ahead of time may necessitate rework during the project's implementation phase, which could cause severe delays.

M2 update: FR-004 is met with in-app feedback when the requester views the request. The status-change event in DEC-012 is the extension point for email or SMS later (deferred scope).

## Request Prioritization & Escalation

Currently, CivicConnect struggles to prioritize requests. Request prioritization and escalation are required features. However, there is no logic for determining priority provided by CivicConnect that will inform whether prioritization is manually assigned by management, calculated or rule based. This must be discussed with Stakeholders from CivicConnect. However, if stakeholders are unavailable then industry research will be used to decide prioritization logic.

M2 update: DEC-003 confirmed and FR-016 added through CR-003. Priority is stored on Request (ERD v2). Automated escalation stays deferred.

## Scalability and Concurrency

Management wants to handle multiple requests and request handlers simultaneously. Counts of expected user traffic and transactions are needed to inform architecture decisions later. The lack of these estimates may result in architecture decisions that don't allow for the scaling needed.

M2 update: concurrency handled by DEC-006 (one transaction, optimistic locking) and the partial unique index on RequestHandler (CR-007). Traffic figures are still assumed (A-01). Scaling path: extract a module as a service (ARC-02) or add a read replica for Reporting.

## System Integration & Legacy Data

CivicConnect stakeholders have mentioned that they are using an unorganized manual process for handling requests. It must be negotiated with CivicConnect's stakeholders, whether or not development team is responsible for transferring existing request data over to the new system and if so what request data. Not being clear about this can result in CivicConnect losing requests from the move to manual processes to a software supported one.

M2 update: no change, still deferred. If approved, legacy data would be loaded through a reviewed Flyway migration.

## Definition of Digital Platform

Currently, CivicConnect only specifies a digital platform as the description of the software solution they want. For early versions of the software solution, a website will be used to prototype the digital solution and gain feedback from stakeholders.

M2 update: confirmed as a responsive web application (DEC-001, ARC-01, ARC-03). Business logic stays behind the REST API so a mobile client could be added later (ASR-006).

# Engineering Decision Log

| Decision ID | Context | Constraints | Alternatives | Decision | Rationale | Trade-offs | Risks | Evidence | Later Consequence |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DEC-001 | Client cannot specify final form of digital platform. | Time, Team Capability and Cost/Resources | Commit to a web/ mobile/ desktop app now vs. prototype first. | Build web prototype for first version of the software. | Preserves flexibility while gathering stakeholder feedback to refine features. | Some rework will be required if platform changes. | Wasted prototype effort if client wants a different platform. | Client scenario does not specify the digital platform. | To be confirmed in Milestone 2. M2: see update below. |
| DEC-002 | Client cannot specify preferred means of securing data (role-based or data based) | Security | Do not add access control for version 1, add role-based access control or add data based accessed control (specify in table who can see which data) | Use role-based access for security. | Stakeholders will likely prefer some kind of role-based access and rework will decrease for version 2. | If data-based access is the preferred control, then a lot of reworks on the software and the database will be needed. | Incorrect role-based access that does not fit the stakeholder’s needs. | Within project description no information for the data classification was given. RBAC was inferred. | To be confirmed in Milestone 2. M2: see update below. |
| DEC-003 | Client cannot provide business rules or an algorithm that will enable the system to assign priority to the requests. | Time | Use publicly available information to derive a means of determining the priority or have managers assign the priority to requests on the system. | Managers will assign request priority using their own judgement via the system. | Significant resources will be wasted if automated priority raking was implemented incorrectly. | May require rework if stakeholders want an automated ranking. | Managers may incorrectly assign the request priority. | R-09: There is no actual client to consult. | To be confirmed in Milestone 2. M2: see update below. |

## Milestone 2 Updates to Engineering Decisions

The original M1 decisions above are kept unchanged as baselined. The later consequences that were marked "To be confirmed in Milestone 2" are updated here with the evidence now available.

| Decision ID | M2 update (30/09/2026) | Status | Related |
| --- | --- | --- | --- |
| DEC-001 | Confirmed - the first version is a responsive web application (Angular single-page application + Spring Boot REST API, see ARC-01, ARC-03 and DEC-004). Business logic stays in the backend so a mobile app could reuse the API later (ASR-006). | Confirmed | ARC-01, ARC-03, DEC-004, ASR-006 |
| DEC-002 | Confirmed and refined - RBAC with Requester, Handler and Manager roles, enforced on the server by Spring Security (ASR-001). Because FR-005 limits staff to their assigned categories, handlers also get a category scope (EmployeeCategory table), and requesters only see their own requests. | Confirmed - refined | ASR-001, FR-005, ERD v2 |
| DEC-003 | Priority field added to Request in ERD v2, set by Management only. The matching functional requirement FR-016 was added through CR-003. | Confirmed | ERD v2, FR-016, CR-003 |

DEC-004 to DEC-008 are recorded in the Architecture Decision Record, Technology Stack and Data & Persistence Baseline sections. DEC-009 and DEC-010 are new M2 decisions recorded in API & Integration Design, DEC-011 and DEC-012 in Initial Design Decisions, and DEC-013 in GitHub & Team Governance.

## Milestone 3 Updates to Engineering Decisions

Implementation changed some M2 decisions. Each change is recorded in full (original decision, evidence, revised decision, consequence) in the Milestone 3 Evidence Index (Controlled Changes).

| Decision | Change | Summary |
| --- | --- | --- |
| DEC-006 | C-01 | Optimistic locking with a Version column replaced by a row lock (SELECT ... FOR UPDATE); no version in the API. |
| DEC-012 (and DEC-007) | C-02 | Audit rows written by a database trigger instead of an AuditListener; append-only triggers kept. |
| New | C-03 | One database role per user type, switched for every transaction. |
| API & Integration Design 21.7 | C-04 | Rate limiting brought forward from Deferred Scope. |
| CR-008 | C-05 | Role names STAFF and MANAGEMENT used everywhere (UI shows Staff and Manager). |
| DEC-008 | C-06 | Default manager created by the database build script. |
| ARC-03 | C-07 | Single jar built (Dockerfile) and deployed from the prod branch to Render after the checks pass (C-07). |

# Architecture Decision Record

Architecture decisions are recorded using the ADR format from the Master Project Brief (Section 13). In v1.2 the ADRs were in one wide ten-column table, which was hard to read, so each ADR now has its own table with the same fields. Each ADR links back to the ASRs above and to requirements in the RTM. We keep three things separate: the architecture (how the system is structured - ARC-01 and ARC-02), the deployment (where it physically runs - ARC-03) and the technology (what it is built with - DEC-004).

## Architecture Alternatives Considered

The following realistic alternatives were compared against the ASRs before the ADRs were written.

| Alternative | Fit against ASRs | Complexity / cost for our team | Outcome |
| --- | --- | --- | --- |
| Two separate applications (public requester site + internal staff site) | Weak on ASR-001: access rules would be duplicated in two places. Stronger security boundary for staff data. | Two deployables, two builds, double the hosting (ASR-007). | Rejected - ARC-01 |
| Microservices (Requests, Access, Reporting as separate services) | Weak on ASR-002/003: a status change and its audit entry would span services and need distributed transactions. Extra network hops hurt ASR-004. | Service discovery, several databases or shared DB, more hosting and monitoring. Not realistic in under 3 weeks. | Rejected - ARC-02 |
| Event-driven architecture | Asynchronous events give eventual consistency, which works against ASR-002. The request lifecycle is linear with no multiple consumers. | Needs a message broker and retry/ordering handling. | Rejected - ARC-02 |
| Traditional layered monolith (no module boundaries) | Meets ASR-001 to ASR-005. Weak on ASR-006 and maintainability - code from different features mixes over time. | Lowest effort to start, but harder to change and split later. | Rejected in favour of modular monolith |
| Modular monolith with layered modules, Angular SPA + REST API, one PostgreSQL database | Meets ASR-001 to ASR-007: one access-control layer, local ACID transactions, no extra network hops, UI separated from business logic. | One deployable plus one managed database. Module boundaries must be kept by discipline and code review. | Selected - ARC-01, ARC-02, ARC-03 |

## Architecture Decisions

| ARC-01 - One web application for requesters, staff and management |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Chanri Du Randt |
| Context | CivicConnect must serve two audiences (public-facing requesters and internal staff/management) with different security and access needs. The team must decide whether to serve them as one application or as separate applications. |
| Constraints | Time, Team Capability and Cost/Resources (ASR-007). Security constraint (ASR-001). |
| Alternatives | 1. Separate websites for CivicConnect personnel and their clients. The client-facing website would have minimal authentication and public pages to view CivicConnect's services and company details. The employee-facing website (managers and service handlers) would have greater security and no publicly accessible pages aside from a login page. 2. One website application for all users, with careful management of access. |
| Decision | One website, with the requester area and the staff/management area separated by role-based routing and per-request permission checks, rather than by splitting into separate deployed applications. |
| Rationale | Limited time is available, so only one main website will be built that shows pages and features per specific user role. Security is easier to manage because only one access-control layer exists (ASR-001). Duplicating access logic across two applications creates two places where a rule can be wrong. The platform form is not confirmed by the client yet (DEC-001), so committing effort to building and maintaining two applications is a disproportionate risk. |
| Trade-offs | Scalability is limited, especially if only one user group's features need to be scaled, since the application must scale as one unit. |
| Risks | All features are reachable through one public website, so compromising the website alone could give attackers access to most of the sensitive data. This is mitigated by strict server-side RBAC (Spring Security, DEC-004), requesters only being able to query their own requests, and the access tests in ASR-001 - but it is still a single security boundary compared to separate deployments. |
| Evidence | ASR-001 is easier to satisfy with one shared enforcement layer. DEC-001 (platform not confirmed). FR-005 and FR-014 show that audience separation can be achieved through role-based routing and permission checks rather than separate applications. Team size and Time constraints. |
| Linked requirements | FR-005, FR-014, NFR-003, ASR-001, ASR-006, ASR-007 |
| Later Consequence | Confirmed for the M2 baseline. If CivicConnect later wants a separate staff intranet or a mobile app, the Access module and REST API can be reused behind a second front end; ARC-03, the RTM rows for FR-005/FR-014 and the Risk Register would need to be updated through change control. |

| ARC-02 - Modular monolith with layered modules |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Chanri Du Randt |
| Context | Having decided on one application (ARC-01), the team must decide how that application is internally structured so it stays maintainable and secure as more modules (requests, access control, reporting) are added. |
| Constraints | Time, Team capability, Cost (ASR-007). Integrity (ASR-002). |
| Alternatives | 1. Microservices - split Requests, Access and Reporting into independently deployed services. 2. Event-driven architecture - modules communicate by publishing and consuming events. 3. Traditional layered monolith without module boundaries. 4. Modular monolith - one deployable made up of modules with clear boundaries. |
| Decision | A modular monolith will be used. It has three business modules, each a Java package with its own layers: - Requests - request submission, the status state machine, assignment, comments and the audit trail, and categories. - Access - authentication, roles, and which categories a handler may see. - Reporting - read-only aggregate counts for management. It owns no tables. It is the one read-only exception to the rule below: it runs aggregate count queries through its own read-only query repository, never uses the Requests module's entities and never writes. Inside each module we use Controller (REST) - Service (business rules, transactions) - Repository (Spring Data JPA). Modules only call each other through public service classes, never through another module's repositories or entities. |
| Rationale | Limited time makes microservices a severe risk. Modular monolith modules form candidates for microservices, making a later migration doable if the need arises. Asynchronous processing, which is a characteristic of event-driven architecture, is not needed for the business processes being supported - they mostly follow linear steps with few consumers of any event. A status change and its audit entry happen in one local database transaction (ASR-002, ASR-003), which would need distributed transactions across services. Module boundaries keep features separated, which a plain layered monolith does not (maintainability, NFR-008). |
| Trade-offs | Modular monoliths are less scalable than microservices, since the whole application scales as one unit. Module boundaries are only enforced by team discipline and code review, not by the network. |
| Risks | Modules may become tightly coupled if built wrongly (e.g. Reporting reading Requests' entities directly). Limited scalability may make the website slow if user activity spikes suddenly. Mitigation: the module rule above is checked in pull request reviews; an automated architecture test (e.g. ArchUnit) is a forward engineering consideration. |
| Evidence | FR-008 and FR-009 describe the request lifecycle as a linear sequence of state transitions triggered directly by a single staff action, with no need for multiple independent consumers reacting asynchronously to the same event, so event-driven architecture is needless complexity. ASR-002 is more reliably satisfied within a single deployable than across independently deployed services. The Team size and Time constraints support rejecting microservices. |
| Linked requirements | FR-001 to FR-013, NFR-007, NFR-008, ASR-002, ASR-003, ASR-004, ASR-007 |
| Later Consequence | Confirmed for the M2 baseline. If one module needs to scale on its own later, it can be extracted as a service because it already has its own package and tables. The repository folder structure (README) must follow these modules. |

| ARC-03 - Physical deployment: three tiers, one application deployable |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline (application host provider deferred) / 30/09/2026 / Chanri Du Randt |
| Context | ARC-01 and ARC-02 describe the logical structure. The team must also decide how the Angular front end, the Spring Boot back end and the database are physically deployed, since logical layers are not the same as physical tiers. |
| Constraints | Cost - free tiers only (ASR-007). Availability during demos (NFR-005). No secrets in the repository (GitHub & Team Governance). |
| Alternatives | 1. Angular production build packaged inside the Spring Boot jar and served from the same server as the API. 2. Angular hosted separately on a static site host, with the Spring Boot API deployed separately. 3. Server-side rendered pages (e.g. Thymeleaf) instead of an Angular SPA. For the database: self-hosted PostgreSQL on the application host, or a free managed PostgreSQL service (Supabase). |
| Decision | Three physical tiers: - Tier 1: the user's browser running the Angular single-page application. - Tier 2: one application host running civicconnect.jar (Java 21, Spring Boot with embedded Tomcat). The jar serves the compiled Angular files and the /api REST endpoints (Alternative 1). - Tier 3: a managed PostgreSQL database on the Supabase free plan. During development each member runs Angular with ng serve (proxying /api to localhost:8080) and Spring Boot with Maven. Database URL, username and password are read from environment variables and must never be committed. The prototype's local development password is an open issue (R-22). |
| Rationale | One application deployable keeps hosting to one free service and makes the browser talk to one origin, so no CORS is needed in production (local development uses a CORS rule for localhost:4200 until the ng serve proxy is added), and the JWT is sent as a header to one origin (DEC-010) (ASR-001, ASR-007). Keeping Angular separate from the backend code supports ASR-006 - a mobile client could use the same API later. Supabase gives a managed PostgreSQL database for free, so we do not have to install, patch or back up a database server ourselves, and it is plain PostgreSQL, so JPA, Flyway and our SQL work unchanged (low lock-in). |
| Trade-offs | A front-end change requires rebuilding and redeploying the jar. The build is more complex because Maven must also build Angular. The database is on a different network from the application, which adds some latency to each query. |
| Risks | Supabase free projects pause after 1 week of inactivity and have no automatic backups (Supabase, 2026a) - the database could be paused right before a demo (NFR-005). Mitigation: open the project and run a health check the day before every presentation; take a manual pg_dump backup before each milestone. Supabase direct connections use IPv6; many free app hosts only support IPv4. Mitigation: connect through the Supavisor session pooler (port 5432), not the transaction pooler, because transaction mode does not support prepared statements used by Hibernate (Supabase, 2026b). Supabase automatically exposes the public schema through its Data API. Mitigation: our tables live in a separate civicconnect schema that is not exposed, and the Data API roles (anon, authenticated) have no access to it; row level security is on for the tables with personal data (client, employee, request, comment; V6, C-08). Only unsecured endpoints are register and log in. Free application hosts may sleep when idle, giving a slow first request (cold start). |
| Evidence | Supabase pricing page (free plan: 500 MB database, pauses after 1 week of inactivity, no automatic backups) (Supabase, 2026a) and Supabase 'Connecting to Postgres' documentation (IPv6 direct connections, session vs transaction pooler) (Supabase, 2026b). ASR-001, ASR-006, ASR-007, NFR-005. |
| Linked requirements | NFR-005, NFR-002, NFR-003, ASR-001, ASR-006, ASR-007 |
| Later Consequence | Deferred: the application host provider. Evidence needed before choosing: free-tier memory (Spring Boot needs roughly 512 MB), whether it runs a Java 21 jar or a Docker container, IPv4/IPv6 support, sleep/cold-start behaviour and environment variable support. If the free host cannot run the jar reliably, Alternative 2 (separate static hosting for Angular) will be reconsidered. |

## Architecture Diagrams

Figure 1 is the logical view: it shows the layers and modules inside the single deployment boundary (ARC-01, ARC-02). Figure 2 is the physical deployment view: it shows where each part actually runs (ARC-03). The modules in Figure 1 are not separate servers - all of them run inside the one jar in Tier 2.

Figure 1 - Logical view: modules and their layers inside one deployable, with the database outside the boundary (ARC-01, ARC-02)

Figure 2 - Physical deployment view: three tiers (ARC-03)

The request-status interaction across modules is described in API & Integration Design, in the "Example Interaction" section.

## Technology Stack

The technology decision (DEC-004) is kept separate from the architecture decisions above. The architecture would still hold with a different stack; the stack was chosen because it fits that architecture, the ASRs and our constraints best. Versions below are the ones used in the repository; rows marked "(to add)" are planned and not in the project yet.

| Layer | Technology | Version | Licence / cost | Purpose |
| --- | --- | --- | --- | --- |
| Front end | Angular (TypeScript) | 21.2 (^21.2.0 in package.json) (Angular, 2026; endoflife.date, 2026) | MIT (Google, no date) / free | Single-page application for requester, handler and manager screens |
| Back-end language / runtime | Java (JDK) | 21 (LTS) | GPL v2 with Classpath Exception (OpenJDK, no date) / free | Runs the Spring Boot application |
| Back-end framework | Spring Boot | 4.1.1 | Apache 2.0 (Spring, no date a) / free | REST API, dependency injection, embedded Tomcat, configuration |
| Web | Spring Web MVC (spring-boot-starter-webmvc) | Managed by Spring Boot 4.1.1 | Apache 2.0 (Spring, no date a) / free | REST controllers |
| Persistence | Spring Data JPA (Hibernate) | Managed by Spring Boot 4.1.1 | Apache 2.0 for Hibernate ORM 7 (Hibernate, no date) / free | Entities, repositories, @Transactional, @Version |
| Database driver | PostgreSQL JDBC driver | Managed by Spring Boot 4.1.1 | BSD-2-Clause (PostgreSQL JDBC Driver, no date) / free | Connects the application to PostgreSQL |
| Schema migrations | Flyway (spring-boot-flyway + flyway-core + flyway-database-postgresql) | Managed by Spring Boot 4.1.1 | Apache 2.0, Community edition (Flyway, no date) / free | Versioned SQL migrations (DEC-008) |
| Code generation | Lombok | Managed by Spring Boot 4.1.1 | MIT (Project Lombok, no date) / free | Getters, setters and constructors to reduce boilerplate |
| Security (to add) | Spring Security (spring-boot-starter-security) | Managed by Spring Boot 4.1.1 | Apache 2.0 (Spring, no date b) / free | Authentication, RBAC, BCrypt password hashing (DEC-010, ASR-001, NFR-002, NFR-003) |
| Validation (to add) | Bean Validation (spring-boot-starter-validation) | Managed by Spring Boot 4.1.1 | Apache 2.0 (Spring, no date a) / free | Server-side input validation for FR-001 |
| Database | PostgreSQL on Supabase (free plan) | Supabase target: 17.x (Supabase, 2026c; Supabase, 2026d). Local development today: 18.4 (README) | PostgreSQL Licence (PostgreSQL Global Development Group, no date) / free plan | Persistent storage (DEC-005) |
| Build | Maven, jar packaging, application.properties | Maven 3.6.3 or later | Apache 2.0 (Apache Software Foundation, 2004) / free | Build, dependency management, one executable jar |
| Security - token validation | Spring Security OAuth2 resource Server (spring-boot-starter-oauth2-resource-server) | Managed by Spring Boot 4.1.1 | Apache 2.0 (Spring, no date b) / free | JWT validation (DEC-010) |

Compatibility assumptions: every team member uses JDK 21 and the same Node.js LTS version for the Angular CLI; Spring Boot 4.1.1 supports Java 17 up to Java 26 and needs Maven 3.6.3 or later (Spring, 2026b). Dependency versions are not pinned by hand - the Spring Boot parent manages them, which avoids version conflicts between Spring libraries. Local development currently uses PostgreSQL 18.4 while Supabase runs PostgreSQL 17, so migrations only use features available in PostgreSQL 17.

### Technology decision matrix

Each option was scored 1 (poor) to 5 (strong) by the team against the Master Brief's technology criteria (Section 18.1), plus two criteria taken from our ASRs: transaction management (ASR-002, ASR-003) and database schema management (DEC-008). Weights reflect our constraints: requirement fit and team capability matter most because of the short schedule. Team capability scores reflect that the team has used Java but not Spring Boot or Angular, and has C#/ASP.NET and JavaScript/Node.js experience but has not used React (A-03). The two ASR criteria and the corrected Angular + Spring Boot team capability score were added in v3.0 (CR-013); the original weights were scaled to 80% to make room for them.

| Criterion (weight) | Angular + Spring Boot + PostgreSQL | React + Node.js/Express + PostgreSQL | React + ASP.NET Core + PostgreSQL | React + Django + PostgreSQL |
| --- | --- | --- | --- | --- |
| Requirement / ASR fit (20%) | 5 - Spring Security RBAC and method-level role checks | 4 - possible, but RBAC assembled from several libraries | 5 - equivalent built-in features | 4 - good ORM and auth, weaker typing |
| Team capability & learning curve (20%) | 2 - team has used Java, not Spring Boot or Angular | 3 - team has used JavaScript and Node.js, not React | 3 - team has used C# / ASP.NET, not React | 1 - no Python/Django experience |
| Security ecosystem & maturity (12%) | 5 | 3 | 5 | 4 |
| Maintainability, testing & tooling (12%) | 4 - strong typing both sides, but Angular/Lombok add boilerplate | 3 | 4 | 3 |
| Cost / licensing (8%) | 5 - all open source | 5 | 5 | 5 |
| Deployment compatibility (8%) | 3 - heavier memory use on free hosts | 5 - very light | 4 | 4 |
| Transaction management (10%) | 5 - declarative @Transactional and row locks (@Lock) | 3 - transactions handled by hand through the chosen ORM | 4 - EF Core transactions are explicit code; no built-in declarative attribute | 5 - transaction.atomic |
| Database schema management (10%) | 5 - Flyway: versioned plain-SQL migrations run automatically on start-up; suits triggers, roles and functions | 3 - migrations from a separate library (e.g. Knex or Prisma), set up by hand | 4 - EF Core code-first migrations; raw SQL possible but less direct | 5 - built-in migrations |
| Weighted score (out of 5) | 4.12 | 3.52 | 4.20 | 3.56 |

| DEC-004 - Technology stack: Angular, Java 21 + Spring Boot 4.1.1, PostgreSQL |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | The architecture (ARC-01 to ARC-03) needs a front-end framework, a back-end runtime and framework, a database and build/migration tooling. No stack is prescribed; the choice must be justified against the requirements, ASRs and constraints (Master Brief, Section 18.1). |
| Constraints | Time (under 3 weeks to final delivery), Team capability (3 students), Cost (free/open source only), Security (POPIA personal data). |
| Alternatives | React + Node.js/Express; React + ASP.NET Core; React + Django (see decision matrix above). |
| Decision | Angular front end; Java 21 with Spring Boot 4.1.1 back end (Spring Web, Spring Data JPA, Lombok, PostgreSQL driver, Flyway, and Spring Security and Bean Validation to be added); PostgreSQL on Supabase; Maven build packaged as a jar with application.properties configuration. |
| Rationale | Team capability: the team has used Java but not Spring Boot or Angular (A-03), and has C#/ASP.NET and JavaScript/Node.js experience but has not used React. The decision matrix therefore favours React + ASP.NET Core narrowly (4.20 against 4.12 for this stack; v3.0 scoring, CR-013). We still chose this stack for the reasons below and accept the learning-curve risk (R-20): Security fit (ASR-001, NFR-002, NFR-003): Spring Security gives URL- and method-level role checks and a BCrypt password encoder out of the box, so we do not write our own security code. Integrity fit (ASR-002, ASR-003): Spring's @Transactional and Spring Data JPA's row locks (@Lock) give us declarative transactions and locking (C-01 replaced the planned @Version optimistic locking), which is exactly what the status change + audit write needs (DEC-006). Controlled schema (DEC-008): Flyway keeps every schema change as a versioned SQL file in Git, so database changes go through the same pull request review as code. Strong typing on both sides: Java and TypeScript catch many errors at compile time, and Angular's fixed structure (components, services, route guards) gives a consistent codebase a new contributor can navigate (NFR-008). Long-term support: Java 21 is an LTS release (Oracle, 2026) and Spring Boot 4.1.1 is a current release (20 August 2026) that officially supports Java 17 to 26 (Spring, 2026a; Spring, 2026b). Cost and deployment: everything is free and open source, and Spring Boot builds one executable jar with an embedded server that runs on any host with Java 21 or in a Docker container (ARC-03). Why not the highest-scoring option: requirement fit, security, cost and maintainability score the same, and Spring Boot scores higher on transaction and schema management, so the 0.08 gap comes only from team capability and deployment weight. The prototype (Spring Boot project, Flyway V1 schema, six JPA entities and the Angular category screen) is already built on this stack, and rebuilding it under the Time constraint would cost time we do not have. The team also chose to learn the Java/Spring ecosystem, and manages the learning curve through R-20 (Spring Security first, pair work) and D-02 (official Spring Boot 4.1 documentation first). No option avoids learning a new front-end framework, because the team has used neither React nor Angular. Learning value: as students, we chose the option that would teach us the most. None of us had used Spring Boot, Spring Security or Angular, a combination commonly used in enterprise systems, so building CivicConnect on this stack develops new skills instead of repeating what we already know from C#/ASP.NET. This is the deciding reason for choosing this stack over the narrowly higher-scoring React + ASP.NET Core, and we accept the slower start it causes (R-20). |
| Trade-offs | Spring Boot uses more memory and starts slower than Node.js, which matters on free hosts. Angular has more boilerplate than React. Lombok hides generated code, so every member needs the IDE plugin/annotation processing switched on. No one in the team has used Spring Boot or Angular, so early development will be slower than in C#/.NET (R-20). |
| Risks | Spring Boot 4 is a newer major version, and many online tutorials are still for Spring Boot 3 (e.g. in Spring Boot 4 Flyway needs the spring-boot-flyway module plus flyway-database-postgresql, otherwise migrations do not run) (Spring, 2026c). Mitigation: use the official 4.1 documentation first. Lombok's @Data on JPA entities can break equals/hashCode and lazy loading. Mitigation: only @Getter/@Setter on entities. Spring Security and Bean Validation are not in the project yet. Mitigation: add them before the Access module and request submission are built. |
| Evidence | Decision matrix above; Spring Boot 4.1 system requirements (Spring, 2026b) and 'Database Initialization' documentation (Spring, 2026c); Spring Boot 4.1.1 release notice (Spring, 2026a); Java SE support roadmap (Oracle, 2026); ASR-001 to ASR-007. |
| Linked requirements | FR-001, FR-009, FR-014, NFR-002, NFR-003, NFR-007, NFR-008, ASR-001, ASR-002, ASR-006, ASR-007 |
| Later Consequence | If Spring Boot 4 causes blocking problems, falling back to the previous Spring Boot major version is possible with limited code change. Any change of database away from PostgreSQL would affect DEC-005 to DEC-008 (triggers, partial index). Reassessment trigger: if Spring Security with JWT login (API-02, FR-014) is not working on the main branch by 7 October 2026, the team raises a change request to reassess the stack against the decision matrix (R-20). |

# Data & Persistence Baseline

This section sets the initial data model for CivicConnect and the decisions that protect business correctness - a request can never end up in an invalid state, be accepted by two handlers at once, or lose its history. It builds on ASR-002, ASR-003, ASR-004 and ASR-005. The first version of the ERD (PED v1.2) was reviewed for M2 and updated; the changes and reasons are listed under 'Changes from the Initial ERD'. M4 (CR-020): the tables in this chapter now describe the schema as built - the database build scripts plus Flyway V3 to V7. The M2 design is kept in the decision records below and in PED v2.0.

## Persistence Model Decision

| DEC-005 - Relational persistence with PostgreSQL |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | CivicConnect needs a database to store service requests, their assignment and audit history, staff and client accounts and categories. |
| Constraints | Cost (no funds for billed infrastructure), Security/POPIA (personal data), Time. |
| Alternatives | 1. A relational SQL database such as PostgreSQL (free and lightweight) to ensure referential integrity. 2. A relational alternative such as MySQL/MariaDB. 3. A NoSQL document database such as MongoDB, allowing more flexible handling of data (supports service requests with varying structures). |
| Decision | Use PostgreSQL, hosted on the Supabase free plan (ARC-03). |
| Rationale | Structure: requests, accounts and audit entries have a mostly fixed structure, so the flexibility of NoSQL is not needed. Relationships: the model has 7 related tables with foreign keys (Request - Category - Client - Employee - AuditEntry). Referential integrity is enforced by the database, not by our code. Access patterns: staff filter and sort by status, category and date (FR-006) and management needs counts grouped by status and category (FR-012/013) - both are plain SQL with indexes. Integrity and consistency: ACID transactions let a status change and its audit entry be saved together (ASR-002, ASR-003). CHECK constraints, unique constraints, partial indexes and triggers enforce rules that MongoDB would leave to the application. Sensitivity: column-level control over what is stored and database roles/grants support POPIA (ASR-005). Growth: expected volume (see Scalability below) is small for PostgreSQL. The team has experience with it, and PostgreSQL has better support than MySQL for the features we need (partial indexes, CHECK constraints, trigger functions) and is the database Supabase offers for free. |
| Trade-offs | Limited flexibility if schema requirements change - every change needs a migration (DEC-008). |
| Risks | Service requests may need completely different fields per category later on, which would require substantial database and code changes. If this happens, a JSONB column for category-specific fields can be added without changing the rest of the model. |
| Evidence | ASR-002, ASR-003, ASR-004, ASR-005, FR-006, FR-009, FR-010, FR-012, FR-015. |
| Later Consequence | Confirmed for the M2 baseline. The use of PostgreSQL-specific features (trigger, partial unique index) means changing database later would affect DEC-006 to DEC-008. M4: as built the schema has 8 tables (client, employee, category, request, request_handler, handler_category, comment, audit_entry) and one view (audit_log); the triggers, the partial unique index, row level security and the SECURITY DEFINER functions are all PostgreSQL-specific. |

## Entities, Aggregates and Ownership

Each table is owned by one module (ARC-02). Only the owning module writes to it; other modules ask the owning module's service. The Request is the main aggregate: its assignments and audit entries are only ever changed through the Request's service, so the rules in ASR-002 and ASR-003 cannot be bypassed.

| Entity | Aggregate / owning module | Purpose | Lifecycle / retention | Sensitivity |
| --- | --- | --- | --- | --- |
| Request | Request aggregate root / Requests | One service request submitted by a client (FR-001). | Created as New by a requester. Changes only through the state machine. Closed or Rejected requests become read-only (FR-011). Never hard-deleted. | Medium - description and location may contain personal information. |
| AuditEntry (audit_entry) | Written only by the database trigger; read by Reporting (AuditService) | Change log of every insert, update and delete on the seven audited tables: old and new row as JSON, actor and time (FR-007, NFR-006, C-02). | Insert only: triggers block UPDATE, DELETE and TRUNCATE. Staff and management read it through the audit_log view (C-08). Retention period to be confirmed (POPIA). | Medium - client personal values are masked in audit_log |
| RequestHandler | Part of Request aggregate / Requests | Which employee handled the request and when (FR-008). | Row created on assignment; UnassignedAt set when reassigned. Never deleted. | Low |
| Comment (comment) | Part of Request aggregate / Requests | A staff note on a request; visible_to_requester decides whether the requester sees it (FR-010, FR-004). | Insert only: triggers block UPDATE, DELETE and TRUNCATE. Never edited or deleted. | Medium - free text may contain personal information |
| Category | Reference data / Requests (maintained by Management) | Controlled category list (FR-015). | Deactivated (Active = false) instead of deleted, because old requests still point to it. | Low |
| Client | Account / Access | Requester account. | Created on registration. Deactivated, not deleted, so audit history stays valid. Deletion/anonymising on request is deferred (POPIA). | High - personal information |
| Employee | Account / Access | Handler and manager accounts, with Role. | Created by Management. Deactivated when the person leaves. | High - personal information |
| HandlerCategory (handler_category) | Access | Which categories a handler may see and work on (FR-005). | Maintained by Management (API-16). Own key handler_category_id; (emp_id, cat_id) unique. | Low |

The Reporting module owns no tables. It only runs read-only aggregate queries (counts per status/category/date) through its own read-only query repository (the ARC-02 exception) and never uses the Requests module's entities or returns personal fields (ASR-005).

## Database ERD

Figure 3 - ERD v3: the physical schema after Flyway V1 to V8 (docs/ERD v3.drawio). ERD v2 is in PED v2.0. Flyway's own table, flyway_schema_history (the list of applied migrations), is left out: it is Flyway's bookkeeping, has no relationships and holds no CivicConnect data.

## Entities

v4.0 (CR-020): the Entities and Relationships tables below describe the schema as built (Figure 3, Flyway V1 to V7). The M2 design (ERD v2) is in PED v2.0; the differences are listed under Changes from the Initial ERD.

| Entity | Primary Key | Key Attributes |
| --- | --- | --- |
| client | client_id | first_name, surname, email (unique), password (BCrypt hash), phone, active, created_at, updated_at (date_of_birth removed by V8, CR-022) |
| employee | emp_id | first_name, surname, email (unique), password (BCrypt hash), role (STAFF / MANAGEMENT), phone, date_of_birth, street, area, city, postal_code, active, created_at |
| request | req_id | ref_num (unique, CC-yyyy-nnnnnn), cat_id (FK), requester_id (FK), description, location, attachment_url, status, priority (LOW / MEDIUM / HIGH or null), created_at, updated_at, closed_at |
| request_handler | req_handler_id | req_id (FK), emp_id (FK), assigned_at, unassigned_at |
| audit_entry | aud_id | table_name, operation (INSERT / UPDATE / DELETE), record_id, old_data, new_data (row as JSON text), emp_id (FK, nullable), client_id (FK, nullable), changed_at |
| category | cat_id | cat_name (unique), active |
| handler_category | handler_category_id | emp_id (FK), cat_id (FK); (emp_id, cat_id) unique |
| comment | com_id | req_id (FK), emp_id (FK), content (up to 2000 characters), visible_to_requester, created_at |
| audit_log (view, V6) | aud_id | The audit_entry columns, with client name, email, phone and date of birth masked; staff see request, request_handler and comment rows only |

## Relationships

| From | To | Via | Cardinality | Purpose |
| --- | --- | --- | --- | --- |
| client | request | requester_id (FK on request) | 1 client - 0..M requests | A client submits any number of requests; each request has exactly one requester. |
| client | audit_entry | client_id (FK on audit_entry, nullable) | 0..1 client - 0..M audit entries | The requester who made the change, such as submitting a request or registering. |
| employee | audit_entry | emp_id (FK on audit_entry, nullable) | 0..1 employee - 0..M audit entries | The staff member or manager who made the change. |
| employee | request_handler | emp_id (FK on request_handler) | 1 employee - 0..M request_handler rows | An employee can be assigned to handle multiple requests over time. |
| request (and the other audited tables) | audit_entry | table_name + record_id (no foreign key; written by the trigger) | 1 row - 0..M audit entries | Every insert, update and delete is logged with the changed row's key, so one audit table covers all seven audited tables (C-02). |
| request | request_handler | req_id (FK on request_handler) | 1 request - 0..M request_handler rows | Keeps every assignment over the request's life; only one row has no unassigned_at at a time (ux_request_handler_active). |
| category | request | cat_id (FK on request) | 1 category - 0..M requests | Every request must belong to exactly one Management-controlled category (FR-015). |
| employee + category | handler_category | emp_id and cat_id (FKs, unique together); own key handler_category_id | M:N junction | Gives each handler a category scope, so staff only see requests in their categories (FR-005). |
| request | comment | req_id (FK on comment) | 1 request - 0..M comments | Staff notes on a request (FR-010). |
| employee | comment | emp_id (FK on comment) | 1 employee - 0..M comments | The staff member who wrote the note. |

## Integrity and Validation Rules

Rules that protect business correctness are enforced in the database where possible, so a bug in one service method or a manual SQL fix cannot break them. The Angular form validation is only for usability; the server always validates again.

| # | Rule | Enforced in the database | Enforced in the application | Traces to |
| --- | --- | --- | --- | --- |
| 1 | Status can only be a defined value and can only change through the state machine. | CHECK constraint on Request.Status. closed_at is set exactly when the status is Closed or Rejected (chk_request_closed_at). | RequestStatus Java enum and the allowed-transition map in TransitionPolicy (DEC-011), called by RequestService; invalid transition returns 422 with a message. | FR-009, ASR-002 |
| 2 | A request can only be accepted by one handler at a time. | Partial unique index ux_request_handler_active on request_handler (req_id) WHERE unassigned_at IS NULL. | Row lock: the request is loaded with SELECT ... FOR UPDATE before every change (C-01). | FR-008, ASR-002 |
| 3 | Audit entries can never be changed or deleted. | Trigger rejects UPDATE and DELETE on audit_entry (DEC-007). Also TRUNCATE, and the same triggers protect comment. | Audit rows are written only by the database trigger (C-02); the application only reads them, through the audit_log view (C-08). | FR-010, NFR-006, ASR-003 |
| 4 | Each audit entry has at most one actor (none for system changes such as migrations). | CHECK chk_audit_one_actor: at most one of emp_id / client_id is set. | Actor taken from the logged-in user, never from the request body. It reaches the trigger through transaction settings (civicconnect.emp_id / civicconnect.client_id). | NFR-006 |
| 5 | Closed and rejected requests are read-only. | - | RequestService rejects any change when status is Closed or Rejected. | FR-011 |
| 6 | A request must have a valid, active category. | FK request.cat_id; NOT NULL. | Service checks category.active on submit (422 CATEGORY_INACTIVE). | FR-015 |
| 7 | Required fields are always present. | NOT NULL on description, location, cat_id, requester_id, status, created_at (see API & Integration Design, Validation and Security at the Boundary). | @NotBlank / @Size on request DTOs. | FR-001 |
| 8 | Reference numbers and emails are unique. | UNIQUE on request.ref_num, client.email, employee.email and category.cat_name. Uniqueness of an email across clients and employees is checked by the application through email_in_use() (V6), not by a constraint (TD-08). | ref_num is generated by the service from request_ref_seq, never typed in. | FR-001, NFR-002 |
| 9 | Passwords are never stored in plain text. | The password column only holds a BCrypt hash; the audit trigger never copies it (it records password_changed instead). | BCrypt password encoder (Spring Security). | NFR-002 |
| 10 | Requesters only see their own requests. | Row level security: the requester role only sees its own client row, requests and visible comments (V6, C-08). | Queries always filter on requester_id = the logged-in client; another client's request returns 404 (API error model). | FR-003, ASR-001 |
| 11 | Priority is Low, Medium, High or not set. | CHECK chk_request_priority (V4). | Only Management can set it (API-12); the body only accepts the three values. | FR-016 |
| 12 | A staff member is linked to a category only once. | UNIQUE (emp_id, cat_id) on handler_category. | API-16 replaces the whole set of categories. | FR-005 |
| 13 | An assignment cannot end before it starts. | CHECK chk_request_handler_dates. | unassigned_at is set from the server clock. | FR-008 |
| 14 | Each user type can only use its own tables and rows. | Roles civicconnect_client, _staff and _management with table and column grants (V3); row level security (V6); the application login cannot create objects (V6). | DbSession switches to the user's role in every transaction (C-03). | ASR-001, NFR-003 |
| 15 | Text fields have length limits. | VARCHAR limits, e.g. location 255, comment 2000, attachment_url 500; description is TEXT. | @Size on the DTOs (description 2000, location 255, attachment link 500, http/https only); tested by descriptionBoundaries and locationBoundaries. | FR-001 |

## Transactions and Concurrency

| DEC-006 - One transaction per state change, with optimistic locking |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | Assigning, changing status and closing a request (FR-008, FR-009, FR-011) each change the Request and also write an AuditEntry (and a RequestHandler row for assignment). If one write succeeds and the other fails, the audit trail has gaps (NFR-006). Two handlers could also open the same request and accept it at the same time, and the second save would silently overwrite the first (lost update). |
| Constraints | Time, Team capability; PostgreSQL default isolation (Read Committed). |
| Alternatives | 1. No concurrency control - last write wins. 2. Optimistic locking with a Version column (JPA @Version). 3. Pessimistic locking (SELECT ... FOR UPDATE) while the handler works on the request. 4. Serializable isolation for every transaction. |
| Decision | Every state-changing operation is one public @Transactional method in RequestService that: loads the request, checks the user's role and category scope, checks the transition against the state machine, updates the Request, inserts the AuditEntry (and RequestHandler row), and commits everything together - or rolls everything back. Request has a Version column (optimistic locking). If the request changed since the user loaded it, the save fails and the API returns 409 Conflict: 'This request was updated by someone else - please refresh.' If the request already has an active handler, API-08 returns 409 ALREADY_ASSIGNED: 'This request is already assigned' (FR-008, CR-007). |
| Rationale | Contention is low (up to 20 users, and a request is normally handled by one person), so optimistic locking is enough and holds no locks while a user is reading or typing. Pessimistic locks could leave requests locked if a user closes the browser, and serializable isolation adds retries everywhere for no benefit. |
| Trade-offs | A user occasionally has to refresh and try again. A global exception handler is needed to turn the optimistic-lock exception into a clear 409 message. |
| Risks | A new write method without @Transactional, or one service method calling another inside the same class (which skips Spring's transaction proxy), would break atomicity. Mitigation: all writes go through RequestService's public methods, and an integration test checks that a failed audit insert rolls back the status change. |
| Evidence | ASR-002, ASR-003, FR-008, FR-009, NFR-006, NFR-007. A2 Task 2 (ACID transaction for the status update and action log; concurrency control, where A2 recommended pessimistic locking - see the Research-to-Decision Map for why M2 chose optimistic locking). |
| Linked requirements | FR-008, FR-009, FR-010, FR-011, NFR-006, NFR-007 |
| Later Consequence | If contention grows (many handlers sharing one queue), a pessimistic lock for the assignment step only will be reconsidered. |

M3 change (C-01): concurrency control is a row lock, not a Version column. Every change to a request loads it with SELECT ... FOR UPDATE (RequestRepository.findByIdForUpdate), so two changes to the same request run one after the other and the second is checked against the first one's result. The partial unique index on request_handler remains the final guard against two active handlers.

## Append-only Audit Trail

| DEC-007 - Enforce the append-only audit trail in the application and the database |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | FR-010 and NFR-007 say comments and audit entries cannot be edited or deleted. If this is only enforced by our code, a bug or a manual SQL fix could still change history. |
| Constraints | Security, Quality, Time. |
| Alternatives | 1. Application only - no update/delete methods on the audit repository. 2. Database trigger that rejects UPDATE and DELETE on audit_entry. 3. A separate audit database or logging service. 4. Hibernate Envers (automatic entity version tables). |
| Decision | Options 1 and 2 together: AuditEntry is an immutable JPA entity with a repository that only saves and reads, and a Flyway migration creates a trigger that raises an error on any UPDATE or DELETE of audit_entry rows. |
| Rationale | The trigger protects the history for every user and tool that connects to the database, not only our application. A separate audit service is disproportionate (ARC-02, ASR-007). Envers records entity versions but not our business events such as comments, and adds extra tables. |
| Trade-offs | A genuine mistake in a comment cannot be corrected - a new correcting entry must be added instead, which is the intended audit behaviour. The trigger is PostgreSQL-specific. |
| Risks | Test data clean-up cannot delete audit rows; tests reset the schema with Flyway clean on the test database only (never enabled on Supabase). |
| Evidence | ASR-003, FR-010, NFR-006, NFR-007. A2 Task 2 (enforce rules in the application with database constraints as a safety net). |
| Linked requirements | FR-007, FR-010, NFR-006, NFR-007 |
| Later Consequence | An audit retention/archiving period is still needed for POPIA and will be decided with CivicConnect (deferred). |

M3 change (C-02): audit rows are written by a SECURITY DEFINER trigger on each audited table (old and new row as JSON, the acting user taken from the transaction), not by an AuditListener. The request history (API-11) and the requester's status history (V5 function request_status_history) are built from these rows. As built: the trigger function audit_row_change runs as the owner with a fixed search_path (V6), skips updates that change nothing, never copies password hashes, and takes the actor from the transaction settings. The block_change triggers stop UPDATE, DELETE and TRUNCATE on audit_entry and comment. Staff and management read the trail through the audit_log view, which masks client personal values (C-08). Tests do not use Flyway clean: each integration test runs in a transaction that is rolled back, and they refuse to run against a non-local database (D-33).

## Schema Migrations and Configuration

| DEC-008 - Flyway versioned migrations, Hibernate in validate mode |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | Three team members each need an identical database, and the same schema must be created on Supabase. Schema changes must be controlled like code. |
| Constraints | Time, Team capability, GitHub governance (all changes through reviewed pull requests). |
| Alternatives | 1. Let Hibernate create/update tables automatically (spring.jpa.hibernate.ddl-auto=update). 2. Hand-run SQL scripts. 3. Liquibase. 4. Flyway. |
| Decision | Flyway versioned SQL migrations in src/main/resources/db/migration (V1__init_schema.sql, V2__erd_v2.sql, V3__audit_append_only.sql, V4__seed_categories.sql, ...) run automatically on start-up. Hibernate runs with spring.jpa.hibernate.ddl-auto=validate, so it checks the entities match the tables but never changes the schema. Dependencies: spring-boot-flyway, flyway-core and flyway-database-postgresql (the Spring Boot 4 documentation names spring-boot-starter-flyway, which brings in the same spring-boot-flyway module; flyway-database-postgresql is required for PostgreSQL) (Spring, 2026c). Database URL, username and password come from environment variables referenced in application.properties; credentials must never be committed (a local development password in the prototype is tracked as R-22). |
| Rationale | Every schema change is a file in Git that is reviewed in a pull request. ddl-auto=update cannot create our CHECK constraints, partial index or trigger, and can silently change tables. Flyway uses plain SQL, which the team already knows, and is simpler than Liquibase's XML/YAML changelogs. |
| Trade-offs | A migration that has already run must never be edited - every change needs a new version file. SQL is written by hand. |
| Risks | Editing an applied migration causes a checksum failure on start-up. Mitigation: pull request review rule - applied migrations are never changed. |
| Evidence | Spring Boot 4.1 'Database Initialization' documentation (Spring, 2026c); DEC-005, DEC-007; GitHub & Team Governance section. |
| Linked requirements | NFR-007, NFR-008, NFR-009 |
| Later Consequence | Seeded data (categories) comes from migrations. The first manager account's password must come from an environment variable, not a migration file. |

M3: Flyway migrations V3 (database roles and grants, C-03), V4 (request priority) and V5 (request status history function) were added. The build script also creates the default manager (C-06). Flyway runs as the schema owner (FLYWAY_USER); the application connects as civicconnect_app. V6 (database hardening: no CREATE for the application login, the audit_log view and row level security, C-08) and V7 (status history only for the requester's own requests, D-36) followed. The files are V1__init_schema, V2__align_with_entities, V3__roles_and_grants, V4__request_priority, V5__request_status_history, V6__database_hardening and V7__status_history_owner_check; the file names in the decision above were the M2 plan. The build scripts create V1 and V2 directly - civicconnect_supabase_build.sql for the test project, civicconnect_production_build.sql for production (no dummy or default accounts, D-31) - and Flyway (baseline version 2) applies V3 onwards. Categories come from the build scripts, not from a migration; the first production manager is inserted by hand.

## Access Patterns and Indexing

| Operation | Requirement | Query pattern | Index / design |
| --- | --- | --- | --- |
| Staff request list with filter and sort | FR-005, FR-006, ASR-004 | Requests in the handler's categories, filtered by status/date, newest first, one page at a time | Composite index on Request (CatId, Status, CreatedAt); paging with Spring Data Pageable |
| Requester's own requests | FR-003 | Requests where RequesterId = current client, newest first | Index on Request (RequesterId, CreatedAt) |
| Request detail with audit history | FR-007 | Audit entries for one request, its assignments and its comments, in time order | Index on audit_entry (table_name, record_id, changed_at) |
| Management activity counts | FR-012, FR-013 | Counts grouped by status/category within a date range | Indexes on request (status) and (cat_id, status, created_at); returns counts only (ASR-005) |
| Look up by reference number | FR-001, FR-002 | Request where RefNum = ? | Unique index on RefNum |
| Comments of a request | FR-007, FR-010 | Comments for one request in time order | Index on comment (req_id, created_at) |
| Staff category scope | FR-005 | Categories of a staff member; staff covering a category | Unique (emp_id, cat_id) and index on handler_category (cat_id) |
| Active handler of a request | FR-008 | The request_handler row without unassigned_at | Partial unique index ux_request_handler_active; index on request_handler (emp_id) |
| Sort by priority | FR-006, FR-016 | Order by priority (High, Medium, Low, unset) | Index on request (priority) (V4) |
| Audit page, newest first | FR-007 | Latest changes across tables | Index on audit_entry (changed_at) |

## Scalability, Availability, Single Points of Failure and Backup

| Concern | Current position | Why this is accepted now | Mitigation / when revisited |
| --- | --- | --- | --- |
| Database is a single point of failure | One Supabase PostgreSQL database. If it is down or paused, the whole application is down. | NFR-005 only requires availability during demos; up to 20 users; replicas are not on the free plan (Cost constraint). | Health check the day before each demo (the free project pauses after 1 week of inactivity (Supabase, 2026a)). Revisit replicas if CivicConnect confirms uptime targets. |
| Database bottleneck | All modules share one database. Each application instance has a HikariCP pool of 10 connections. The Supabase session pooler allows 20 connections per user and database (raised from the Nano default of 15 on 18/10/2026, D-39) and 200 client connections; Flyway connects as postgres, which has its own pool. | Load is low at pilot scale, and the indexes above keep queries short. | Measured at M3: the pool is the first limit under load (stress probe). During a deploy the old and new instance together use up to 20 connections as civicconnect_app - exactly the pooler limit (D-39) - so the application pool must not go above 10 unless the pooler pool size is raised too. If reports slow down request handling, move Reporting queries to a read replica or summary table. |
| Data growth | No volume figures from CivicConnect yet. Working assumption: under 10 000 requests a year, with around 5-10 audit entries per request. | This is small for PostgreSQL and well inside the 500 MB free-plan database limit (Supabase, 2026a). No hard-coded limits (NFR-009). | Monitor database size in Supabase. Archive closed requests once a POPIA retention period is agreed. |
| Backup and recovery | The Supabase free plan has no automatic backups or point-in-time recovery (Supabase, 2026a). | Paid backups conflict with the Cost constraint. | Manual pg_dump before every milestone and before any migration on Supabase, stored outside the repository. Test one restore before the final presentation. |
| Attachments (FR-001) | The database only stores AttachmentUrl, not the file itself. | Keeps the database small. | Where files are stored is deferred together with attachment hardening (Deferred Scope). Free app hosts often lose local files on restart, so files will not be stored on the app server. |
| Application tier | One application instance. | Stateless JWT authentication (DEC-010) means no user session is kept on the server. | A second instance could be added later without code changes. |

## Data Sensitivity and POPIA

Personal information in the model is: client and employee names, emails and phone numbers, and possibly the description and location of a request. Credentials are only stored as BCrypt hashes. Categories, statuses and timestamps are not personal. To comply with POPIA (ASR-005) we:

- Removed fields no requirement uses: DateOfBirth from Client and Employee, and Street, Area, City and PostalCode from Employee (data minimisation).

- Enforce access on the server (Spring Security + category scope + RequesterId filter), not only in the Angular UI.

- Keep management reports to aggregate counts with no personal fields (resolves the Management vs POPIA stakeholder conflict and R-03).

- Keep database credentials in environment variables, keep our tables out of Supabase's exposed Data API schema, and use TLS for the database connection.

- Defer (and record as open): the retention period for closed requests and audit data, and the process for deleting/anonymising a client's data on request.

M3: client and employee date of birth and employee address columns are still stored and returned (ERD v2 change 1 was not done). Recorded as technical debt TD-03 for a team decision. M4 decision (CR-022): the employee columns stay, because the scenario does not mention an existing HR or employee database, so this application is the only record of its staff. The client date of birth had no purpose and was removed by V8__drop_client_date_of_birth.sql (TD-03 resolved). Audit rows written before V8 keep the old value, because the audit trail is append-only; the audit_log view masks it. Database controls as built: each user type has its own database role with table and column grants (V3); row level security limits requesters to their own account, requests and visible comments (V6); the audit_log view masks client names, emails, phone numbers and dates of birth for staff and management (C-08); password hashes are never copied into the audit trail.

## Changes from the Initial ERD

The ERD in PED v1.2 was reviewed against the requirements and ASRs. These changes were made for ERD v2 (shown in red in Figure 3):

| # | Change | Reason | Traces to |
| --- | --- | --- | --- |
| 1 | Removed DateOfBirth (Client, Employee) and Street, Area, City, PostalCode (Employee). | No requirement uses them; POPIA data minimisation. | ASR-005, R-03 |
| 2 | Password renamed to PasswordHash. | Makes it clear only a hash is stored. | NFR-002 |
| 3 | Added Active to Client and Employee. | Accounts are deactivated, not deleted, so audit history keeps valid foreign keys. | NFR-006 |
| 4 | Added Priority to Request. | DEC-003 decided managers assign priority, but the v1.2 ERD had nowhere to store it. | DEC-003 |
| 5 | Added Version to Request. | Optimistic locking. | DEC-006, FR-008 |
| 6 | AuditEntry: ComId renamed AuditId; added FromStatus, ToStatus and ClientId (nullable). | NFR-006 needs before/after state, and the requester's own actions (submitting) must be logged too. | NFR-006, ASR-003 |
| 7 | New EmployeeCategory table. | FR-005 limits staff to their assigned categories, which v1.2 could not store. | FR-005, DEC-002 |
| 8 | RequestHandler uses its own key (ReqHandlerId) instead of the composite (ReqId, EmpId). | The composite key stopped the same employee being reassigned to the same request a second time. | FR-008 |
| 9 | Unique constraints on RefNum, emails and CatName. | Prevents duplicate requests/accounts - one of CivicConnect's original problems. | FR-001, Problem Statement |

ERD v3 (M3) replaces ERD v2 in Figure 3. It is drawn from the schema as built (Flyway V1 to V7) and uses the physical table and column names. Differences from ERD v2:

- Change 1 was not applied: date_of_birth (client, employee) and street, area, city and postal_code (employee) are still stored (TD-03). M4: V8 removed the client date_of_birth; the employee fields are kept as the staff record (CR-022).

- Change 2 was not applied: the column is still called password; it holds only the BCrypt hash (NFR-002).

- Change 5 was dropped: request has no version column; a row lock replaced optimistic locking (C-01).

- Change 6 was replaced: audit_entry is the change log written by a database trigger for each audited table (table_name, operation, record_id, old_data, new_data, emp_id or client_id, changed_at) instead of FromStatus and ToStatus (C-02). Staff and management read it through the audit_log view (C-08).

- EmployeeCategory is called handler_category.

# Initial Design Decisions

Before the affected code was written, two genuine CivicConnect design problems were identified. Assignment 2 Task 1 supplied the alternatives. The decisions below are the team's final project-specific judgement. One follows the A2 recommendation and one partly differs from it.

## Design Problem 1: Controlling Status Transitions

A request may only move along the FR-009 state machine (New, Assigned, In Progress, Resolved, Closed, with Rejected possible from New or Assigned), and Closed or Rejected requests are read-only (FR-011). If each controller or Angular screen checks this itself, the rules get duplicated and drift apart, which breaks NFR-007 and ASR-002.

| DEC-011 - Table-driven transition map for request status |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | FR-009, FR-011 and NFR-007 need one place that decides which status moves are legal (ASR-002). |
| Constraints | Time, Team capability |
| Alternatives | 1. State pattern: one class per status that knows its own allowed moves (A2 Task 1). 2. Table-driven transition map: one EnumMap from each status to the set of statuses it may move to (A2 Task 1). 3. Checks written directly in each controller or screen. |
| Decision | Option 2. A TransitionPolicy class in the Requests module service layer holds an EnumMap<RequestStatus, Set<RequestStatus>>. RequestService.changeStatus() calls TransitionPolicy before any change. TransitionPolicy also supplies the allowed next statuses, returned as allowedTransitions in API-06, so Angular never holds the rules (ASR-006). An illegal move throws InvalidTransitionException, returned as 422 with a message (integrity rule 1). |
| Rationale | Our six statuses only differ in which moves are allowed. No status has its own fields or behaviour, so six State classes would add code without adding value. This matches the A2 recommendation. Option 3 is the duplication problem itself. |
| Expected benefit | High cohesion (all rules in one class), low coupling (controllers only call the service), easy to test as a pure function, and a new status needs one enum value and one map entry. |
| Trade-offs | If a status later needs its own behaviour, the map will start collecting special cases. |
| Risks | R-16 (rules leaking into controllers). Mitigation: PR review. |
| Evidence | A2 Task 1, Design Problem 1 (Fowler, 2018; Freeman and Robson, 2020). FR-009, FR-011, ASR-002. |
| Affected components | RequestStatus enum, TransitionPolicy, RequestService, InvalidTransitionException, global exception handler |
| Implementation evidence | Status enum and CHECK constraint exist in the prototype. TransitionPolicy: Planned. Test: TransitionPolicyTest Planned. M3: built - TransitionPolicy and TransitionPolicyTest run in CI. |
| Linked requirements | FR-009, FR-011, NFR-007, ASR-002 |
| Later Consequence | Trigger to move to the State pattern: the first status that needs its own behaviour or fields. |

RequestController --> RequestService.changeStatus()

|

+--> TransitionPolicy.check(from, to)

|      EnumMap<RequestStatus, Set<RequestStatus>>

|      illegal move -> InvalidTransitionException -> 422

v

RequestRepository (Version check, DEC-006)

## Design Problem 2: Reacting to Status Changes

Every status change must create an audit entry (NFR-006), and the requester must see the result (FR-004). Deferred scope already expects more reactions later, such as email or SMS. If RequestService calls each reaction directly, every new reaction means editing tested core logic.

| DEC-012 - Observer through Spring application events |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | Status changes and assignments trigger reactions: the audit entry now, and notifications later. |
| Constraints | Time, Security (audit is a Must requirement) |
| Alternatives | 1. Observer pattern (A2 Task 1). 2. Direct sequential calls from RequestService to each reaction (A2 Task 1). |
| Decision | Option 1, using Spring application events rather than a hand-built observer list. RequestService publishes RequestStatusChangedEvent, RequestAssignedEvent and RequestPriorityChangedEvent (FR-016). AuditListener is a synchronous @EventListener, so it runs inside the same transaction as the change (DEC-006). Future non-critical listeners, such as notifications, use @TransactionalEventListener after commit. |
| Rationale | RequestService does not need to know who reacts to a change, so new reactions are new listener classes. This follows the A2 recommendation, with one deliberate difference: A2 argued Observer isolates failures between reactions. For CivicConnect, audit is a Must, so a failed audit insert must roll back the status change. The audit reaction is therefore deliberately not isolated. Only non-critical reactions run after commit. |
| Expected benefit | Lower coupling, core logic closed for modification, RequestService testable with listeners mocked. |
| Trade-offs | Indirection: reading RequestService alone does not show that auditing happens, so the event flow is documented in the README. Transaction phases are easy to get wrong. |
| Risks | R-18. Mitigation: integration test that forces the audit insert to fail and checks the status is unchanged. |
| Evidence | A2 Task 1, Design Problem 2 (Freeman and Robson, 2020). Spring Framework documentation on application events and transaction-bound events (Spring, no date c; Spring, no date d). NFR-006, ASR-003. |
| Affected components | RequestStatusChangedEvent, RequestAssignedEvent, AuditListener, AuditEntryRepository, RequestService. Comments are written by RequestService.addComment() as COMMENT audit entries. |
| Implementation evidence | AuditEntry entity exists in the prototype. Events and listener: Planned. Test: StatusChangeRollbackTest Planned. M3: changed by C-02 - database triggers write the audit, so the status-change events and the AuditListener were not built. M4: StatusChangeRollbackTest makes the audit insert fail and checks that the status change is rolled back (R-18). Observer through Spring events is used where one module must react to a change in another: EmployeeService publishes StaffMemberRemovedEvent, and HandlerRemovalListener releases the employee's open requests in the same transaction (D-05). |
| Linked requirements | FR-004, FR-008, FR-009, NFR-006 |
| Later Consequence | DEC-006 is unchanged in effect: its audit insert is performed by AuditListener inside the same transaction. Email or SMS, if approved, is a new after-commit listener. |

RequestService.changeStatus()  [@Transactional]

|-- update Request (status, Version)

|-- publish RequestStatusChangedEvent(reqId, from, to, actor)

|

+--> AuditListener (@EventListener, same transaction)

|       insert AuditEntry STATUS_CHANGE   -> failure rolls back all

|

+--&gt; NotificationListener Planned

(@TransactionalEventListener AFTER_COMMIT)

## Research-to-Decision Map

This shows how each relevant Assignment 2 finding was used. A2 recommended options, and M2 made the final decisions. Where a decision differs, the CivicConnect-specific reason is given.

| A2 finding | A2 recommendation | Final M2 decision | Same or different | Why |
| --- | --- | --- | --- | --- |
| Task 1, Problem 1: State pattern vs transition map | Transition map now, State pattern if behaviour grows | DEC-011 | Same | Statuses only differ in allowed moves. |
| Task 1, Problem 2: Observer vs direct calls | Observer, isolating failures | DEC-012 Observer via Spring events | Partly different | Audit is a Must (NFR-006), so the audit listener runs inside the transaction and is not isolated. |
| Task 2: ACID for status update and action logging | One atomic transaction | DEC-006 | Same | A status change without its audit entry breaks NFR-006. |
| Task 2: concurrency control | Pessimistic row locking | DEC-006 optimistic locking (Version) plus a partial unique index | Different | Contention is low (A-01). Pessimistic locks could stay held while a user reads or leaves, and optimistic locking holds no locks. CR-007 is still met: the second handler receives 409. |
| Task 2: where to enforce rules | Application layer with database constraints as a safety net | Integrity rules table, DEC-007 | Same, stronger | The audit trigger protects history from any tool connecting to the database. |
| Task 2: caching on the write path | Do not cache | No caching on write paths | Same | Stale status risk (Risk Register note). |
| Task 3: requester and handler interaction | In-process interface behind a clear abstraction | ARC-02 module services, DEC-009 | Same | One deployable, so a network hop adds latency and failure modes only. |
| Task 4: branching and CI | GitHub flow, required status checks, pinned .NET SDK | DEC-013 GitHub Actions with pinned JDK 21 and Maven wrapper | Adapted | M2 selected Java (DEC-004), not .NET. |

# Deployment Compatibility

The deployment decision itself is ARC-03. This section confirms that the M2 decisions are compatible with that direction.

| Concern | Position | Link |
| --- | --- | --- |
| Direction | One Spring Boot jar (Java 21) serving the Angular build and /api, plus Supabase PostgreSQL. Application host provider deferred. | ARC-03 |
| Compatibility | Flyway, JPA and the audit trigger are plain PostgreSQL, so they work unchanged on Supabase. Hibernate needs the session pooler because transaction mode does not support prepared statements (Supabase, 2026b). | DEC-005, DEC-008 |
| Configuration and secrets | Database URL, username, password and the token signing key come from environment variables. No production secret is committed; the prototype's local development password moves to environment variables before any deployment (R-22). M3: done - commit 7ac7b9a replaced it with an environment variable (R-22 closed). CI secrets live in GitHub Actions secrets. | DEC-008, R-22 |
| State | Stateless token authentication, so the application keeps no session state and can restart or scale without data loss. All state is in PostgreSQL. | ARC-03 |
| Networking | Same origin for Angular and the API, so no CORS set-up. TLS to the database. Tables in a non-exposed schema, with row level security on the tables with personal data (V6, C-08). | ARC-03, ASR-005 |
| Operational risks | Database pause and no backups, host memory and cold starts. | R-14, R-15 |
| Deferred with evidence needed | Application host: free-tier memory, Java 21 or Docker support, IPv4/IPv6, sleep behaviour, environment variables. Attachment storage location. | ARC-03, A-02, A-05 |

# Implementation Status (Prototype)

M3 note: this chapter records the M2 prototype and is kept for history. The system as built for M3 is described in the Milestone 3 Evidence Index.

M2 marks the start of controlled construction. This section records what exists in the repository at the time of the baseline, how it maps to the architecture, and where the code does not yet match the documented decisions. Repository: https://github.com/ClarissaBierman/SEN381-Project-CivicConnect. Build and run instructions are in the README.

## Repository Structure and Architecture Mapping

Current (prototype)                         Target (ARC-02)

civicconnect-backend/                       com.civicconnect

pom.xml, mvnw, .mvn/wrapper                 requests/   controller, service,

src/main/java/com/civicconnect/                         repository, domain

CivicconnectBackendApplication.java      access/     controller, service,

model/                                                repository, domain

Client, Employee, Category,             reporting/  controller, service,

ServiceRequest, RequestHandler,                     repository (read only)

RequestHandlerId, AuditEntry            common/     config, security,

src/main/resources/                                     exception handling

application.properties

db/migration/V1__init_schema.sql

src/test/java/.../

CivicconnectBackendApplicationTests.java

civicconnect-frontend/  (category screen prototype)

The prototype currently groups all entities in one model package. Moving them into the Requests and Access modules is planned so the code follows ARC-02 (planned).

## What Is Built

| Component | Evidence | Status | Traces to |
| --- | --- | --- | --- |
| Spring Boot 4.1.1 project on Java 21 with Maven wrapper | pom.xml, mvnw, .mvn/wrapper | Done | DEC-004 |
| Flyway schema matching ERD v1.2 | db/migration/V1__init_schema.sql | Done | DEC-008 |
| JPA entities for all six ERD v1.2 tables (plus the RequestHandlerId key class) | model/*.java | Done (ERD v1.2) | DEC-005 |
| Hibernate validate mode and context test | application.properties, CivicconnectBackendApplicationTests | Test exists (generated contextLoads); not yet run in CI | DEC-008, R-21 |
| Credentials from environment variables | application.properties | Ongoing (a local development password was committed - see R-22) | DEC-008, R-22 |
| ERD v2 changes (removed fields, PasswordHash, Version, Priority, audit columns, EmployeeCategory, RequestHandler key) | V2__erd_v2.sql and entity updates | Done | Changes from the Initial ERD, R-21 |
| Append-only audit trigger | V3__audit_append_only.sql | Done | DEC-007 |
| Module packages | requests, access, reporting, common | Done | ARC-02 |
| Spring Security and Bean Validation dependencies | pom.xml | Done | DEC-004 |
| TransitionPolicy and test | TransitionPolicy.java, TransitionPolicyTest.java | Done | DEC-011 |
| RequestService.changeStatus, event and AuditListener | RequestService.java, AuditListener.java | Done | DEC-006, DEC-012 |
| Status endpoint | PATCH /api/v1/requests/{id}/status (API-09) | Done | DEC-009 |
| Angular project | civicconnect-frontend | Prototype (category screen and CategoryService only) – Done with v1 in a staging environment. | ARC-03 |
| CI workflow | .github/workflows/ci.yml | Done | DEC-013 |

M4 status: this table is the M2 record and is kept as history. Hibernate validate mode and context test: contextLoads runs in the CI Backend job on every pull request. Credentials: DB_URL, DB_USERNAME, DB_PASSWORD, FLYWAY_USER, FLYWAY_PASSWORD and JWT_SECRET are environment variables since commit 7ac7b9a (10/10/2026); the earlier local password is closed under R-22. ERD v2 changes: made by V2__align_with_entities.sql (V2__erd_v2.sql was the M2 file name); change 1 was finished in M4 for clients only (V8, CR-022). Append-only audit trigger: the block_change triggers are in V2__align_with_entities.sql lines 146 to 158 (V3__audit_append_only.sql was never created). RequestService.changeStatus: changed by C-02 - the audit triggers (V2__align_with_entities.sql lines 137 to 143) write the audit, so no status-change event or AuditListener exists.

## Known Gaps Between the PED and the Code

| Gap | Plan |
| --- | --- |
| The schema is still ERD v1.2 (DateOfBirth, address fields, password column name, composite RequestHandler key, no Version, Priority, FromStatus, ToStatus or EmployeeCategory). | V2 migration and entity updates. Until then the RTM marks these items Planned (R-21). |
| Code is packaged by layer (model) instead of by module. | Refactor into module packages (ARC-02). |
| Employee roles are STAFF and MANAGEMENT in V1, HANDLER and MANAGER in ERD v2. | Renamed in V2 (CR-008). |
| No security or validation yet. | Add both dependencies before building Access and request submission (DEC-004). |

M4 status: all four gaps were closed. The schema now matches ERD v3 through migrations V2 to V8 (V8 removed the client date of birth, CR-022). The code is packaged by module: access, requests, reporting and common (ARC-02). Roles are REQUESTER, STAFF and MANAGEMENT everywhere (C-05). Spring Security and Bean Validation are in place.

## Initial Verification

| Test | Type | Checks | Requirement | Status |
| --- | --- | --- | --- | --- |
| contextLoads | Spring context | Flyway migrates and every entity matches its table (validate mode) | NFR-007, DEC-008 | Exists (generated); not yet run in CI |
| TransitionPolicyTest | Unit | Every allowed and illegal from/to pair | FR-009, FR-011 | Planned |
| StatusChangeRollbackTest | Integration | A failed audit insert leaves the status unchanged | NFR-006, DEC-012 | Planned |
| ConcurrentAssignmentTest | Integration | Two accepts on one request: exactly one succeeds | FR-008, CR-007 | Planned |
| AuditAppendOnlyTest | Integration | UPDATE and DELETE on audit_entry fail | FR-010, DEC-007 | Planned |
| AccessControlTest | Integration | Requester token on staff endpoints returns 403 | NFR-003, ASR-001 | Planned (M3) |

M4 status: contextLoads runs in CI. TransitionPolicyTest exists. ConcurrentAssignmentTest became ConcurrencyIntegrationTest.concurrentAcceptsOneWins. AuditAppendOnlyTest became RequestWorkflowIntegrationTest.auditTrailAndNotesAreAppendOnly. AccessControlTest became ApiHttpIntegrationTest.requesterCannotUseStaffEndpoints. StatusChangeRollbackTest was added in M4 (failedAuditRollsBackStatusChange): it makes the audit insert fail for one request and checks that the status change and its note are rolled back (DEC-012, R-18).

## Application Documentation

The README in the repository is the developer-facing documentation and must agree with this PED. It contains:

- Purpose and current implementation status (from the What Is Built table above)

- Prerequisites and versions: JDK 21, Maven wrapper, Node.js LTS and Angular CLI, PostgreSQL

- Setup and run steps, including the environment variables (without values)

- Repository structure mapped to the ARC-02 modules

- Database and Flyway migration notes, including "never edit an applied migration"

- Implemented endpoints

- Where the design decisions live in the code (TransitionPolicy, the status-change event flow)

- How to run the tests, known limitations and TODOs

- Links to the PED, RTM and ADRs

# API & Integration Design

This section records the initial interface and integration decisions for CivicConnect. It defines which parts of the system talk to each other, how they do it, what information crosses each boundary and how validation, errors, security and future changes are handled. It covers only the interactions that the architecture (ARC-01 to ARC-03) and the requirements actually need. We have not added network boundaries just because APIs or microservices were taught. Relevant Assignment 2 research (Task 3) is referenced from DEC-009 and is not repeated here. Endpoints marked Planned are the agreed contract for development. The prototype currently implements Category endpoints only (see the "Current Implementation Evidence vs Contract" section).

## Interaction boundaries

| # | Interaction | Mechanism | Information exchanged | Why this mechanism |
| --- | --- | --- | --- | --- |
| IB-1 | Angular SPA ↔ Spring Boot API | REST over HTTPS, JSON bodies, JWT bearer token (DEC-009, DEC-010) | Request, category, comment, audit and activity DTOs | The only network boundary in the system - required because the UI runs in the browser (ARC-03, Tier 1). |
| IB-2 | Module ↔ module (Requests, Access, Reporting) | In-process Java calls to each module's public service class | Java objects within one transaction | Same deployable (ARC-02). A network call would add latency and break the local transaction ASR-002/003 depend on. |
| IB-3 | Application ↔ PostgreSQL | JDBC via Spring Data JPA over TLS, Supabase session pooler | SQL / entities | Decided in DEC-005 and ARC-03. |
| IB-4 | External systems (SMS, email, WhatsApp, file storage, public API) | None in v1 | - | Out of scope or deferred (Scope Baseline); recorded under the "Integrations Deliberately Not Established" section and Forward Engineering Considerations. |

## Interface Decisions (ADRs)

| DEC-009 - REST/JSON API between the Angular SPA and the back end |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Eduard Herman |
| Context | ARC-01 and ARC-03 separate the Angular SPA (browser) from the Spring Boot back end. ASR-006 requires all business rules to be reachable through the back end only, so another client could be added later. The team must decide how the SPA and back end communicate. |
| Constraints | Time and Team capability (ASR-007), Security (ASR-001), Performance (ASR-004). |
| Alternatives | 1. REST over HTTP with JSON. 2. GraphQL. 3. gRPC / gRPC-Web. 4. Server-rendered pages (Thymeleaf) with no public API. |
| Decision | A resource-based REST API under /api/v1 with JSON request/response bodies built from DTOs (never JPA entities), standard HTTP status codes and one error format (the "Error Model" section). Modules talk to each other in-process, not over HTTP (IB-2). |
| Rationale | Our operations map directly onto resources and actions (submit, list, change status, comment). Spring Web and Angular HttpClient support REST natively. REST keeps business rules on the server, so a future mobile client reuses the same endpoints (ASR-006). GraphQL's flexible queries are not needed for around 15 fixed screens and make per-field authorisation harder (ASR-001). gRPC-Web needs an extra proxy. Server-rendered pages were already rejected in ARC-03 because they tie the UI to the server. |
| Trade-offs | Some screens need more than one call (e.g. request detail plus audit history). DTOs add mapping code. |
| Risks | The Angular client and API contract could drift apart (R-12). Mitigation: the endpoint contract table is the reference, every endpoint change updates it in the same pull request, and Angular and the API are built and deployed together in one jar (ARC-03). |
| Evidence | ASR-001, ASR-004, ASR-006, ASR-007; ARC-01, ARC-03; prototype CategoryController ↔ Angular CategoryService demonstrates the pattern end to end. A2 Task 3 (in-process interfaces behind a clear abstraction for requester and handler interaction). |
| Linked requirements | FR-001 to FR-016, NFR-003, NFR-008 |
| Later Consequence | A mobile or second client uses the same /api/v1. Breaking changes require a change request and /api/v2 (the "Versioning and Change" section). |

| DEC-010 - Stateless JWT authentication for the REST API |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Eduard Herman |
| Context | Every endpoint except register and login must know who the caller is and their role (ASR-001, NFR-002, NFR-003). The Scalability section assumes no user session is kept on the server. The team must choose how users authenticate to the API. |
| Constraints | Security/POPIA, Cost (free only), Time, Team capability. |
| Alternatives | 1. Server-side session with an HttpOnly session cookie (Spring Security default). 2. JWT access token signed by our back end and sent as Authorization: Bearer. 3. External identity provider (Supabase Auth / Keycloak / Auth0). 4. HTTP Basic authentication on every call. |
| Decision | Option 2. POST /api/v1/auth/login checks the email and BCrypt hash and returns a signed JWT (HS256, 60-minute expiry) with claims for user id, account type (CLIENT/EMPLOYEE) and role (REQUESTER / HANDLER / MANAGER). Spring Security's OAuth2 Resource Server validates the token on every request. The signing secret is read from an environment variable. Angular keeps the token in memory (sessionStorage as fallback) and attaches it through an HttpInterceptor. Refresh tokens are deferred - the user logs in again after 60 minutes. |
| Rationale | Stateless: the application tier keeps no sessions, so a second instance could be added without code changes (Scalability table). Works identically for a future mobile client (ASR-006). Uses Spring Security's built-in JWT support, so no cryptography code is written by the team. Option 1 would also work on our single origin but ties us to server session state. Option 3 adds an external dependency, account-linking work and another free-tier limit with no requirement behind it. Option 4 sends the password with every request. |
| Trade-offs | A token cannot be revoked before expiry - a deactivated account keeps access for up to 60 minutes (mitigated by checking Active at login and re-checking in the service layer on writes). No refresh token means users re-authenticate hourly. |
| Risks | Token theft via XSS if stored in the browser (R-11). Mitigation: Angular's built-in template escaping, no innerHTML with user data, short expiry, HTTPS only. Signing secret leak. Mitigation: environment variable only, never committed, rotated if exposed. |
| Evidence | Spring Security Reference - OAuth 2.0 Resource Server JWT (Spring, no date e); IETF RFC 7519 (Jones, Bradley and Sakimura, 2015); OWASP API Security Top 10 (2023) API2 Broken Authentication (OWASP, 2023); ASR-001, NFR-002, NFR-003. |
| Linked requirements | FR-014, FR-005, FR-003, NFR-002, NFR-003, ASR-001, ASR-005, ASR-006 |
| Later Consequence | Adds spring-boot-starter-security and spring-boot-starter-oauth2-resource-server to DEC-004. If CivicConnect later wants SSO (Deferred Scope), DEC-010 is superseded by an identity-provider ADR and the login endpoint is replaced. |

## API Conventions

- Base path: /api/v1; plural resource nouns (/requests, /categories).

- Format: JSON, camelCase field names; timestamps in ISO-8601 UTC (e.g. 2026-09-30T14:05:00Z).

- DTOs only: entities are never returned directly; PasswordHash, internal Version handling and unrelated personal fields never leave the server.

- Identity from the token, never the body: requesterId, comment author and audit actor are always taken from the JWT.

- Paging and sorting: ?page=0&size=20&sort=createdAt,desc; maximum size 100; paging is done in the database (ASR-004).

- Concurrency (M3, C-01): every change to a Request locks its row for the transaction; clients do not send a version.

- Status values: NEW, ASSIGNED, IN_PROGRESS, RESOLVED, CLOSED, REJECTED - matching the FR-009 state machine.

- Role values (M3, C-05): REQUESTER, STAFF (H in the table below) and MANAGEMENT (M).

- Rate limits (M3, C-04): too many calls give 429 TOO_MANY_REQUESTS with a Retry-After header.

## Endpoint Contract

Roles: R = Requester, H = Handler, M = Manager. "Scope" means the handler's assigned categories (EmployeeCategory). All paths are relative to /api/v1.

M3: the contract below is updated to the implemented API. In the API the roles are called STAFF (H) and MANAGEMENT (M) (C-05); no endpoint takes a version (C-01). API-18 to API-27 were added during construction; additions are non-breaking (Versioning and Change).

| ID | Method & path | Roles | Request body / params | Success | Main errors | Traces to | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| API-01 | POST /auth/register | Public | firstName, surname, email, phone, password | 202 (same message for a new and an existing email, C-09) | 400, 429 | FR-001, NFR-002 | Implemented |
| API-02 | POST /auth/login | Public | email, password | 200 {token, expiresAt, role: REQUESTER ¦ STAFF ¦ MANAGEMENT} | 400, 401 | NFR-002, FR-014 | Implemented |
| API-03 | GET /auth/me | R, H, M | - | 200 {id, role, firstName, surname, email} | 401 | FR-014 | Implemented |
| API-04 | POST /requests | R | categoryId, description, location, attachmentUrl? | 201 request detail (id, refNum, status NEW, createdAt, ...) | 400, 422 (inactive category) | FR-001, FR-015 | Implemented |
| API-05 | GET /requests/mine | R | page, size, sort | 200 page of own requests | 401 | FR-003 | Implemented |
| API-06 | GET /requests/{id} | R (own), H (scope), M | - | 200 detail incl. status, last updated, requester-visible comments and statusHistory; for staff also handler and allowedTransitions (empty when the user may not change the status) | 403, 404 | FR-002, FR-004, FR-007 | Implemented |
| API-07 | GET /requests | H (scope), M | status, open, unassigned, categoryId, from, to, page, size, sort (incl. priority) | 200 page | 400, 403 | FR-005, FR-006 | Implemented |
| API-08 | POST /requests/{id}/assignment | H (self), M (any handler) | {employeeId?} (manager only) | 200 updated request | 403, 409, 422 | FR-008 | Implemented |
| API-09 | PATCH /requests/{id}/status | H (scope), M | {toStatus, note?, noteVisibleToRequester?} | 200 updated request | 403, 409, 422 | FR-009, FR-011, NFR-006 | Implemented |
| API-10 | POST /requests/{id}/comments | H (scope), M | {content, visibleToRequester?} | 201 comment | 400, 403, 422 (closed) | FR-010 | Implemented |
| API-11 | GET /requests/{id}/audit | H (scope), M | - | 200 list of audit entries | 403, 404 | FR-007, NFR-006 | Implemented |
| API-12 | PATCH /requests/{id}/priority | M | {priority} | 200 | 403, 404, 422 (closed) | FR-016, DEC-003 | Implemented |
| API-13 | GET /categories | R, H, M | ?active=true (forced for R) | 200 list | 401 | FR-015 | Implemented |
| API-14 | POST /categories | M | {catName} | 201 | 400, 403, 409 | FR-015 | Implemented |
| API-15 | PATCH /categories/{id} | M | {catName?, active?} | 200 | 400, 403, 404, 409 | FR-015 | Implemented |
| API-16 | GET / PUT /employees/{id}/categories | M | {categoryIds[]} | 200 | 400 (unknown category or not staff), 403, 404 | FR-005, DEC-002 | Implemented |
| API-17 | GET /reports/activity | M | from?, to?, categoryId?, status? | 200 {filters, generatedAt, totals {total, open, overdue, resolved, closed, rejected}, byCategory[]} - counts only | 400, 403 | FR-012, FR-013, ASR-005 | Implemented |
| API-18 | GET / PATCH /clients/me | R | firstName?, surname?, phone?, email?, password?, currentPassword (for email/password) | 200 own profile | 400, 409 | FR-014, NFR-002 | Implemented (M3); dateOfBirth removed in M4 (CR-022) |
| API-19 | GET /clients/{id}/contact | M | - | 200 {id, name, email, phone, active} - read is logged | 403, 404 | ASR-005 | Implemented (M3) |
| API-20 | PATCH /clients/{id}/active | M | {active} | 204 | 403, 404 | NFR-003 | Implemented (M3) |
| API-21 | GET / POST /employees, GET / PATCH /employees/{id} | M | firstName, surname, email, phone?, password, role; PATCH {role?, active?} | 200 / 201 | 400, 403, 404, 409, 422 (LAST_MANAGER) | FR-005 | Implemented (M3) |
| API-22 | GET /categories/{id}/handlers | M | - | 200 [{id, name}] active staff covering the category | 403, 404 | FR-008 | Implemented (M3) |
| API-23 | GET /audit/{resource}, GET /audit/{resource}/{id} | M | recordId?, operation?, page, size, sort | 200 page of audit entries for one table; client entries without personal values | 400, 403, 404 | NFR-006, ASR-005 | Implemented (M3) |
| API-24 | GET /requests/{id}/comments | R (own), H (scope), M | - | 200 comments (requesters: visible only) | 403, 404 | FR-002, FR-010 | Implemented (M3) |
| API-25 | GET /categories/{id} | R, H, M | - | 200 one category (inactive: 404 for requesters) | 404 | FR-015 | Implemented (M3) |
| API-26 | PATCH /employees/me/password | H, M | currentPassword, password | 204 | 400 (wrong current password, on currentPassword), 429 | FR-014, NFR-002, R-25 | Implemented (M3) |
| API-27 | GET /health | Public | - | 200 {status: UP, database: UP} | 503 {status: DOWN} when the database cannot be reached | NFR-005, ARC-03 | Implemented (M3) |

There is deliberately no DELETE /categories/{id}: categories are deactivated because existing requests still reference them (Entities, Aggregates and Ownership table). The prototype's hard delete will be removed (the "Current Implementation Evidence vs Contract" section).

## Error Model

All errors use one response body based on Spring's ProblemDetail (IETF RFC 9457; Nottingham, Wilde and Dalal, 2023), extended with a machine-readable code:

{

"type": "about:blank",

"title": "Invalid status transition",

"status": 422,

"code": "INVALID_TRANSITION",

"detail": "A request cannot move from NEW to RESOLVED.",

"instance": "/api/v1/requests/42/status",

"timestamp": "2026-09-30T14:05:00Z",

"fieldErrors": []

}

| HTTP | Code | When | Angular behaviour |
| --- | --- | --- | --- |
| 400 | VALIDATION_FAILED | Bean Validation fails (missing or too-long fields) | Show fieldErrors next to the form fields |
| 401 | UNAUTHENTICATED | Token missing, expired or invalid; or the account was deactivated ("Your account is no longer active") | Clear token, redirect to login; deactivated: login page explains why |
| 403 | FORBIDDEN | Wrong role, or handler outside category scope | "You do not have access" |
| 404 | NOT_FOUND | Resource does not exist - or a requester asks for another client's request (the API does not reveal that it exists) | "Not found" |
| 409 | CONFLICT / VERSION_CONFLICT / ALREADY_ASSIGNED | Duplicate email/category name, optimistic-lock failure (DEC-006), or the request already has an active handler (API-08, partial unique index) (M3: VERSION_CONFLICT is not used - C-01) | "Updated by someone else - please refresh" or "This request is already assigned" |
| 422 | INVALID_TRANSITION / REQUEST_CLOSED / CATEGORY_INACTIVE | A business rule is broken | Show the detail message |
| 422 | OUT_OF_SCOPE / LAST_MANAGER | Handler does not cover the category; the last active manager would be removed (M3) | Show the detail message |
| 429 | TOO_MANY_REQUESTS | Rate limit or login lockout (M3, C-04); Retry-After header | Show the detail ("try again in ...") |
| 503 | SERVICE_UNAVAILABLE | Database unreachable (e.g. paused Supabase project) | "Service temporarily unavailable" |
| 500 | INTERNAL_ERROR | Unexpected error - logged on the server; no stack trace in the response | Generic message |

One @RestControllerAdvice class maps exceptions to these responses, so controllers never build error bodies themselves.

## Example Interaction: a Handler Changes a Request's Status (FR-009)

This is the path used for the end-to-end trace (moved here from Architecture Diagrams and updated to the API contract):

- The Angular request-detail screen sends PATCH /api/v1/requests/{id}/status with {toStatus, version, note} and the Authorization: Bearer <JWT> header.

- The Spring Security filter chain validates the JWT and checks for the HANDLER or MANAGER role (DEC-010, ASR-001).

- RequestController validates the DTO (@Valid) and calls RequestService.changeStatus().

- RequestService (one @Transactional method) asks the Access module whether this handler may work on this category, loads the request, checks the transition against the state machine (ASR-002), compares version, updates the request and publishes a RequestStatusChangedEvent. AuditListener handles the event inside the same transaction and inserts the AuditEntry with the before/after status (DEC-012, ASR-003).

- Both writes commit together. On any failure nothing is saved and the API returns 403, 409 or 422 in the format from the "Error Model" section, which Angular displays to the user.

As implemented (M3): steps 1 and 4 changed. The body has no version (C-01); RequestService locks the request row and checks the transition against the current state. The audit row is written by the database trigger in the same transaction (C-02), not by an AuditListener.

## Validation and Security at the Boundary

- Validation twice: Angular form validation is for usability only; the server always re-validates with Bean Validation on DTOs (@NotNull categoryId, @NotBlank @Size(max=2000) description, @NotBlank @Size(max=255) location, @Email email).

- Authorisation in two layers: URL/role rules in the security configuration plus @PreAuthorize, and object-level checks in the service layer (requester owns the request; handler has the category in scope). The second layer addresses OWASP API1 Broken Object Level Authorization (OWASP, 2023) - a role check alone would let one requester read another's request by changing the id in the URL (R-10).

- Transport: HTTPS only in the deployed environment.

- Same origin: in production Angular and the API share one origin (ARC-03), so CORS is not enabled there. The CORS rule for localhost:4200 exists for local development only. M3: development uses the ng serve proxy (proxy.conf.json), so the CORS rule is not needed there; the single-jar build is still to do (C-07, TD-01).

- Privacy: response DTOs contain only the fields the screen needs; /reports/activity returns counts only (ASR-005).

- Rate limiting is implemented (C-04). Still deferred: malware scanning of attachments - only a link is stored, and it opens in a new tab without the referrer (Deferred Scope).

## Versioning and Change

- Adding fields or endpoints is non-breaking and follows a normal reviewed pull request.

- Removing or renaming fields or changing their meaning is breaking: it needs a change request (Master Brief, Section 14) and would be published as /api/v2.

- Because Angular is packaged inside the same jar as the API (ARC-03), client and server are always deployed together, which removes most version-drift risk for v1. A future mobile client would make versioning matter more.

## Current Implementation Evidence vs Contract

| Contract item | Prototype today (main, merged in PR #3) | Planned change |
| --- | --- | --- |
| /api/v1 prefix | /api/categories (no version) | Rename when the security configuration is added |
| JWT authentication (DEC-010) | None - all endpoints open | Add before the Requests module is built |
| DTOs | Category entity returned directly | Add CategoryDto |
| No hard delete | DELETE /api/categories/{id} exists | Remove; use PATCH with active = false |
| Error model | Spring default errors; 404 only | Add @RestControllerAdvice with ProblemDetail |
| Same origin / proxy | CORS config plus hard-coded http://localhost:8080 in category.service.ts | proxy.conf.json for ng serve; relative /api/v1 URLs |

The prototype proves the IB-1 path works end to end (Angular HttpClient → Spring controller → JPA → PostgreSQL). The rows above are tracked as open items and are not claimed as implemented.

M3 status: every row above is resolved - all endpoints are under /api/v1 with JWT authentication, responses are DTOs, there is no DELETE endpoint, every error uses the error model, and the frontend uses relative /api/v1 URLs through proxy.conf.json.

## Integrations Deliberately Not Established

SMS/email notifications, WhatsApp intake, attachment file storage (only AttachmentUrl is stored), a public third-party API and SSO are not built. They are recorded here rather than invented and each is reconsidered through change control. Evidence needed before committing to any of them: provider free-tier limits, POPIA implications, and failure behaviour when the provider is unavailable.

# User Interface Design

This section records the initial user-interface and interaction design for CivicConnect. The wireframes are low-fidelity: they show what each role sees and does, which requirement and API endpoint each part of the screen supports, and how errors are shown. They are not the final visual design - final UI polish is not part of M2 (M2 brief, Section 11). The numbered markers on each wireframe are explained in the notes under it.

## Screen Map

One Angular application serves all roles (ARC-01). After login the menu only shows the screens for the user's role, and the API checks the role again on every call (ASR-001, DEC-010).

| Role | Screens | Main requirements | API endpoints |
| --- | --- | --- | --- |
| All users | Register, Login | FR-014, NFR-002 | API-01, API-02, API-03 |
| Requester | New Request, My Requests (with request detail and status history) | FR-001 to FR-004, FR-015, NFR-004 | API-04, API-05, API-06, API-13 |
| Handler | Request queue (own categories only), Request detail (change status, add note, audit history, accept) | FR-005 to FR-011, FR-016 (view only) | API-06 to API-11 |
| Manager | Activity overview, Requests (all categories, set priority, assign handler), Categories, Handler categories | FR-005, FR-012, FR-013, FR-015, FR-016 | API-07, API-08, API-12 to API-17 |

## Wireframes

Figure 4 - Wireframe 1: Requester submits a request and views their requests

Figure 5 - Wireframe 2: Service Handler request queue and request detail

Figure 6 - Wireframe 3: Management service activity overview

## Usability and Accessibility Rationale

- NFR-004: the requester form is one short screen with plain labels, required fields marked with *, and inline error messages next to the field (from the API fieldErrors). Target: 2 of 3 first-time users submit a request unaided within 5 minutes.

- Only valid choices are offered: categories come from the Management list (FR-015) and the status dropdown only lists moves that TransitionPolicy allows (DEC-011), so users cannot pick an illegal status.

- Every error from the error model has a clear message, for example "This request was updated by someone else - please refresh" for a version conflict (DEC-006).

- Accessibility: every input has a visible label, status is shown as text and not only as colour, buttons use words instead of icons, and all actions can be reached with the keyboard. Angular form controls keep labels linked to their inputs.

- Privacy by design: requesters are shown by number only and the Management overview shows counts only (ASR-005).

- Responsive web: the two panels stack on narrow screens, because native mobile apps are out of scope.

Verification: the NFR-004 informal user test (3 non-team users) is planned for M3, once the requester screens are built. Deferred again in M4 (CR-014). Final visual styling is deferred.

# Process and Team Working Agreement

The team runs on weekly check-ins to review progress, reassign work where needed and catch any member falling behind early, consistent with the mitigation already committed to in the Risk Register (R-02). Section ownership for the PED is tracked through GitHub Issues, with each member responsible for their assigned sections and, later, their assigned areas of the codebase.

Design and requirement decisions are worked through as a team. Where the three of us agree, that becomes the decision. Where we don't, we discuss it until we reach a majority view, and anything non-trivial gets logged in the Engineering Decision Log with the reasoning behind it, not just the outcome, so the choice can be revisited if circumstances change.

All work, whether it's a PED section or later code, goes through the pull request process described under GitHub & Team Governance: two real reviews from the other members before anything merges into main. This applies equally to all three of us, including whoever owns the repository.

If a member becomes consistently unavailable or can't keep up with their allocated section, the remaining two redistribute the work between them and escalate to the module lecturer if it continues to affect delivery.

# GitHub & Team Governance

Our team manages all controlled project artefacts and code through a single shared GitHub repository.

Since the whole point of this milestone is to show a controlled process rather than just handing in a finished document, we set the repository up properly from the start to avoid a large amount of commits right before the deadline.

The main branch is protected. None of us can push directly to it, even by accident, because direct commits are switched off at the repository settings level. Any change, whether it's an update to the PED, the risk register, or later on actual code, has to go through a pull request.

Before a pull request can be merged it needs approval from two other team members, not just one, and none of us can approve our own work. We also made sure the setting can't be bypassed, including by whoever owns the repository, so the rule actually holds under pressure rather than being something we could quietly skip closer to the deadline.

Reviewing a pull request means actually reading the change and commenting on it, not just clicking approve. When the other members review something one of us has submitted, the expectation is that they check it makes sense against what we've already agreed, that it's consistent with the rest of the document, and that nothing important is missing or wrong. An approval with no comment on a substantial change doesn't count as a real review under our own process, even if GitHub would technically allow it.

We're using GitHub Issues to track the outstanding work for Milestone 1, one issue per section (Scope Baseline, Requirements, Constraints, RTM, Risk Register, and so on), assigned to whoever owns that section. This gives us a visible record of who is doing what and when it actually got done, rather than relying on us remembering it after the fact.

Finally, no passwords, API keys, or credentials are committed to the repository at any point. Since we haven't picked a technology stack yet that risk is currently low, but the rule stands regardless of what we build later.

Milestone 2 update: The same rules now apply to code. Each GitHub Issue gets a short-lived branch (for example feature/FR-009-transition-policy). Each PR description names the requirement, decision or risk it covers, so reviewers check it against the RTM and not only that it builds. Documentation changes to the PED are also reviewed.

Evidence so far (https://github.com/ClarissaBierman/SEN381-Project-CivicConnect): PR #1 GitHub & team governance notes (merged 08/09/2026), PR #2 Milestone 1 v1.1 (merged 30/09/2026) and PR #3 prototype backend and frontend (merged into main 30/09/2026), all merged into the protected main branch. Commits come from all three members (Clarissa: repository set-up and governance; Eduard: prototype backend and frontend; Chanri: Milestone 2 document branch).

Database changes: The schema only changes through a new Flyway migration file reviewed in a PR. A merged migration is never edited (DEC-008).

Secrets: Credentials and the JWT signing secret must come from environment variables and must never be committed. The local development password committed in the prototype is an open issue (R-22). M3: closed - it was removed in commit 7ac7b9a (R-22).

| DEC-013 - GitHub flow kept, CI started with GitHub Actions |  |
| --- | --- |
| Status / Date / Owner | Accepted - M2 baseline / 30/09/2026 / Team |
| Context | Code is now being written. R-05 warns that review could be skipped under deadline pressure. |
| Constraints | Time, Cost |
| Alternatives | GitHub flow, Gitflow, trunk-based development (A2 Task 4) |
| Decision | Keep GitHub flow with protected main, two approvals and no self-approval. Add a GitHub Actions workflow on every PR and on push to main: Temurin JDK 21, ./mvnw -B verify. Add the Angular build once frontend code exists. Make the build a required status check. |
| Rationale | A2 recommended required status checks next to human review. A2 assumed a pinned .NET SDK, and because M2 selected Java this becomes a pinned JDK and the Maven wrapper. |
| Trade-offs | Tests that start Spring need a database in CI: a PostgreSQL 17 service container in the GitHub Actions workflow, so Flyway and the audit trigger run against the same database type as Supabase. |
| Risks | R-05, R-19 |
| Evidence | A2 Task 4 (GitHub, no date; Fowler, 2024). Workflow file .github/workflows/ci.yml is planned. Done in M3: CI and Security workflows, required checks on main and prod. |
| Later Consequence | Adopted now: GitHub flow, protected main and two approvals. Planned: the CI build check, then making it a required status check. Deferred: lint, coverage and security scanning gates. M3: done - the CI workflow (backend tests with JaCoCo coverage, frontend build and tests, end-to-end tests, deployment image) and the Security workflow (CodeQL, gitleaks, dependency review) run on every push and pull request, and npm audit runs in the Frontend job. Coverage is measured and reported, not enforced as a minimum, and there is still no lint gate. |

# AI Usage Register

The following is used to record AI usage regarding this document.

| Date | Student | Tool | Engineering task | AI contribution | Verification | Decision | Issues Found |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 09/09/2026 | Chanri Du Randt | CLAUDE | Reformatting and rewriting the Engineering Decision Log entries | Critique to reformat the answers specifically the engineering decision log. | Milestone 1 was cross referenced to verify critiques before editing the document using the AI’s suggestions. | Parts of the document were rewritten with a better format such as the decision log section. | None |
| 09/09/2026 | Eduard Herman | Claude | Scope Baseline, Requirements and Constraints | Used AI to rewrite sentences to be more professional | Read through all the sentences before using the AI's suggestions | Used the sentences with a more professional tone | None |
| 09/09/2026 | Clarissa Bierman | Claude | Reviewing the full Milestone 1 document for compliance with the Master Project Brief and Milestone 1 brief, and checking for proper language and grammar. | Checked that all required sections and questions were answered, flagged formatting and terminology gaps against the brief's required table structures, and flagged sentences that read wrong or not formal enough. | Read through all flagged issues and suggested adjustments myself; accepted the ones that matched what the team actually intended and reworded anything that still sounded incorrect before applying it. | Accepted with edits and adjustments made to fit our specific document. | Found two sections that contradicted each other between team members' write-ups (access control approach, and the website/platform decision), plus a few table formats that didn't match the brief's required columns which were corrected. |
| 30/09/2026 | Chanri Du Randt | Claude | Reviewing the ASRs, Architecture Decision Records, technology stack and Data & Persistence Baseline for Milestone 2, and listing the Milestone 1 sections that needed changes. | Suggested ASRs measurable targets and links to decisions. Listed the Milestone 1 changes. | Checked every decision against our requirements, the M2 brief and the Master Brief before using it. Checked the Spring Boot, Flyway, Supabase, Angular and PostgreSQL claims against the official documentation. Compared ERD v2 with what we actually built. | Accepted with edits. Our team gave the technology stack and Supabase hosting. We changed wording to fit our document. | AI assumed the Angular build is served from the Spring Boot jar and gave its own scores in the decision matrix, so the team had to confirm or change these. |
| 30/09/2026 | Chanri Du Randt | Claude | Adding the team's edited RTM to the PED, adding citations and references, building the Change Request Register, checking the PED for logic errors and missing items, filling in placeholders, and creating the user interface wireframes. | Inserted the edited RTM and updated its endpoints, design decisions and risk IDs. Added in-text citations and reference entries. Drafted the Change Request Register with impact analyses. Listed logic errors and missing items. Updated DEC-004 and the decision matrix. Drew three low-fidelity wireframes and wrote the User Interface Design section. | Checked all citations against the sources ourselves. Answered every placeholder question as a team (owners, approvers, prototype status, team experience). Decided which logic errors to fix. Reviewed the wireframes against the requirements and API contract before approving them. | Accepted with edits. The team kept category-based visibility, chose the CR numbering from the RTM, and approved the wireframes before they were added. | AI had assumed the team already knew Java, Spring Boot and Angular; corrected in DEC-004, the decision matrix, A-03 and R-20. The AI's first CR numbering clashed with ours and was renumbered. Several risk and decision IDs were out of date and were fixed. |
| 14/10/2026 | Chanri Du Randt | Claude | Backend: module restructure, security fixes (B1 to B4), rate limiting, database roles, per-table audit API, priority, reports, tests | Proposed and wrote code and tests in a working copy; explained each change | All 233 backend tests run (unit, and integration on PostgreSQL 17); diffs read before committing; team does PR reviews | Accepted with changes the team asked for (e.g. limits per email and per IP, releasing requests on category removal) | An independent AI review found defects D-05 to D-15, all fixed with regression tests |
| 14/10/2026 | Chanri Du Randt | Claude | Frontend: Staff, Categories, Audit and Profile screens, contact requester, role rename, accessibility fixes | Wrote the Angular service tests | Production build, 28 unit tests and scripted browser checks against the running system. Code was then built locally and the screens were reviewed. | Accepted | Stale-data race on fast clicks (D-09) found in review and fixed |
| 15/10/2026 | Chanri Du Randt | Claude | M3 evidence: Playwright E2E tests, k6 load test, this PED v3.0 draft | Wrote and ran the tests; drafted the M3 chapter and the tracked changes in this document | E2E 3/3 in three consecutive runs; load-test numbers checked against the raw k6 output; team review of every tracked change | Accepted after team review | Items only the team can confirm are marked |
| 16/10/2026 | Chanri Du Randt | Claude | M3 review against the M3 brief; black-box API tests; D-40 fix; README; PED v3.0 updates | Reviewed the repository, CI history and PED against the M3 brief; wrote ApiBlackBoxIntegrationTest (15 cases), the README and the tracked PED changes of 16/10/2026 | Full backend suite run locally on PostgreSQL 17 (249 of 249) and frontend 38 of 38; the D-40 test fails on the old code; overdueBoundary failed until the time-zone fix; PR #34 reviewed and approved by Clarissa Bierman and Eduard Herman | Accepted (PR #34) | overdueBoundary exposed D-42 (tests did not run in UTC); several PED statements were out of date after PR #32 |
| 10/10/2026 – 11/10/2026 | Eduard Herman | Claude (Claude Code desktop app) | Building PED v2.0 Section 22 Wireframes 1–3 as Angular screens (requester, handler, management), with an in-memory API client following the API-04 to API-17 contract. | Drafted the components, routes, role guard, styles and 11 unit tests from the PED’s wireframes and endpoint contract. Suggested one PR per wireframe. | I checked every wireframe marker and the 22.3 accessibility rules against the screens, ran the app and went through each role myself, and ran the build and tests (11/11) on each branch before committing. PRs #6, #8 and #9 were each approved by both teammates. | Accepted with corrections, committed by me as three PRs, merged in order. The in-memory client was later replaced by the real API (PR #16). | The date filter used toISOString(), which shifted dates a day in UTC+2. Fixed before committing. The default date range hid the seed data, so it was changed to the last 30 days. “Assign to handler” needs an endpoint that isn’t in the API contract. I flagged it as a change request. |
| 14/10/2026 – 16/10/2026 | Eduard Herman | Claude (Claude Code desktop app) | Diagnosing failing tests and local setup problems | Found the root causes of: the JwtSecurityTest.noTokenNoUser failure (CurrentUserService threw ResponseStatusException instead of the PED error model) the mvnw.cmd line-ending change (Dependabot committed CRLF) the IntelliJ Maven import error (Maven 3.10 wrapper) frontend tests not starting (Node 22.13 too old for jsdom 30) the 5 npm audit findings (all Angular dev tooling) the integration-test guard (D-33) | Reproduced each problem, tested each proposed fix in a separate copy of the repo first, then re-ran the full suites (73 → 188 backend tests, 38 frontend tests). | Fixes passed on to the code owners, or applied locally (Node upgrade, IntelliJ “Bundled Maven” setting). The JWT fix was reported to the author. | The AI first misread an IntelliJ test run as only one test (it was a stale run configuration), and corrected this after seeing the test tree. |
| 16/10/2026 | Chanri Du Randt | Claude | ERD v3 from the current schema | Read the database build script and Flyway migrations V1 to V7 and generated the ERD. | Tables, columns, types and foreign keys checked against the build script and migrations. Diagram rendered in draw.io and every relationship end checked: exactly one at the parent (zero or one for nullable foreign keys), zero or many at the child. Production build script confirmed to have the same tables and keys. | Accepted. The M2 Entities and Relationships tables were kept as the baseline, with a note pointing to ERD v3, instead of being overwritten. | ERD v2 no longer matched the code: it still had Version, FromStatus/ToStatus and EmployeeCategory, and its data-minimisation change was never applied (TD-03). |
| 16/10/2026 | Chanri Du Randt | Claude | Manual test log, k6 results and finishing PED v3.0 | Checked the manual test log; moved it to docs/; added the k6 stress-probe table and interpretation; recorded the release candidate, CI run, staging URL and the Prod smoke-test results. | Every k6 figure checked against the raw output in perf/results/ and the test was run on my laptop. Release CI run and the tag’s commit checked on GitHub. Staging health check called. PED checked against the Word schema and rendered in Word. The Prod smoke tests themselves were run by Clarissa Bierman, not the AI. | Accepted by Chanri; goes through PR review like other changes. | MT-16/MT-17 used the same request (corrected by the tester); PR #34 was merged without the test-log commit; the NFR-004/NFR-005 entries were swapped; leftover placeholder text in the submission block; the PED said to run E2E and k6 against staging, which can’t use dummy accounts (D-31). |
| 13/10/2026 | Clarissa Bierman | Claude | Register and login pages; local setup and backend startup fix | Suggested code snippets for the register and login pages and the HandlerCategoryRepository query fix, and helped with local setup and debugging. | Ran the backend and frontend locally, tested register and login by hand with valid and invalid input, and ran the frontend unit tests. CI passed on the pull requests. Read through code to ensure it is okay. | Accepted with changes after my own review; merged through PR #12, #14 and #15. | The backend failed on startup because a repository still used the old composite key (D-17), fixed in PR #12. |
| 16/10/2026 | Clarissa Bierman | Claude | Frontend race-condition fixes and regression tests (PR #32) | Suggested fixes so late server replies cannot update a record that is no longer selected, and drafted regression tests for them. | Each new test was run against the old code to confirm it fails there and passes on the fix. Frontend 38 of 38 tests pass and CI is green on PR #32. | Accepted with changes; merged through PR #32 after review. | The activity page status filter was not sent to the server (D-41), fixed in the same pull request. |
| 18/10/2026 | Chanri Du Randt | Claude | Checking PED v4.0 registers and change records; merging local edits onto the main-branch PED | Compared three PED versions and moved the local M4 edits onto the main version; drafted CR-014 to CR-019, risk statuses, R-28, R-29, TD-11, TD-12, the ASR Verification table and acronyms as tracked changes | Every status and evidence claim checked against the repository, the CI history and earlier PED sections; tracked changes checked by rejecting them and comparing with the main version. | Team approves by approving the Pull Request committing this document to the repo. | Local copy missed two members' edits (R-29); new CR numbers clashed with existing ones (R-06) |

# Baseline Sign Off

| Project | Baseline Type | Version | Date | Scope reviewed (Y/N) | Requirements-traceability checked (Y/N) | Risk review completed (Y/N) | Repository-governance controls checked (Y/N) | Outcome (Accepted / Conditionally Accepted / Revision Required) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CivicConnect | Milestone 1- Engineering Foundation & Requirement Baseline | 1.0 | 09/09/2026 | Y | Y | Y | Y | Accepted |
| CivicConnect | Milestone 2 - Architecture, Technology & Initial Design Baseline | 2.0 | 30/09/2026 | Y | Y | Y | Y | Accepted |

The Milestone 2 baseline includes ASR-001 to ASR-007, ARC-01 to ARC-03, DEC-004 to DEC-013, ERD v2, the API contract (API-01 to API-17), RTM v2.0 and the Change Request Register (CR-001 to CR-012). Open or deferred decisions: the application host provider (ARC-03), attachment file storage, the POPIA retention period for requests and audit data, legacy data migration, and the V2 migration that brings the prototype schema in line with ERD v2 (R-21). Any change after this baseline follows the change request process.

Accepted with known gaps (30/09/2026), to be closed before M3: the V2 migration to ERD v2 (R-21), credentials moved to environment variables (R-22), Spring Security and Bean Validation added (DEC-004, DEC-010), and the first automated tests and CI build check (DEC-013).

# Milestone 3 Evidence Index

This chapter is the PED v3.0 evidence index for Milestone 3. It follows the ten PED v3.0 sections listed in the M3 brief (Section 6), in the same order, and points to the evidence in the repository instead of repeating it.

## Submission Information

| Item | Value |
| --- | --- |
| Team | 404 Team Not Found |
| Team members | Chanri Du Randt; Clarissa Bierman; Eduard Bernard Kruger Herman |
| GitHub repository | https://github.com/ClarissaBierman/SEN381-Project-CivicConnect |
| M3 release candidate | v3.0.0-rc1, commit 3bb0a3e (prod): https://github.com/ClarissaBierman/SEN381-Project-CivicConnect/releases/tag/v3.0.0-rc1 |
| PED version | v3.0 |
| RTM | This document: Requirements Traceability Matrix, Tables 1 to 3 (Table 3 added for M3) |
| CI and test evidence | GitHub Actions: workflow "CI" (.github/workflows/ci.yml - jobs Backend, Frontend, End-to-end) and workflow "Security" (security.yml). Test reports are uploaded as run artifacts (backend-test-reports, e2e-reports). Release run (CI on prod 3bb0a3e, all jobs green): https://github.com/ClarissaBierman/SEN381-Project-CivicConnect/actions/runs/38951977445 |
| Performance evidence | perf/README.md and perf/results/ in the repository |
| Staging / test environment | https://civicconnect-pxjj.onrender.com (Render, prod branch). Health check on 16/10/2026: database UP, status UP. Smoke tests P-01 to P-07: 7 of 7 Pass on 16/10/2026 (Prod sheet of docs/CivicConnect manual test log.xlsx) |
| Date submitted | 16/10/2026 |

## M3 Overview

All 16 functional requirements are implemented in an Angular 21 frontend and a Spring Boot 4.1 backend (Java 21) on PostgreSQL 17 (Supabase). The release candidate is built and tested by the CI workflow on every push and pull request. Remaining work before the candidate is final is listed under Release Readiness.

| Area | Requirements | Main components |
| --- | --- | --- |
| Accounts and login | FR-014, NFR-002, NFR-003 | access module: AuthService, JwtService, ActiveAccountJwtConverter; Angular login, register, profile |
| Requester | FR-001 to FR-004 | RequestService, CommentViews; requester page (form, my requests with pager, updates) |
| Handler queue and detail | FR-005 to FR-011 | RequestService, TransitionPolicy, CommentService, AuditService; request-queue page |
| Management | FR-012, FR-013, FR-015, FR-016 | ReportService, CategoryService, EmployeeService; Activity, Requests, Categories, Staff and Audit pages |
| Audit | NFR-006, NFR-007 | Database audit and append-only triggers; request history and per-table audit API |
| Security controls | NFR-003, ASR-001, ASR-005 | Database role per transaction (V3, DbSessionInterceptor), per-request account check, rate limits |

## M2 Baseline Conformance

| M2 baseline item | Implemented as planned? | Evidence |
| --- | --- | --- |
| ARC-01 one Angular app, menu per role | Yes | app.routes.ts role guard; E2E-02 |
| ARC-02 modular monolith | Yes | Packages com.civicconnect.access, requests, reporting, common |
| ARC-03 single deployable, same origin | Yes: the single jar is built in M3 (C-07); development still uses the ng serve proxy | Dockerfile; CI Deployment image job; C-07; TD-01 (resolved) |
| DEC-004 Spring Boot, Java 21, PostgreSQL | Yes | pom.xml; CI uses PostgreSQL 17; decision matrix rescored in v3.0 (CR-013), decision unchanged |
| DEC-005 / ERD v2 schema through Flyway | Yes; V3 to V7 added | db/migration V1 to V7 |
| DEC-006 optimistic locking | Changed to a row lock | C-01 |
| DEC-007 append-only audit trail | Yes (database triggers) | auditTrailAndNotesAreAppendOnly |
| DEC-008 configuration in environment variables | Yes | application.properties uses ${DB_URL} etc.; .env.example |
| DEC-009 REST API under /api/v1 | Yes, with additions | Endpoint Contract (updated); ApiHttpIntegrationTest |
| DEC-010 JWT bearer tokens | Yes, plus issuer check and per-request account check | JwtSecurityTest; ActiveAccountJwtConverterTest |
| DEC-011 TransitionPolicy state machine | Yes | TransitionPolicyTest; RequestServiceTest |
| DEC-012 events and AuditListener | Changed: database trigger writes audit rows | C-02 |
| DEC-013 CI on every PR, protected main | Yes; E2E and security workflows added | .github/workflows |
| CR-003 priority (FR-016) | Yes | V4 migration; API-12; priorityAndHistory |
| CR-008 role names Handler / Manager | Changed to STAFF / MANAGEMENT | C-05 |
| ERD v2 change 1 (data minimisation) | Not done | TD-03 |
| Data & Persistence, Scalability table: one HikariCP pool, "default 10 connections" | Conforms: 10 connections (spring.datasource.hikari.maximum-pool-size=10). Commit 7ac7b9a (10/10/2026) had lowered it to 5; the team set it back to 10 in commit 7bdb199 (15/10/2026). | The team keeps the M2 value. At most 10 queries run at once per instance, plus one connection Flyway uses at start-up; this stays within the Supabase free plan's limits, and the session pooler's pool size (Supabase dashboard) must allow at least 11. The connection pool is still the first limit a scalability test reaches (stress probe: requests queue, p95 316 ms at 259 requests/s). Run B of the load test used 5 connections (Performance). |

## Controlled Changes

Each significant change: original decision, implementation evidence or problem, revised decision, consequence. The Engineering Decision Log and the Endpoint Contract point here.

v4.0: the controlled changes C-01 to C-09 now sit with the change requests in the Change Request Register chapter (Controlled Design Changes), so that every change record is in one place.

## Construction and Configuration

- Repository: one repository with civicconnect-backend and civicconnect-frontend; GitHub flow with feature branches and pull requests into a protected main with two approvals (DEC-013).

- Commit author alias: commits authored as "CoffeeLover" in the repository history are Chanri Du Randt's (the git user name set on Chanri's laptop). Chanri's pull requests and reviews appear under the GitHub account chanri0702-jpg.

- What review caught and missed: reviews approved the pull requests without asking for code changes. When the HandlerCategory composite key (HandlerCategoryId) was replaced by a single handler_category_id key, two places still used the old key; the code looked correct, so review missed them. Both were fixed in follow-up pull requests: #11 (EmployeeService, commit 4f4bf47) and #12 (HandlerCategoryRepository, commit 2204bcc - the backend failed on startup). See D-16 and D-17. The CI Backend job now starts the application (contextLoads) and runs the integration tests on every pull request, so this kind of mismatch fails the build before a reviewer approves.

- Modules: com.civicconnect.access, requests, reporting and common. Requests and reporting call access services, never its tables.

- Database changes only through Flyway (V1 to V7). civicconnect-backend/database/civicconnect_supabase_build.sql rebuilds a test or staging database (V1 and V2, dummy data, default manager, roles); Flyway then applies V3 and later as the schema owner.

- Secrets: DB_URL, DB_USERNAME, DB_PASSWORD, FLYWAY_USER, FLYWAY_PASSWORD and JWT_SECRET are environment variables (.env locally, git-ignored; .env.example lists them). CI generates throw-away values for each run. gitleaks scans every push.

- Environments: local (ng serve proxy, local PostgreSQL), CI (PostgreSQL 17 service, random credentials), Supabase (connection pooler, Flyway as owner). All times are stored and sent in UTC.

## CI and Automated Verification

| Workflow / job | What runs | Gate |
| --- | --- | --- |
| CI - Backend | PostgreSQL 17 service built from the build script; ./mvnw verify -Pintegration,coverage: compile, 189 unit tests, 60 integration tests against the database, JaCoCo report | Any failure fails the job |
| CI - Frontend | npm ci; production build; 38 unit tests (Vitest); npm audit of runtime packages (high) | Any failure fails the job |
| CI - End-to-end | Database, backend jar and Angular dev server; 3 Playwright system tests; report and trace uploaded | Runs after Backend and Frontend; failure fails the workflow |
| CI - Deployment image | Builds the Dockerfile as Render does, starts it with 512 MB of memory against a test database and checks the health check, the Angular app and the API on one address | Runs after Backend and Frontend; failure fails the workflow |
| Security - CodeQL | Static analysis of Java and TypeScript | Findings in the Security tab |
| Security - gitleaks | Secret scanning of the history | Fails on a new secret |
| Security - Dependency review | New vulnerable dependencies in pull requests | Fails a pull request that adds a high or critical vulnerability; active (passed on PRs #32 and #33) |
| Dependabot | Weekly dependency update pull requests | Reviewed like any PR |

Backend, Frontend and End-to-end should be required checks on main, so a red build blocks merging. A green run shows that the checks passed, not that they are required: Confirmed 16/10/2026 under Settings - Rules: rulesets “main protection” and “prod protection” require Backend, Frontend and End-to-end to pass and a pull request with approval, and block force pushes.

Results on the M3 code (local run, 14-15/10/2026): backend 233 of 233 passed; frontend unit 28 of 28; end-to-end 3 of 3 in three consecutive runs with no retries. On GitHub, every CI and Security job, including End-to-end and Deployment image, passed for main at 6a198c4 (PR #32) and for the release pull request into prod (PR #33). The gate held on PR #32: the Backend job failed on commit c0dd9a7 (a compile error) and the pull request merged only after 2b6f2a8 fixed it. Local run on 16/10/2026: backend 249 of 249 (189 unit, 60 integration on PostgreSQL 17) and frontend 38 of 38. Green CI link of release candidate: https://github.com/ClarissaBierman/SEN381-Project-CivicConnect/actions/runs/38951977445.

| Backend coverage (JaCoCo) | Lines | Branches |
| --- | --- | --- |
| Unit tests only (188) | 94.4 % | 90.1 % |
| Unit and integration (233) | 97.1 % | 91.3 % |
| Unit and integration (249), 16/10/2026 | 97.1 % | 91.7 % |

Interpretation: coverage shows which backend code the tests run, not that it is correct. It is high because each business rule is small and has its own test. It says nothing about the Angular screens (covered by the end-to-end tests instead), about behaviour with Supabase latency, or about rules that are missing altogether. Tests were written from acceptance criteria and risks (Quality Strategy Applied and Black-box, Integration and System Validation), not to raise the number.

## Quality Strategy Applied

| Risk / ASR | Why it got stronger verification | Verification |
| --- | --- | --- |
| ASR-001 / R-10 access control | A requester reading someone else's data is the highest-impact failure (POPIA). | Unit (another client's request gives 404), integration over HTTP (requesterCannotUseStaffEndpoints, requesterSeesOnlyOwnRequests, databaseRoleBlocksRequester), E2E-02 |
| ASR-002 workflow and concurrency | Lost updates or illegal transitions corrupt the record. | TransitionPolicyTest, RequestServiceTest (row lock, already assigned), databaseAllowsOneActiveHandler, E2E-01 |
| ASR-003 audit | The audit must be complete and tamper-evident. | fullLifecycleIsAudited, auditTrailAndNotesAreAppendOnly, priorityAndHistory |
| ASR-005 privacy | Staff names must not reach requesters; client personal data must not be in the audit view. | clientContactVersusAudit, ResponsesNeverContainPasswordsTest, E2E-01 (no staff names) |
| NFR-002 / NFR-003 authentication | A session must end when an account is deactivated; logins must not be brute-forced. | ActiveAccountJwtConverterTest, deactivatedEmployeeTokenRefused, E2E-03, loginLockoutOverHttp, perAccountApiLimit |
| ASR-004 / NFR-001 performance | The request list is used all day. | k6 load test (Performance and Reliability) |
| Lower risk (category and profile editing) | Simple create/update screens. | Unit tests only |

## Black-box, Integration and System Validation

Techniques were chosen where the behaviour needs them.

| Technique | Where it is used | Test evidence |
| --- | --- | --- |
| Boundary value analysis | Description 2000 characters accepted, 2001 refused; password 72 bytes accepted, 73 refused (counted in bytes, so 60 accented letters are refused); location 255 accepted, 256 refused; overdue at exactly 7 days and one second later (CR-004); page size 100 and 101 | descriptionLimit; MaxBytesValidatorTest; ControllerRoutingTest; descriptionBoundaries; locationBoundaries; overdueBoundary; pageSizeCap |
| Equivalence partitioning | Callers: no token / requester / staff in scope / staff out of scope / manager / deactivated account; categories (active / inactive / unknown / missing); status and priority values (valid / unknown / missing) | noTokenIs401; requesterCannotUseStaffEndpoints; RequestServiceTest (outside categories); deactivatedEmployeeTokenRefused; categoryPartitions; statusChangePartitions; priorityPartitions |
| State transition | FR-009 state machine, invalid moves and terminal states | TransitionPolicyTest; RequestServiceTest (cannot skip steps, read-only); E2E-01 |
| Decision table | Which status changes a user is offered (table below) | allowedTransitionsDependOnTheUser; statusHistoryAndAllowedTransitions |
| Negative / failure | Unauthorised, invalid input, locked out, database unavailable | requesterCannotUseStaffEndpoints; sortByNestedFieldRefused; loginLockoutOverHttp; FilterErrorHandlerTest; E2E-02; E2E-03; malformedAndUnknown |

### Decision table: status changes offered (API-06 allowedTransitions)

| Role | Handler of the request? | Current status | Status changes offered |
| --- | --- | --- | --- |
| Requester | - | Any | None (not returned) |
| Staff (in scope) | No | New | Rejected |
| Staff (in scope) | No | Assigned, In Progress, Resolved | None |
| Staff | Yes | Assigned | In Progress, Rejected |
| Staff | Yes | In Progress | Resolved |
| Staff | Yes | Resolved | Closed |
| Manager | - | Assigned | In Progress, Rejected |
| Any | - | Closed, Rejected | None (read-only) |

### API / integration tests

60 integration tests run against a real PostgreSQL 17 database built from the build script, with the audit triggers, database roles and migrations V3 to V7: ApiHttpIntegrationTest (25, over HTTP through the whole security filter chain), ApiBlackBoxIntegrationTest (15 cases designed from the API contract only, with boundary values and equivalence classes), RequestWorkflowIntegrationTest (7), DatabaseRolesIntegrationTest (9, each database role tested directly in SQL), ConcurrencyIntegrationTest (2, two real transactions at the same time), RateLimitOrderIntegrationTest (1) and contextLoads (1). Examples: requesterCannotUseStaffEndpoints, deactivationTakesEffectImmediately, clientContactVersusAudit, prioritySortOrder, openAndUnassignedFilters, statusHistoryAndAllowedTransitions, databaseAllowsOneActiveHandler, auditTrailAndNotesAreAppendOnly.

### End-to-end / system tests (Playwright, civicconnect-frontend/e2e)

| ID | Journey | Basis | Expected result | Result |
| --- | --- | --- | --- | --- |
| E2E-01 | Requester submits; the IT Support handler accepts, moves it to In Progress, adds a visible note and resolves it; the requester sees every step | FR-001, FR-004, FR-007 to FR-010 | Only allowed statuses offered, none pre-selected; requester sees 5 updates in order and no staff names | Pass (3 of 3 runs) |
| E2E-02 | A requester tries to see another requester's request (list and direct API call with their own token) and to use staff screens and endpoints | ASR-001, NFR-003, R-10 | 404 NOT_FOUND with no data; 403 FORBIDDEN; redirected to own home screen | Pass (3 of 3 runs) |
| E2E-03 | A manager deactivates a staff member who is logged in; the staff member's next action | NFR-003, B1 | 401; login page says the account is no longer active; cannot log in again | Pass (3 of 3 runs) |

Manual system tests (docs/CivicConnect manual test log.xlsx): 33 tests on the test build (MT-01 to MT-33: a local build of prod a21dac1, the same code as main 6a198c4, against the team's test Supabase project), run on 16/10/2026 by Clarissa Bierman and Eduard Herman. Result: 31 Pass; 1 Blocked (MT-29: the shared test database has two active managers, so the last-manager rule cannot be tried without deactivating a real account; covered by lastManagerCannotBeDeactivated); 1 Not run (MT-33, the NFR-004 usability test). Prod smoke tests P-01 to P-07 on the staging site (https://civicconnect-pxjj.onrender.com, prod 3bb0a3e = v3.0.0-rc1), run on 16/10/2026 by Clarissa Bierman: 7 of 7 Pass, including P-03 (no dummy account can log in, D-31), P-04 (the first manager changed the temporary password, R-25) and P-07 (the idle site woke in about 90 seconds, R-15).

### Test evidence records (examples)

| Test | E2E-02 (access-control.spec.ts) |
| --- | --- |
| Test basis | ASR-001, NFR-003 acceptance criterion; risk R-10 (OWASP API1 broken object-level authorisation) |
| Why selected | Changing an ID in a URL is the most likely way to leak another person's request. |
| Technique / level | Negative test, equivalence partitioning of callers; system level through the browser |
| Input / precondition | Dummy data; Thabo creates a request in the test; Naledi logged in |
| Expected result | Naledi's list does not show it; GET /api/v1/requests/{id} with her token gives 404 NOT_FOUND and none of the request's text; GET /api/v1/requests gives 403; /management/activity redirects to /requests/new |
| Actual result | As expected |
| Status | Pass |
| Evidence | Playwright report (CI End-to-end job artifact e2e-reports) |
| Interpretation | Shows the object-level check in the API, not only the hidden menu. It does not prove every endpoint is protected; the integration tests cover the others. |

| Test | descriptionLimit (ApiHttpIntegrationTest) |
| --- | --- |
| Test basis | API & Integration Design 21.7: @Size(max=2000) description; defect D-14 |
| Why selected | The API allowed 5000 characters while the PED and the form allowed 2000. |
| Technique / level | Boundary value analysis; API integration |
| Input / precondition | Description of 2001 characters, requester token |
| Expected result | 400 VALIDATION_FAILED with a field error on description (2000 is accepted by the other submission tests) |
| Actual result | As expected |
| Status | Pass |
| Evidence | CI Backend job, surefire report |
| Interpretation | The server enforces the documented limit whatever the client sends. |

| Test | prioritySortOrder (ApiHttpIntegrationTest) |
| --- | --- |
| Test basis | FR-006, FR-016; defect D-07 |
| Why selected | Regression test: priority was sorted alphabetically. |
| Technique / level | Equivalence classes of priority (High, Medium, Low, unset); API integration |
| Input / precondition | Three new requests set to Low, High and Medium; seed requests without priority |
| Expected result | sort=priority,desc returns High, Medium, Low, then unset |
| Actual result | As expected |
| Status | Pass |
| Evidence | CI Backend job, surefire report |
| Interpretation | The order is now defined by the query (CASE), not by the text of the values. |

| Test | overdueBoundary (ApiBlackBoxIntegrationTest) |
| --- | --- |
| Test basis | FR-012 acceptance criterion; CR-004: overdue = not Resolved, Closed or Rejected within 7 days of CreatedAt |
| Why selected | CR-004 planned a boundary test at 7 days. An off-by-one or time-zone error would misreport overdue work to Management. |
| Technique / level | Boundary value analysis; API integration (activity report, API-17) |
| Input / precondition | The application's clock frozen at 2030-03-01 09:00 UTC, a day with no other requests; one request submitted; report filtered to that day; clock moved to 7 days minus 1 s, exactly 7 days, and 7 days plus 1 s |
| Expected result | Overdue 0, 0 and 1; total and open 1 |
| Actual result | First run on a laptop in South African time: overdue was already 1 at 7 days minus 1 s (D-42). After the fix: as expected, in UTC and in South African time. |
| Status | Pass (after D-42 was fixed) |
| Evidence | CI Backend job, surefire report; local run 16/10/2026 |
| Interpretation | The 7-day rule is exact at the boundary. The first failure showed that the tests did not run in UTC like the application (D-42); the application itself was not affected, because main() sets UTC. |

## Performance and Reliability

Operation: staff filtering the request list (API-07), the most used and most expensive read. Targets: FR-006 filter/sort within 2 s (k6 threshold p95 < 2000 ms) and NFR-001 p95 at most 3 s at up to 20 users; fewer than 1 % failed calls. Workload: 20 users (A-01), each with their own staff account, random filter mixes, 2 to 5 s think time, 30 s ramp-up, 3 minutes steady. Data: about 10,000 requests over 365 days with matching assignments and audit rows (perf/seed-perf-data.sql). Environment: backend, database and k6 on one machine, database pool of 10 connections in Run A (the committed setting) and 5 in Run B (a copy taken before 10 was restored). Run A (evidence of record): team laptop, Intel Core i7-1255U (10 cores), 16 GB RAM, Windows 11, PostgreSQL 18, k6 v2.2.0. Run B (repeat on a second machine): 2-vCPU, 8 GB Linux container, PostgreSQL 17.9, k6 v1.3.0.

| Metric (pilot workload) | Run A (15/10/2026) | Run B (14/10/2026) | Target |
| --- | --- | --- | --- |
| List calls | 1,166 | 1,157 | - |
| Median / p90 / p95 / p99 | 16.7 / 26.2 / 29.8 / 42.6 ms | 14.3 / 26.1 / 31.6 / 42.6 ms | p95 < 2,000 ms - PASS |
| Maximum | 149.9 ms | 156.8 ms | - |
| Failed calls | 0.00 % | 0.00 % | < 1 % - PASS |
| Throughput | 5.19 requests/s | 5.1 requests/s | - |

Stress probe (exploratory, not pass/fail): 50 users, no think time, 1 minute, all rate limits raised. It shows where the limits are, not a target.

| Metric (stress probe: 50 users, no think time, 1 minute; exploratory, not pass/fail) | Run A (15/10/2026) | Run B (14/10/2026) | Note |
| --- | --- | --- | --- |
| List calls | 16,098 | 11,789 | - |
| Median / p95 / p99 | 174 / 316 / 443 ms | 229 / 597 / 881 ms | No target: exploratory |
| Maximum | 839 ms | 1,885 ms | - |
| Failed calls | 0.00 % | 0.00 % | Nothing failed |
| Throughput | 259 requests/s | 189 requests/s | About 50 times the pilot rate |

What the results mean: the 2-second target (FR-006, NFR-001) is met by a wide margin - p95 was about 30 ms - and the second machine gave almost the same figures, so the result is repeatable. Under about 50 times the pilot load nothing failed: requests queued for a free database connection (10 in Run A, 5 in Run B) and, on Run B, for CPU, so the connection pool is the first limit.

Limitations: the database ran on the same machine as the application, so there was no network delay; calls from Render to Supabase will be slower, roughly 10 to 20 ms more per query (R-26). All virtual users shared one IP address, so the per-IP rate limits were raised; in the pilot the per-account limits stayed at their normal values. The test only read data; nothing was written at the same time. The data was synthetic: 10,000 requests spread evenly over categories and dates. One instance; API time only, not browser rendering. All figures were checked against the raw k6 output in perf/results/ on 16/10/2026. Full method: perf/README.md.

Reliability: a database outage returns 503 SERVICE_UNAVAILABLE from controllers and from the security filters (D-06), and the frontend shows "Service temporarily unavailable". The Supabase free plan pauses after a week without use (R-14), so the team health-checks the database the day before each demo (NFR-005). Health check on 16/10/2026: both Supabase databases were up - the test project used for local runs and the production project behind the staging site (/api/v1/health returned database UP).

## Defects and Quality Interpretation

### Defect register

| ID | Defect | Severity | Found by | Status / fix | Regression evidence |
| --- | --- | --- | --- | --- | --- |
| D-01 | Sorting by an unknown or nested field (e.g. requester.password) gave 500 and could order by a hidden column | High | Code review | Fixed: sort whitelist, 400 | sortByNestedFieldRefused; SortGuardTest |
| D-02 | A deactivated account kept working until its token expired (B1) | High | Code review | Fixed: account checked on every call | deactivatedEmployeeTokenRefused; E2E-03 |
| D-03 | Email or password could be changed without the current password (B3) | High | Code review | Fixed | ClientServiceTest |
| D-04 | No protection against password guessing (B4) | High | Code review | Fixed: C-04 | loginLockoutOverHttp; LoginAttemptLimiterTest |
| D-05 | Removing a handler also changed their Resolved, Closed and Rejected requests | High | Independent review | Fixed: only open requests released | deactivationTakesEffectImmediately; HandlerRemovalListenerTest |
| D-06 | A database outage on a logged-in call gave an unformatted 500 instead of 503 | Medium | Independent review | Fixed: filter error handler | FilterErrorHandlerTest |
| D-07 | "Sort: Priority" sorted alphabetically (unset, Medium, Low, High) | Medium | Independent review | Fixed: CASE ordering | prioritySortOrder; RequestSpecsTest |
| D-08 | The status list pre-selected "Rejected" on New requests (one click rejected) | Medium | Independent review | Fixed: nothing pre-selected | E2E-01 (Update disabled until a status is chosen) |
| D-09 | Clicking rows quickly could show, and save, the previous row's data | Medium | Independent review | Fixed: previous load cancelled | Manual check only (TD-06) |
| D-10 | Activity page left out open requests older than the date range; picker showed the newest 100 of any status | Medium | Independent review | Fixed: open / unassigned filters and buttons | openAndUnassignedFilters |
| D-11 | Staff were offered status changes the server then refused | Low | Independent review | Fixed | allowedTransitionsDependOnTheUser |
| D-12 | Requester updates used the last-updated time and missed intermediate statuses | Low | Independent review | Fixed: status history (V5) | statusHistory; request-api.service.spec |
| D-13 | A comment could be saved while the request was being closed | Low | Independent review | Fixed: row lock | CommentServiceTest |
| D-14 | API accepted 5000-character descriptions; PED says 2000 | Low | Independent review | Fixed | descriptionLimit |
| D-15 | An emptied phone number was saved as empty text | Low | Independent review | Fixed | Code review only |
| D-16 | EmployeeService still used the old HandlerCategory composite key after the database change | High | Running the backend after merge | Fixed in PR #11 (4f4bf47) | EmployeeServiceTest; contextLoads in CI |
| D-17 | HandlerCategoryRepository still used the old composite key, so the backend failed on startup | High | Running the backend after merge | Fixed in PR #12 (2204bcc) | contextLoads and integration tests in CI |
| D-18 | A requester changing their email always got a 500: the email check also read the employee table, which the requester's database role cannot read | High | Independent review (M3) | Fixed: email_in_use() database function (V6) | requesterChangesEmail; emailInUseForEveryRole |
| D-19 | The app's database login could create objects in the schema, so a planted to_jsonb overload would run as the owner inside the SECURITY DEFINER audit trigger | High | Independent review (M3) | Fixed in V6: CREATE revoked; definer functions search pg_catalog first and call built-ins by full name | appRoleCannotCreateObjects; definerFunctionsPinTheSearchPath |
| D-20 | Removing a handler read the request without a lock, so a priority or status change committed at the same moment was overwritten | Medium | Independent review (M3) | Fixed: each request is locked and re-read before it is changed | handlerRemovalKeepsConcurrentChange; locksBeforeChanging |
| D-21 | The database roles were more open than documented: staff and management could read client personal values in audit_entry, the requester role could read every row, and there was no row level security | Medium | Independent review (M3) | Fixed in V6: audit_log view, row level security (C-08) | DatabaseRolesIntegrationTest |
| D-22 | Names of only spaces were accepted and saved as empty text | Low | Independent review (M3) | Fixed: @NotBlankIfPresent on PATCH bodies | blankNamesRefused; NotBlankIfPresentValidatorTest |
| D-23 | Staff could claim an In Progress request that had lost its handler, although it waits for a manager | Low | Independent review (M3) | Fixed: staff accept New requests only | orphanedInProgressNeedsManager; staffCannotClaimOrphanedInProgress |
| D-24 | Calls with a missing, expired or forged token were refused before the per-IP rate limit, so they were never counted | Low | Independent review (M3) | Fixed: the per-IP limits run before authentication | RateLimitOrderIntegrationTest; stagesSplitTheLimits |
| D-25 | Registration revealed whether an email address has an account (409) | Low | Independent review (M3) | Fixed: the same 202 answer either way (C-09) | registrationDoesNotRevealAccounts; registerSameAnswerForTakenEmail |
| D-26 | Staff could not change their own password, and the default manager's password could only be changed with a raw API call | Medium | Independent review (M3) | Fixed: API-26 and the My account screen (C-09) | staffChangeOwnPassword; staffOnlyChangeOwnPassword; AccountPage tests |
| D-27 | Request queue: after a change, the previous request reopened even if the user had selected another one, and a slow list response could replace a newer page | Low | Independent review (M3) | Fixed: reloads go through switchMap and keep the latest selection | Code review only |
| D-28 | Some tests were weaker than they looked: the row-lock test only checked a mock, ClientServiceTest mocked away the database role problem behind D-18, and the password scan skipped three response DTOs | Low | Independent review (M3) | Fixed: tests with two real transactions; the password scan finds every DTO on the classpath | ConcurrencyIntegrationTest; ResponsesNeverContainPasswordsTest |
| D-29 | The k6 result files contained the login tokens of the 20 test staff accounts | Low | gitleaks in CI | Fixed: the script no longer saves them; the old commit is recorded in .gitleaksignore | gitleaks on every push |
| D-30 | Made-up page URLs filled the server memory: the single-jar file serving cached every URL it resolved and pages outside /api were not rate limited (20,000 requests: live heap 38 to 202 MB) | High | Second independent review (M3) | Fixed: no URL cache, only packaged files are looked up, per-IP limit on every path | SpaFallbackResolverTest; ipLimitCoversEveryPath; measured 37.0 to 37.4 MB after 20,000 requests |
| D-31 | A public deployment would start with the dummy and default accounts, whose passwords are published in the repository | High | Second independent review (M3) | Fixed: the public site deploys the prod branch against a separate production project built with civicconnect_production_build.sql (no dummy or default accounts; the first manager is created by hand) | Production build tested: default and dummy logins refused (401); the first manager logs in, changes the password and adds staff |
| D-32 | The Java memory settings could exceed the 512 MB plan (heap 70% plus about 170 MB outside the heap) | Medium | Second independent review (M3) | Fixed: heap 55%, limits for metaspace, code cache and direct memory, 40 request threads | Measured: 282 MB heap limit, 273 MB in use after the E2E run; CI image job runs with 512 MB |
| D-33 | Integration tests write to whatever database .env names, which can now be the live one (some commit, audit rows cannot be removed), and some counts assumed only the dummy data | Medium | Second independent review (M3) | Fixed: IntegrationDatabaseGuard stops them on a non-local database; counts compared with the database | IntegrationDatabaseGuardTest; refusal shown with a Supabase URL |
| D-34 | An empty email address was accepted and locked the account out | Low | Second independent review (M3) | Fixed: @NotBlankIfPresent on email | blankNamesRefused; NotBlankIfPresentValidatorTest |
| D-35 | The append-only audit test passed even with the trigger disabled (since V6 a missing grant refused first) | Low | Second independent review (M3) | Fixed: the test connects as the schema owner, also covers notes | auditTrailAndNotesAreAppendOnly (fails with the trigger disabled) |
| D-36 | The status-history function ignored row level security, so a requester's role could read another request's history | Low | Second independent review (M3) | Fixed in V7: requesters only get their own requests | statusHistoryOnlyForOwnRequests |
| D-37 | Log injection (CodeQL): request values written to the logs unchanged | Low | CodeQL | Fixed: LogSafe in all five log lines | LogSafeTest |
| D-38 | Frontend: late responses can update the wrong record (queue page contact details, Staff page categories, requester list pages) | Low | Second independent review (M3) | Fixed in PR #32 (c0dd9a7): replies for a record that is no longer selected are ignored and older page loads cancelled | request-queue-page.spec; staff-page.spec; requester-page.spec (fail on the old code) |
| D-39 | During a zero-downtime deploy two instances can ask for 20 database connections as civicconnect_app, more than the Supabase session pool of 15 per user and database (confirmed 18/10/2026; Flyway uses the postgres user, a separate pool) | Low | Second independent review (M3) | Fixed 18/10/2026: the Supabase session pool size was raised from 15 to 20 per user and database, so the old and new instance fit during a deploy (2 x 10 = 20). The application pool stays at 10 unless the pooler is raised too. | Supabase connection pooling settings (pool size 20); docs/deployment.md step 6 |
| D-40 | A rare duplicate-key error can write an email address into the logs (POPIA) | Low | Second independent review (M3) | Fixed: only the constraint name or SQL state is logged | integrityLogHasNoPersonalData (fails on the old code) |
| D-41 | Activity page: the open-requests list ignored the chosen status filter (FR-013) | Low | Team review (M3, PR #32) | Fixed in PR #32 (c0dd9a7): the status filter is sent | activity-page.spec |
| D-42 | Integration tests ran in the machine's time zone, but the application runs in UTC (main() sets it): on a laptop in South African time Hibernate stored times 2 hours early, so the overdue boundary was wrong in local test runs | Low (tests only) | Black-box test overdueBoundary (M3) | Fixed: the tests run in UTC (-Duser.timezone=UTC in pom.xml). The application was not affected | overdueBoundary passes in UTC and in South African time; fails in South African time without the fix |

D-16 and D-17 passed review because the code looked correct; they are why the Backend job now starts the application and runs the integration tests on every pull request. "Independent review" was an AI-assisted review of the whole code base by a reviewer that had not seen the changes (see AI Usage Register); every finding was checked against the code before it was fixed.

### Static analysis and security findings

| Check / finding | Assessment | Handling |
| --- | --- | --- |
| gitleaks: a JWT secret in an old ci.yml commit | A test value, not the production secret (the .env value differs) | Fingerprint and reason recorded in .gitleaksignore |
| gitleaks: 80 JWT login tokens in the k6 result files (commit 7bdb199) | Tokens of the 20 test staff accounts on local test databases, valid for one hour; all expired | Removed from the results and the script fixed (D-29); fingerprints and reason recorded in .gitleaksignore |
| Database password in the prototype history (R-22) | Credentials are now environment variables only | Replaced by ${DB_PASSWORD} in commit 7ac7b9a (10/10/2026). It was a local development password for localhost only, never used for a shared database, so the history was not rewritten |
| CodeQL | Two log-injection alerts (FilterErrorHandler): request values written to the logs unchanged. Low real risk: Tomcat refuses raw line breaks and the URI stays encoded | Fixed in all five log lines, not only the two flagged (D-37). CodeQL jobs passed on the release candidate (3bb0a3e); the 6 alerts open on 16/10/2026 were triaged on 18/10/2026: #1 (Spring CSRF protection disabled) dismissed as a false positive, because the API is stateless and the token is sent in the Authorization header, never in a cookie; #5 (possible null in a test), #6 to #8 (unused parameters in GlobalExceptionHandler) and #11 (unchecked number parse of the token subject in CurrentUserService) fixed in PR #39 (branch fix/codeql-test-null-check) |
| npm audit (runtime packages, high) | Gate in the Frontend job | Passed on main 6a198c4 and PR #33 (the Frontend job fails otherwise) |
| Dependency review | Active on every pull request; passed on PRs #32 and #33 | No findings |

### Technical debt register

| ID | Debt | Consequence | Plan |
| --- | --- | --- | --- |
| TD-01 | Single-jar packaging (ARC-03) - resolved in M3 | Two processes to deploy; CORS needed if they are split | Done: Dockerfile, CI image job and render.yaml (C-07) |
| TD-02 | Rate-limit and lockout counters in memory | Limits multiply with instances; reset on restart | Shared store before scaling out |
| TD-03 | Client date of birth was stored without a purpose (ERD v2 change 1) - resolved in M4. Employee date of birth and address are kept as the staff record, because no separate HR system exists in the scenario. | More personal data than needed (POPIA) | Done (M4, CR-022): V8__drop_client_date_of_birth.sql removed the column, and the API (API-18) and the profile page no longer offer it. The employee fields stay as the HR record. |
| TD-04 | No keyword or reference-number search (FR-006 "search") | Staff filter and page to find a request | Add a search parameter to API-07 |
| TD-05 | No stale-screen detection (C-01) | Silent last-write-wins on priority and reassignment | Compare updatedAt and return 409 VERSION_CONFLICT |
| TD-06 | Few Angular component tests: since PR #32 the queue, staff, activity and requester pages and the role guard have specs; the other pages have none | UI regressions such as D-09 are only caught manually or by E2E | Component tests for the remaining pages |
| TD-07 | A password change does not end other sessions | A stolen token stays valid until it expires (60 minutes) | Token version per account |
| TD-08 | Email unique across clients and employees, and case-insensitive category names, enforced only in the application | Direct SQL could create duplicates | Database constraint or trigger |
| TD-09 | Unused frontend files (README rewritten 16/10/2026) | Confusing for new contributors (NFR-008) | Remove the unused files |
| TD-10 | Staff moved to Manager keep their category rows | Restored silently if moved back | Clear on role change |
| TD-11 | Attachments are external links only (A-02): no file storage, no size limit, no malware scan; plain http allowed | Staff open unverified links (R-28); a linked file can disappear, or hold personal data outside POPIA control | Allow only https; then file upload with size limits and malware scanning (deferred attachment hardening) |
| TD-12 | Independent / elastic scalability not designed in: one deployable (ARC-02), one instance | If one module (e.g. Reporting) became heavy, the whole application must scale together; the free tier cannot run a realistic load test to show whether this is needed (R-26) | Deferred (CR-018): load test on representative hosting before a real release; split a module only with evidence |
| TD-13 | Frontend visual styling is basic: plain layouts and default fonts and colours, following the wireframes but with no brand look. CivicConnect gave no branding (logo, colours, fonts or style guide). | The product works and is accessible, but looks unfinished to real users. Reworking styles across existing pages later costs more than building them in from the start, because each component's CSS and layout must be revisited and retested. | Get CivicConnect's branding, then define shared style variables (colours, fonts, spacing) first and apply them page by page, with the E2E tests run after each change. |
| TD-14 | No email, SMS or push notifications: requesters and staff only see changes in the app (FR-004, deferred scope). | Requesters must log in to see a status change, and staff are not alerted to new requests. Not built on purpose: a comprehensive notification service needs a paid subscription that CivicConnect would have to take out (Cost / Resources constraint), and building on a free tier, with its sending limits, would usually mean reworking the integration once the real service is chosen. | Agree a provider and subscription with CivicConnect. Then publish a status-change event from RequestService and send the messages from an after-commit listener (DEC-012), so a failed message never undoes a change. |

## Release Readiness

### Release Evidence Summary

| Evidence area | Result | Interpretation | Concern / action |
| --- | --- | --- | --- |
| Build and CI | Pass: CI and Security on main 6a198c4 and on PR #33 into prod. Run on the tagged commit (v3.0.0-rc1, 3bb0a3e): CI and Security pass | Build, unit, integration and E2E gates are configured | Done: release run linked in Submission Information |
| Automated regression | 249 backend (189 unit, 60 integration) and 38 frontend unit tests pass | Business rules and every fixed defect except D-09 and D-15 are protected | Few component tests (TD-06) |
| API / integration | 60 tests against PostgreSQL 17 pass, 15 of them black-box tests designed from the API contract | Security chain, database roles, triggers and migrations work together | Supabase pooler differs from the CI database |
| System / E2E | 3 Playwright journeys pass locally and in CI; 33 manual tests on the test build: 31 Pass, 1 Blocked, 1 Not run (manual test log); Prod smoke tests on staging: 7 of 7 Pass on 16/10/2026 | The critical journey and two negative journeys work end to end | Done on staging: Prod smoke tests 7 of 7 Pass on 16/10/2026 |
| Static / security | CodeQL, gitleaks and npm audit configured | Two gitleaks findings documented (the second is D-29) | Open CodeQL alerts: 6 on 16/10/2026 (https://github.com/ClarissaBierman/SEN381-Project-CivicConnect/security); dependency review active |
| Performance | p95 29.8 ms at 20 users (target 2 s), repeated on two machines | Target met locally with a wide margin | Repeat on staging with Supabase latency (R-26) |
| Known defects | D-01 to D-42 recorded; open: D-39 (Low) | No known release blocker in the code; the public site must use the production database build (D-31) | Technical debt TD-01 to TD-10 remains |
| Acceptance | RTM Table 3 links each requirement to tests | Automated evidence for FR-001 to FR-016 and most NFRs | NFR-004 usability test and NFR-005 health-check log missing |

Classification: CONDITIONALLY READY (confirmed by the team, 16/10/2026). The core evidence is credible. Conditions and their status: (1) staging runs on Render against the production database - done; the E2E suite and the k6 test need the dummy accounts, which must not exist there (D-31), so they run in CI and locally, and the Prod smoke tests P-01 to P-07 are run on staging instead - done, 7 of 7 Pass on 16/10/2026; (2) a green CI run of all jobs on the tagged commit - done (3bb0a3e); (3) the M3 changes merged through reviewed pull requests - PRs #29 to #35 are merged; the manual test log and ERD v3 still to merge; (4) the NFR-004 informal usability test (MT-33) - deferred to 18/10/2026; (5) the public site runs on the production project built with civicconnect_production_build.sql (D-31) - done; P-03 passed: no dummy account can log in.

### Residual risks

| Residual risk | Why it remains | Current mitigation | Next action / owner |
| --- | --- | --- | --- |
| Performance on Supabase not measured | The load test ran locally without network latency | Wide local margin; paging and indexes | k6 run against a staging copy with test accounts (never the production database) |
| Many simultaneous writers | The lock and unique index are tested with two transactions at once (ConcurrencyIntegrationTest), but not under heavier parallel load | Row lock, unique index, tests | Add a concurrent-write scenario |
| Default manager credential | Known password in the build script | Change at first login (R-25) | Change before staging; done |
| One instance only | Rate limits in memory; one jar | Pilot load of 20 users (A-01) | Shared store if scaled out |
| Supabase free plan pauses | Free tier behaviour | 503 handling; health check before demos (R-14) | Health check the day before; done. |
| AI-assisted code | Large parts drafted with AI | Tests, reviews, AI Usage Register (R-27) | Every member walks through the code before the defence and a meeting is scheduled the day prior to coordinate details regarding the presentation (CR-015). |

### Staging and rollback

Staging: the Render free web service in render.yaml runs the image built from the prod branch (main is merged into prod for a release), after the CI and Security checks pass, against a separate production Supabase project built with civicconnect_production_build.sql - no dummy or default accounts (D-31) - through the session pooler. The team's existing project, with the dummy data, stays the test database. Steps: docs/deployment.md. Staging URL: https://civicconnect-pxjj.onrender.com, running prod at 3bb0a3e (v3.0.0-rc1). The E2E suite and the k6 test use the dummy accounts, which must not exist on this database (D-31), so they run in CI and locally; on staging the Prod smoke tests P-01 to P-07 are run instead: 7 of 7 Pass on 16/10/2026. Record the Prod smoke tests P-01 to P-07 in the Prod sheet of docs/CivicConnect manual test log.xlsx. Open the site a few minutes before a demo: the free instance sleeps after 15 minutes without traffic.

Rollback: on Render, redeploy an earlier deploy from the service's Events page (or revert the commit on main). Flyway migrations only go forward. V5 only adds a function, but V6 takes away staff and management's direct read access to audit_entry (they now read the audit_log view), so a jar from before V6 cannot show audit history on a V6 database. Rolling back past V6 therefore means restoring the pg_dump taken before the upgrade, or giving SELECT on audit_entry back by hand. If data must be restored, use the latest pg_dump (R-23).

# Final Project (M4) Closure

This chapter closes the project for the Final Project (M4). It continues the PED from v3.0 to v4.0 and does not replace earlier sections. It accounts for every M1 in-scope commitment, calculates the Scope Completion Percentage from the approved M1 acceptance criteria and records the final status of the M3 findings, the go-live decision and the project conclusion. The final assessed release is [tag, e.g. v4.0.0] / commit [hash].

## M1 Scope → Final Delivery

Each in-scope capability from the M1 Scope Baseline is listed with its requirement, its M1 priority, its final status and the evidence for it. Final status uses the M4 categories: IMPLEMENTED, PARTIALLY IMPLEMENTED, NOT IMPLEMENTED and CHANGED THROUGH APPROVED CHANGE. Out-of-scope and deferred items are listed separately (Table C) and are not counted as failed commitments.

### In-scope commitments

Table A - M1 in-scope commitments and their final status

| # | M1 in-scope commitment | Req. | M1 priority | Final status | Acceptance criteria | Evidence | Conclusion / reason for variance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Submit a request with category, description, location, optional attachment | FR-001 | Must | IMPLEMENTED | Met | RTM T3; E2E-01; descriptionBoundaries; MT-09, MT-10 | Delivered. The attachment is stored as a link; file upload stays deferred (attachment hardening, Table C). |
| 2 | View the current status of a request | FR-002 | Must | IMPLEMENTED | Met | E2E-01; RequestServiceTest; MT-11 | Delivered as committed. |
| 3 | View own request history | FR-003 | Must | IMPLEMENTED | Met | requesterSeesOnlyOwnRequests; E2E-02 | Delivered; other requesters' requests return 404. |
| 4 | In-app feedback when status changes | FR-004 | Should | IMPLEMENTED (changed by CR-005) | Met | statusHistory; E2E-01; MT-11 | CR-005 limited feedback to in-app. SMS/email remain deferred. |
| 5 | View requests in the staff member's authorised scope | FR-005 | Must | IMPLEMENTED (changed by CR-002) | Met | staffListIsScoped; MT-14, MT-27 | CR-002 defined scope as the categories Management assigns. |
| 6 | Search, filter and sort requests | FR-006 | Must | PARTIALLY IMPLEMENTED | Met (filter/sort ≤ 2 s) | managerListAppliesFiltersAndNames; k6 p95 29.8 ms; MT-15 | Filter and sort meet the 2-second criterion. Free-text search was not built (TD-04). Low impact at pilot volume: status, category and date filters with paging locate requests. |
| 7 | Full request detail with audit trail | FR-007 | Must | IMPLEMENTED | Met | fullLifecycleIsAudited; MT-21 | Delivered. |
| 8 | Assign or accept responsibility | FR-008 | Must | IMPLEMENTED (2nd criterion added by CR-007) | Met (both) | databaseAllowsOneActiveHandler; ConcurrencyIntegrationTest; MT-16, MT-17 | Simultaneous accepts: exactly one wins, the other gets 409 ALREADY_ASSIGNED. |
| 9 | Controlled status transitions | FR-009 | Must | IMPLEMENTED | Met | TransitionPolicyTest; statusChangePartitions; MT-18 | Delivered (D-08, D-11 fixed). |
| 10 | Append-only comments and resolution notes | FR-010 | Must | IMPLEMENTED | Met | CommentServiceTest; auditTrailAndNotesAreAppendOnly; MT-19 | Delivered. Limitation: the staff notes list doesn't label visible vs internal notes (MT-19 observation). |
| 11 | Resolve or close authorised requests | FR-011 | Must | IMPLEMENTED | Met | RequestServiceTest (read-only); MT-20 | Delivered. |
| 12 | Aggregate service activity | FR-012 | Should | IMPLEMENTED (overdue rule added by CR-004) | Met (both) | ReportServiceTest; overdueBoundary; MT-24 | Delivered (D-42 found and fixed). |
| 13 | Filter activity by category, status and date | FR-013 | Should | IMPLEMENTED | Met | activity-page.spec; MT-25 | Delivered (D-10, D-41 fixed in PR #32). |
| 14 | Information for accountability and service review | FR-007, FR-012, NFR-006 | Should | IMPLEMENTED | Met | Audit page; AuditServiceTest; MT-30 | Delivered through the request history, activity counts and the audit page (no client personal data). |
| 15 | Authentication and RBAC for three roles | FR-014, NFR-002, NFR-003 | Must | IMPLEMENTED (role names changed by CR-008) | Met | AuthServiceTest; JwtSecurityTest; E2E-02; MT-01 to MT-06 | Delivered; roles are REQUESTER, STAFF and MANAGEMENT (CR-008). |
| 16 | Management-controlled category list | FR-015 | Must | IMPLEMENTED (changed by CR-001) | Met | CategoryServiceTest; categoryPartitions; MT-12, MT-26 | CR-001 changed "admin" to Management. |
| 17 | Audit trail of who changed what and when | NFR-006, NFR-007 | Must | IMPLEMENTED (design changed by C-02) | Met | fullLifecycleIsAudited; auditTrailAndNotesAreAppendOnly; MT-21 | Implemented with database triggers instead of an application listener (C-02), so every change is audited. |
| 18 | Added after M1: Management sets request priority | FR-016 | Should | IMPLEMENTED (added by CR-003) | Met | priorityAndHistory; priorityPartitions; MT-23 | Added through approved change CR-003 in M2. |

### Non-functional requirements

Table B - Non-functional requirements and their final status

| Req. | Requirement | M1 priority | Final status | Acceptance criteria | Evidence | Conclusion |
| --- | --- | --- | --- | --- | --- | --- |
| NFR-001 | p95 ≤ 3 s at ≤ 20 users | Should | IMPLEMENTED | Partially Met | k6 pilot run: p95 29.8 ms (repeated on a second machine) | Met in the local test with 10,000 requests. Not measured on the production hosting (R-26). |
| NFR-002 | Passwords hashed, never in plain text | Must | IMPLEMENTED | Met | AuthServiceTest; ResponsesNeverContainPasswordsTest | BCrypt; no password in any response or audit row. |
| NFR-003 | RBAC enforced on the server, not just the UI | Must | IMPLEMENTED | Met | requesterCannotUseStaffEndpoints; databaseRoleBlocksRequester; E2E-02 | Enforced in the API and by database roles (C-03). |
| NFR-004 | 2 of 3 first-time users submit unaided within 5 minutes | Should | Not met | Not met | MT-33 (manual test log) | N/A -deferred. |
| NFR-005 | No unplanned downtime during demos | Should | IMPLEMENTED | Met | FilterErrorHandlerTest; health checks 16/10/2026 | 503 instead of a crash when the database is down; health-checked before demos. |
| NFR-006 | Every action logged with actor, time and before/after | Must | IMPLEMENTED | Met | fullLifecycleIsAudited; statusHistory | Full lifecycle rebuilt from the audit trail. |
| NFR-007 | Changes outside the workflow blocked or logged | Must | IMPLEMENTED | Met | auditTrailAndNotesAreAppendOnly; databaseRoleBlocksRequester | The database refuses UPDATE and DELETE on audit rows. |
| NFR-008 | Documented, navigable code structure | Could | IMPLEMENTED | Met | README.md (rewritten, TD-09) | README describes the structure, setup, tests, CI and release flow. |
| NFR-009 | No hard-coded limits; scalable data model | Could | IMPLEMENTED | Met | SortGuardTest; pageSizeCap; k6 with 10,000 rows | Lists paged (max 100); categories stored as data. |

### Out-of-scope and deferred items

These items were outside the committed M1 scope. They are not counted in the Scope Completion Percentage and are not failed commitments.

Table C - Out-of-scope and deferred items

| M1 classification | Item | Final status | Conclusion |
| --- | --- | --- | --- |
| Out of scope | Automated multi-channel intake (WhatsApp, email) | Remained out of scope | Single web form, as committed. |
| Out of scope | Native mobile apps | Remained out of scope | Responsive web only; the REST API would allow a mobile client later (ASR-006). |
| Out of scope | Payments, multi-tenant, real-time chat, SMS/push, BI dashboards, public API, localisation | Remained out of scope | Not built, as committed. |
| Deferred | SMS/email notification channel | Still deferred | In-app feedback only (FR-004); why it was not built and how it would be added: TD-14. |
| Deferred | Exportable / advanced reporting | Still deferred | Core counts and filters delivered (FR-012, FR-013). |
| Deferred | Attachment hardening (size limits, malware scan) | Still deferred | Only a link is stored, so no files are uploaded. |
| Deferred | Automated escalation of overdue requests | Still deferred | Overdue requests are counted and visible, not escalated. |
| Deferred | SSO / self-service password reset | Still deferred | Logged-in users can change their password (D-26); there is no forgotten-password reset. |
| Deferred | Migration of historical records | Still deferred | No legacy data was supplied. |
| Deferred | Rate limiting | Brought forward (C-04) | Implemented early for security (login lockout, API limits). |

### Scope changes since M1

All changes to the M1 baseline went through change control and are recorded in the Change Request Register.

Table D - Approved changes that affect the scope baseline

| Change | Effect on the baseline |
| --- | --- |
| CR-001 | Category list maintained by Management (was "admin") - FR-015, NFR-009 |
| CR-002 | Staff scope = categories assigned by Management - FR-005 |
| CR-003 | New FR-016: Management sets priority (added to the baseline) |
| CR-004 | Overdue definition added to FR-012 (7 calendar days) |
| CR-005 | FR-004 feedback limited to in-app |
| CR-007 | Second acceptance criterion for FR-008 (simultaneous accepts) |
| CR-008 | Role names: STAFF and MANAGEMENT |
| C-02, C-03, C-04 | Design changes (audit trigger, database roles, rate limiting); no change to the requirements |

## Scope Completion Percentage

The percentage follows the M4 formula: each approved acceptance criterion scores Met = 1.0, Partially met = 0.5, Not met = 0.0. The baseline is the M1 acceptance criteria as changed by approved change requests: 16 functional requirements (FR-008 and FR-012 have two criteria each after CR-007 and CR-004), which gives 18 functional criteria, plus 9 non-functional requirements - 27 criteria in total.

Table E - Scope Completion calculation

| Criteria | Final status | Score |
| --- | --- | --- |
| FR-001 to FR-016 (18 criteria) | All met | 18.0 |
| NFR-002, 003, 005, 006, 007, 008, 009 (7 criteria) | Met | 7.0 |
| NFR-001 | Partially met | 0.5 |
| NFR-004 | Not met | 0 |
| Total | 27 criteria | 25.5/ 27 |
| Scope Completion % | (25.5÷ 27) × 100 | 94.4 % |

Conclusion: 94.4% of the approved M1 acceptance criteria are met, above the 80% target. Every Must-have requirement is implemented. The only partial delivery of a Must item is free-text search within FR-006, whose acceptance criterion (filter and sort within 2 seconds) is met. The delivered scope is coherent: all three roles can complete their critical journeys end to end.

## Schedule Performance and Variance

Planned dates come from the Constraints table (CR-012); actual dates from Document Control, the pull requests and the release tags in the repository.

Table F - Planned and actual milestone delivery

| Milestone | Planned (CR-012) | Actual | Variance | Cause | Decision / trade-off | Evidence |
| --- | --- | --- | --- | --- | --- | --- |
| M1 - Requirements baseline | Due 9 September, presented 10 September | PED v1.0 approved 09/09/2026 | On time | - | - | Document Control; PR #1 (08/09/2026) |
| M2 - Architecture and design | Due 30 September, presented 1 October | PED v2.0 approved 30/09/2026 | On time, with known gaps | The prototype was built late in the phase: V2 migration, credentials and CI were not done (R-21, R-22) | Baseline accepted with known gaps, all closed in M3 (Baseline Sign Off) | Document Control; PRs #2 to #5 (30/09/2026) |
| M3 - Construction and release candidate | Due 14 October, presented 15 October | Release candidate v3.0.0-rc1 tagged 16/10/2026 (3bb0a3e); PED v3.0 16/10/2026. Video presentation submitted on Friday 16/10/2026 instead of the live presentation on Thursday 15/10/2026. | Presentation format changed: a video on 16/10/2026 instead of a live presentation on 15/10/2026 | Learning curve of Spring Boot and Angular (R-20); two independent code reviews found D-18 to D-42; staging set-up (Render, separate production database) | Testing and security were not cut: rate limiting was brought forward (C-04). Deferred instead: free-text search (TD-04), attachment hardening, part of the component tests (TD-06) | PRs #29 to #35; tag v3.0.0-rc1 |
| M4 - Final product | Final project due 18 October; defence in week 7, 19 to 22 October (study guide v3.0) | On time: submitted on the due date. Delivered with known limitations, recorded as technical debt and not hidden | [Team to complete] | NFR-004 usability test could not be run unaided on the free hosting (CR-014) | NFR-004 deferred (CR-014) rather than run with developer help, which would have invalidated the test. The final days went to quality and compliance instead of new features: the CodeQL fixes, the forced audit failure test (R-18) and removing the client date of birth (CR-022). The remaining gaps are recorded as TD-11 to TD-14 | PRs #36 to #38; CR-014 to CR-022; tag v4.0.0 |

Interpretation: M1 and M2 were delivered and presented on the planned dates, M2 with known gaps that were closed in M3. M3 was presented as a video on Friday 16 October 2026 instead of live on 15 October. Schedule pressure in M3 was absorbed by deferring features and recording them as technical debt, not by reducing testing or security (Master Brief, section 18).

## Cost and Operational Cost

Every service was chosen against the cost constraint (ASR-007: R0 licensing and hosting). The free tiers held, but their limits shaped several decisions.

Table G - Services, cost and the limits that affected the project

| Service | Used for, plan and cost | Limits that affected the project | Evidence |
| --- | --- | --- | --- |
| GitHub | Repository, Actions (CI and Security), CodeQL, Dependabot, gitleaks - free for a public repository, R0 | None reached | .github/workflows |
| Render | Staging web service (one Docker image) - free plan, R0 | 512 MB and 0.1 CPU: the JVM memory had to be tuned (D-32). Sleeps after 15 minutes without traffic and takes about 90 seconds to wake (P-07), which stopped the unaided usability test (CR-014). No load test possible on the hosting (R-26) | render.yaml; P-01 to P-07 |
| Supabase (two projects: test and production) | PostgreSQL 17 - free plan, R0 | 500 MB database; pauses after a week without use (R-14); no automatic backups (manual pg_dump); Nano compute with a session pool of 15 per user and database, raised to 20 for deploys (D-39) | A-04; Supabase settings; docs/deployment.md |
| Open-source tools | Spring Boot, Angular, PostgreSQL, Flyway, JUnit, Playwright, k6 - R0 | - | pom.xml; package.json; perf/ |
| AI assistance | Drafting code, tests and documents - [Team to complete: whose subscription and its cost] | - | AI Usage Register |

Total project cost: R0 for hosting and tooling (nothing is paid). ASR-007 is met.

Likely operational cost for real use is to be determined with CivicConnect after determining the preferred hosting environments if any. Requirements will likely be: an always-on application instance (no sleep), a paid database plan (daily backups, no weekly pause) and an uptime monitor. The free tiers are acceptable for a pilot demonstration, not for a public service, because of the sleep, the weekly pause and the missing backups.

## Stakeholder Validation

Each stakeholder from the Stakeholder Analysis is checked against what was delivered. Outcomes use the Master Brief categories: satisfied, partially satisfied, changed, rejected or not achieved.

Table H - Stakeholder expectations and outcome

| Stakeholder | Expectation (Stakeholder Analysis) | Outcome | Evidence |
| --- | --- | --- | --- |
| Service Requester | Create an account and log in; submit a request easily; track its progress; contact CivicConnect about it | Satisfied, except that easy first use (NFR-004) is not yet validated with real users (CR-014) | FR-001 to FR-004, FR-014; E2E-01; MT-07 to MT-13 |
| Service Handler | See assigned requests; record details; change the status; contact the requester | Satisfied; partially for finding a request, as there is no free-text search (TD-04) | FR-005 to FR-011; MT-14 to MT-22; contact details on the queue page |
| CivicConnect Management | Assign requests; manage staff and categories; follow the request lifecycle; report on requests | Satisfied | FR-012, FR-013, FR-015, FR-016; MT-23 to MT-30; audit page |
| Government (POPIA) | Personal information only collected and shown where needed | Partially satisfied: reports hold counts only, the audit view masks client data and the client date of birth was removed (V8, TD-03); employee date of birth and address are kept as the staff record. No retention period is agreed | ASR-005; activityReport; TD-03 |
| Developers | Clear requirements and a documented, maintainable code base | Satisfied | RTM; README (NFR-008); ERD v3; Flyway migrations |

Limitation: there was no real CivicConnect stakeholder to sign off (R-09). Validation was done by the team acting in each role (manual test log) and, once run, by non-team users (MT-33).

## Decision Consequence Reflection

Significant decisions are judged against the evidence available when they were made, not with hindsight (Master Brief, section 22).

Drafted from the project evidence. The last two columns are the team's view and must be confirmed in review.

Table I - Decisions, outcomes and learning

| Original decision | Evidence at the time | Expected benefit / risk | Actual outcome | Evidence | Would we decide differently? | Learning |
| --- | --- | --- | --- | --- | --- | --- |
| DEC-004 Angular + Spring Boot + PostgreSQL | Decision matrix (4.12 against 4.20 for React + ASP.NET after CR-013); ASR-001 to ASR-003 | Security, transactions and migrations built in; risk: no team experience (R-20), memory on free hosts | All requirements built; security and transactions worked as expected; the JVM needed memory tuning for 512 MB (D-32); the learning curve was absorbed with reviews and AI help (R-27) | RTM Table 3; D-32; AI Usage Register | No - the security and transaction fit outweighed the small matrix gap; we would plan the memory tuning and the learning time from the start | A decision matrix records the trade-off; it does not make the decision |
| DEC-006 optimistic locking (Version column) | Low contention; A2 Task 2 recommended pessimistic locking | No locks held while users read | Replaced in M3 by a row lock (C-01): every write already re-checks the state, and the unique index guards double assignment | C-01; concurrentAcceptsOneWins; TD-05 | Yes - start with the row lock | Prototype the concurrency path early; the simplest correct mechanism was the database's own |
| DEC-007 / DEC-012 audit written by the application, protected by a trigger | NFR-006, NFR-007; Spring events looked simple | A complete, tamper-proof history | Replaced by database triggers that write every change (C-02): complete even outside the API, but the SECURITY DEFINER trigger created a weakness found in review (D-19), fixed in V6 | C-02; D-19; auditTrailAndNotesAreAppendOnly | Keep the trigger, but design its security from the start | Database-level controls are strong but need their own security review |
| C-03 one database role per user type (new in M3) | ASR-001, ASR-005: defence in depth | A bug in a Java check cannot expose other data | Worked, but the grants were more open than documented (D-21) and broke a requester email change (D-18); row level security added in V6 (C-08) | DatabaseRolesIntegrationTest; D-18; D-21 | Keep it, with row level security and per-role SQL tests from the start | Defence in depth only counts when each layer is tested |
| ARC-03 one deployable on free hosting | ASR-007 (R0); A-05 | One service, no CORS, simple deployment | Staging works (P-01 to P-07), but the instance sleeps (CR-014), the pool needed raising (D-39) and the load test could not run on the hosting (R-26) | C-07; P-07; D-39; R-26 | Not the architecture; for user testing, budget a small always-on instance | Free tiers shape testing as much as cost |

## Deployment, Rollback and Observability

How the final release reaches staging, how it is checked, how it is rolled back and how problems would be noticed.

Table J - Release, rollback and operational evidence

| Area | Evidence | Status | Gap / next step |
| --- | --- | --- | --- |
| Release | [Team to complete: v4.0.0 tag, commit and release pull request into prod]. Previous release candidate: v3.0.0-rc1 (3bb0a3e) | [Team to complete] | - |
| Deployment path | Pull request into prod, then CI and Security must pass before Render deploys (render.yaml: autoDeployTrigger checksPass). Staging: https://civicconnect-pxjj.onrender.com | In place | [Team to complete: Render deploy ID and time for v4.0.0] |
| Checks after a deploy | /api/v1/health returns database UP; Prod smoke tests P-01 to P-07 (7 of 7 Pass for v3.0.0-rc1 on 16/10/2026) | In place | [Team to complete: rerun P-01 to P-07 on v4.0.0] |
| Rollback | Render: redeploy the previous deploy. Flyway only goes forward: a jar from before V6 cannot read the V6 audit trail, so rolling back past V6 means restoring the backup | Planned, not rehearsed | Rehearse once on the test project |
| Backup and restore | Manual pg_dump before each release (Scalability, Availability and Backup) | [Team to complete: date of the last dump and of the restore test promised there] | Paid plan for automatic backups |
| Observability | Health endpoint (application and database); Render logs (errors and warnings, request values sanitised, D-37); Supabase dashboard (size, connections); GitHub Security tab | Partial | No metrics or tracing |
| Alerting | None: degradation is only noticed by checking manually or by a user | Gap | Add an uptime monitor with alerts before real use (it also keeps the free instance awake) |

Incident response [Team to complete: who checks the health endpoint and logs, and what to do on a 503 - first check whether the Supabase project is paused and resume it, then check Render's events and logs].

## Final Quality and Security Summary

What the evidence shows - and what it does not. We do not claim the system is secure or defect-free.

Table K - Quality and security evidence

| Area | Result | What it shows | What it does not show |
| --- | --- | --- | --- |
| Automated tests | 251 backend (190 unit, 61 integration on PostgreSQL 17), 38 frontend unit, 3 E2E; all pass in CI | Business rules, the API, database roles and triggers work together; the critical journeys work in a browser | Behaviour on Supabase over the network; heavy concurrent writes |
| Coverage | 97.1 % of lines, 91.7 % of branches (backend) | Which code the tests run | That the code is correct; frontend coverage |
| Manual tests | 33 on the test build (31 Pass, 1 Blocked, 1 Not run) and 7 Prod smoke tests (7 Pass) | Each role's journeys by hand | Real users (NFR-004 deferred, CR-014) |
| Performance | p95 29.8 ms at 20 users locally; 259 requests/s probe without errors | A large margin to the 2-second target | Performance on the hosting (R-26) |
| Defects | D-01 to D-42 recorded; all fixed, D-39 on 18/10/2026 | Findings were fixed with regression tests | Defects not found yet |
| Static analysis and scanning | gitleaks: two findings handled; npm audit and dependency review pass. CodeQL: of the 6 alerts open on 16/10/2026, #1 (CSRF protection disabled) was dismissed as a false positive (stateless API, token in the Authorization header, no cookies) and #5, #6, #7, #8 and #11 were fixed in PR #39 | Known patterns are checked on every push | Logic flaws and design weaknesses |
| Security controls | JWT (60 minutes), BCrypt, role checks in the API, database roles and row level security, rate limits and login lockout, append-only audit trail, secrets in environment variables | Defence in depth in the API and the database | That the system is secure |
| Residual security risks | R-28 attachment links; TD-07 sessions survive a password change; TD-02 in-memory rate limits; default account on the test database (R-25) | Known and recorded | - |

## Known Limitations and Future Evolution

Limitations of the final product and how it would evolve.

Table L - Known limitations

| Area | Limitation now | Next step | Reference |
| --- | --- | --- | --- |
| Search | No free-text or reference-number search; staff filter and page instead | Add a search parameter to API-07 | TD-04 |
| Notifications | In-app only; no SMS or email, so requesters must log in to see updates | Agree a provider and subscription with CivicConnect, then publish a status-change event and send from an after-commit listener (DEC-012) | Deferred scope; TD-14 |
| Attachments | Links only, not checked | https only, then file upload with size limits and scanning | R-28, TD-11 |
| Hosting | Free tier sleeps and pauses; single instance; no automatic backups | Always-on instance and a paid database plan; shared store for rate limits before scaling out | R-14, R-15, TD-02 |
| Performance | Not measured on the hosting | Load test on representative hosting | R-26, TD-12 |
| Usability | NFR-004 not validated with real users | Run MT-33 once the staging site can be used unaided | CR-014 |
| Privacy | Retention period undecided (the client date of birth was removed in V8; employee date of birth and address are kept as the staff record) | Agree a retention period with CivicConnect | CR-022 |
| Accounts | No password reset; a password change does not end other sessions | Self-service reset; token version per account | TD-07 |

Evolution: the easiest change is a second client such as a mobile app, because all business rules are in the API (ASR-006). The hardest are leaving PostgreSQL (triggers, row level security and the partial index, DEC-005) and splitting a module into its own service (TD-12). TD-03 (personal data) was resolved in M4 (CR-022); the first debt to address now is TD-07 (sessions).

## Test and Code Reference Index

Where every test and code element named in this document is found. Paths are relative to the repository root; each group row gives the folder the paths below it start from. Line numbers point to the class, method, constant or SQL statement in the final release commit. E2E-01 to E2E-03 are the Playwright tests; MT-xx and P-xx are in docs/CivicConnect manual test log.xlsx.

Table M - Test and code reference index

| File | Names in this document (line) |
| --- | --- |
| Backend tests | civicconnect-backend/src/test/java/com/civicconnect/ |
| CivicconnectBackendApplicationTests.java | class CivicconnectBackendApplicationTests (line 9), contextLoads (line 12) |
| ResponsesNeverContainPasswordsTest.java | class ResponsesNeverContainPasswordsTest (line 25) |
| access/service/AuthServiceTest.java | class AuthServiceTest (line 43), registerSameAnswerForTakenEmail (line 95) |
| access/service/ClientServiceTest.java | class ClientServiceTest (line 27) |
| access/service/EmployeeServiceTest.java | class EmployeeServiceTest (line 42) |
| common/config/SpaFallbackResolverTest.java | class SpaFallbackResolverTest (line 16) |
| common/error/ErrorHandlingTest.java | class ErrorHandlingTest (line 21), integrityLogHasNoPersonalData (line 57) |
| common/error/FilterErrorHandlerTest.java | class FilterErrorHandlerTest (line 17) |
| common/logging/LogSafeTest.java | class LogSafeTest (line 9) |
| common/ratelimit/ApiRateLimitFilterTest.java | stagesSplitTheLimits (line 99), ipLimitCoversEveryPath (line 152) |
| common/ratelimit/LoginAttemptLimiterTest.java | class LoginAttemptLimiterTest (line 18) |
| common/security/ActiveAccountJwtConverterTest.java | class ActiveAccountJwtConverterTest (line 22) |
| common/security/JwtSecurityTest.java | class JwtSecurityTest (line 25), noTokenNoUser (line 98) |
| common/validation/MaxBytesValidatorTest.java | class MaxBytesValidatorTest (line 11) |
| common/validation/NotBlankIfPresentValidatorTest.java | class NotBlankIfPresentValidatorTest (line 17) |
| common/web/SortGuardTest.java | class SortGuardTest (line 14) |
| integration/ApiBlackBoxIntegrationTest.java | class ApiBlackBoxIntegrationTest (line 52), descriptionBoundaries (line 95), locationBoundaries (line 109), categoryPartitions (line 118), statusChangePartitions (line 137), priorityPartitions (line 160), overdueBoundary (line 179), pageSizeCap (line 206), malformedAndUnknown (line 216) |
| integration/ApiHttpIntegrationTest.java | class ApiHttpIntegrationTest (line 48), requesterCannotUseStaffEndpoints (line 91), noTokenIs401 (line 101), deactivatedEmployeeTokenRefused (line 111), deactivationTakesEffectImmediately (line 119), lastManagerCannotBeDeactivated (line 151), clientContactVersusAudit (line 164), priorityAndHistory (line 185), activityReport (line 217), sortByNestedFieldRefused (line 230), loginLockoutOverHttp (line 240), perAccountApiLimit (line 253), removingCategoryReleasesRequests (line 273), defaultManagerCanLogIn (line 288), prioritySortOrder (line 296), openAndUnassignedFilters (line 314), statusHistoryAndAllowedTransitions (line 334), descriptionLimit (line 360), inactiveCategoryHidden (line 369), requesterChangesEmail (line 378), registrationDoesNotRevealAccounts (line 392), staffChangeOwnPassword (line 410), orphanedInProgressNeedsManager (line 434) |
| integration/ConcurrencyIntegrationTest.java | class ConcurrencyIntegrationTest (line 44), concurrentAcceptsOneWins (line 96), handlerRemovalKeepsConcurrentChange (line 139) |
| integration/DatabaseRolesIntegrationTest.java | class DatabaseRolesIntegrationTest (line 25), appRoleCannotCreateObjects (line 56), definerFunctionsPinTheSearchPath (line 67), staffOnlyChangeOwnPassword (line 127), emailInUseForEveryRole (line 139), statusHistoryOnlyForOwnRequests (line 152) |
| integration/RateLimitOrderIntegrationTest.java | class RateLimitOrderIntegrationTest (line 25) |
| integration/RequestWorkflowIntegrationTest.java | class RequestWorkflowIntegrationTest (line 58), fullLifecycleIsAudited (line 90), requesterSeesOnlyOwnRequests (line 133), registrationNeverLeaksPassword (line 144), databaseRoleBlocksRequester (line 165), databaseAllowsOneActiveHandler (line 175), auditTrailAndNotesAreAppendOnly (line 201) |
| integration/StatusChangeRollbackTest.java | class StatusChangeRollbackTest (line 40), failedAuditRollsBackStatusChange (line 100) |
| reporting/repository/ReportRepositoryTest.java | class ReportRepositoryTest (line 18) |
| reporting/service/AuditServiceTest.java | class AuditServiceTest (line 38) |
| reporting/service/ReportServiceTest.java | class ReportServiceTest (line 21) |
| requests/repository/RequestSpecsTest.java | class RequestSpecsTest (line 21) |
| requests/service/CategoryServiceTest.java | class CategoryServiceTest (line 23) |
| requests/service/CommentServiceTest.java | class CommentServiceTest (line 34), cannotCommentOnClosedRequest (line 85) |
| requests/service/HandlerRemovalListenerTest.java | class HandlerRemovalListenerTest (line 29), locksBeforeChanging (line 100) |
| requests/service/RequestServiceTest.java | class RequestServiceTest (line 61), staffCannotClaimOrphanedInProgress (line 309), managerListAppliesFiltersAndNames (line 433), staffListIsScoped (line 462), mineHasNoHandler (line 481), openAndUnassignedFilters (line 547), allowedTransitionsDependOnTheUser (line 565), statusHistory (line 580) |
| requests/service/TransitionPolicyTest.java | class TransitionPolicyTest (line 9) |
| support/IntegrationDatabaseGuard.java | class IntegrationDatabaseGuard (line 24) |
| support/IntegrationDatabaseGuardTest.java | class IntegrationDatabaseGuardTest (line 9) |
| web/ControllerRoutingTest.java | class ControllerRoutingTest (line 44) |
| Backend code | civicconnect-backend/src/main/java/com/civicconnect/ |
| CivicconnectBackendApplication.java | class CivicconnectBackendApplication (line 9) |
| access/domain/Client.java | class Client (line 9) |
| access/domain/Employee.java | Role (line 12) |
| access/event/StaffMemberRemovedEvent.java | class StaffMemberRemovedEvent (line 15) |
| access/repository/HandlerCategoryRepository.java | class HandlerCategoryRepository (line 11) |
| access/service/AuthService.java | class AuthService (line 32) |
| access/service/EmployeeService.java | class EmployeeService (line 36) |
| common/error/ErrorCode.java | VALIDATION_FAILED (line 7), NOT_FOUND (line 11), VERSION_CONFLICT (line 13), ALREADY_ASSIGNED (line 14), INVALID_TRANSITION (line 15), REQUEST_CLOSED (line 16), CATEGORY_INACTIVE (line 17), OUT_OF_SCOPE (line 18), LAST_MANAGER (line 19), TOO_MANY_REQUESTS (line 20), SERVICE_UNAVAILABLE (line 21), INTERNAL_ERROR (line 22) |
| common/error/FilterErrorHandler.java | class FilterErrorHandler (line 26) |
| common/error/GlobalExceptionHandler.java | class GlobalExceptionHandler (line 36) |
| common/logging/LogSafe.java | class LogSafe (line 8) |
| common/security/ActiveAccountJwtConverter.java | class ActiveAccountJwtConverter (line 21) |
| common/security/CurrentUserService.java | class CurrentUserService (line 13) |
| common/security/DbSession.java | class DbSession (line 21) |
| common/security/DbSessionInterceptor.java | class DbSessionInterceptor (line 25) |
| common/security/JwtService.java | class JwtService (line 15) |
| common/validation/MaxBytes.java | class MaxBytes (line 19) |
| common/validation/NotBlankIfPresent.java | class NotBlankIfPresent (line 18) |
| reporting/domain/AuditEntry.java | class AuditEntry (line 20) |
| reporting/repository/ReportRepository.java | class ReportRepository (line 16) |
| reporting/service/AuditService.java | class AuditService (line 39), forRequest (line 59) |
| reporting/service/ReportService.java | class ReportService (line 20) |
| requests/controller/CategoryController.java | class CategoryController (line 18) |
| requests/controller/RequestController.java | class RequestController (line 31) |
| requests/domain/Category.java | class Category (line 7) |
| requests/domain/ServiceRequest.java | class ServiceRequest (line 13), Status (line 15) |
| requests/repository/RequestRepository.java | class RequestRepository (line 14) |
| requests/repository/RequestSpecs.java | class RequestSpecs (line 23) |
| requests/service/CommentService.java | class CommentService (line 21) |
| requests/service/CommentViews.java | class CommentViews (line 15) |
| requests/service/HandlerRemovalListener.java | class HandlerRemovalListener (line 40) |
| requests/service/RequestAccess.java | checkStaffScope (line 43) |
| requests/service/RequestService.java | class RequestService (line 50), create (line 82), mine (line 106), get (line 114), changeStatus (line 161), assign (line 204), setPriority (line 274) |
| requests/service/TransitionPolicy.java | class TransitionPolicy (line 14) |
| Database migrations (Flyway) | civicconnect-backend/src/main/resources/db/migration/ |
| V1__init_schema.sql | whole file |
| V2__align_with_entities.sql | chk_request_closed_at (line 25), chk_request_handler_dates (line 38), ux_request_handler_active (line 41), chk_audit_one_actor (line 76), block_change (line 146) |
| V3__roles_and_grants.sql | civicconnect_app (line 23), civicconnect_client (line 28) |
| V4__request_priority.sql | chk_request_priority (line 12) |
| V5__request_status_history.sql | request_status_history (line 9) |
| V6__database_hardening.sql | audit_row_change (line 23), email_in_use (line 71), audit_log (line 110) |
| V8__drop_client_date_of_birth.sql | whole file |
| Backend configuration and build | civicconnect-backend/ |
| database/civicconnect_production_build.sql | whole file |
| database/civicconnect_supabase_build.sql | whole file |
| mvnw.cmd | whole file |
| pom.xml | whole file |
| src/main/resources/application.properties | DB_URL (line 8), DB_USERNAME (line 9), DB_PASSWORD (line 10), spring.datasource.hikari.maximum-pool-size (line 11), FLYWAY_USER (line 19), FLYWAY_PASSWORD (line 20), spring.jpa.hibernate.ddl-auto (line 27), JWT_SECRET (line 43) |
| Frontend and end-to-end tests | civicconnect-frontend/ |
| e2e/access-control.spec.ts | E2E-02 (line 11) |
| e2e/deactivation.spec.ts | E2E-03 (line 11) |
| e2e/request-lifecycle.spec.ts | E2E-01 (line 10) |
| package.json | whole file |
| proxy.conf.json | whole file |
| src/app/app.routes.ts | whole file |
| src/app/category.service.ts | whole file |
| src/app/core/request-api.service.spec.ts | whole file |
| src/app/features/handler/request-queue-page.spec.ts | whole file |
| src/app/features/management/activity-page.spec.ts | whole file |
| src/app/features/management/staff-page.spec.ts | whole file |
| src/app/features/requester/requester-page.spec.ts | whole file |
| Repository root | (paths from the repository root) |
| .github/workflows/ci.yml | whole file |
| .github/workflows/security.yml | whole file |
| perf/request-list.k6.js | k6 load test |
| perf/seed-perf-data.sql | whole file |

# References

Angular (2026) Angular versioning and releases. Available at: https://angular.dev/reference/releases (Accessed: 30 September 2026).

Apache Software Foundation (2004) Apache License, Version 2.0. Available at: https://www.apache.org/licenses/LICENSE-2.0 (Accessed: 30 September 2026).

Belgium Campus ITversity (2026a) SEN381 CivicConnect Master Project Brief. Unpublished course document.

Belgium Campus ITversity (2026b) SEN381 CivicConnect Milestone 2 (M2): Architecture, Technology & Initial Design Baseline. Unpublished course document.

endoflife.date (2026) Angular. Available at: https://endoflife.date/angular (Accessed: 30 September 2026).

Flyway (no date) Flyway LICENSE.txt. Available at: https://github.com/flyway/flyway/blob/main/LICENSE.txt (Accessed: 30 September 2026).

Fowler, M. (2018) Refactoring: Improving the Design of Existing Code. 2nd edn. Boston, MA: Addison-Wesley.

Fowler, M. (2024) Continuous Integration. Available at: https://martinfowler.com/articles/continuousIntegration.html (Accessed: 30 September 2026).

Freeman, E. and Robson, E. (2020) Head First Design Patterns. 2nd edn. Sebastopol, CA: O'Reilly Media.

GitHub (no date) About protected branches. Available at: https://docs.github.com/en/repositories/configuring-branches-and-merges-in-your-repository/managing-protected-branches/about-protected-branches (Accessed: 30 September 2026).

Google (no date) Angular LICENSE. Available at: https://github.com/angular/angular/blob/main/LICENSE (Accessed: 30 September 2026).

Hibernate (no date) License. Available at: https://hibernate.org/community/license/ (Accessed: 30 September 2026).

Jones, M., Bradley, J. and Sakimura, N. (2015) RFC 7519: JSON Web Token (JWT). Internet Engineering Task Force. Available at: https://www.rfc-editor.org/rfc/rfc7519 (Accessed: 30 September 2026).

National Treasury (no date) POPIA. Available at: https://www.treasury.gov.za/POPIA/ (Accessed: 9 September 2026).

Nottingham, M., Wilde, E. and Dalal, S. (2023) RFC 9457: Problem Details for HTTP APIs. Internet Engineering Task Force. Available at: https://www.rfc-editor.org/rfc/rfc9457 (Accessed: 30 September 2026).

OpenJDK (no date) OpenJDK Legal Documents. Available at: https://openjdk.org/legal/ (Accessed: 30 September 2026).

Oracle (2026) Oracle Java SE Support Roadmap. Available at: https://www.oracle.com/java/technologies/java-se-support-roadmap.html (Accessed: 30 September 2026).

OWASP (2023) OWASP Top 10 API Security Risks - 2023. Available at: https://owasp.org/API-Security/editions/2023/en/0x11-t10/ (Accessed: 30 September 2026).

PostgreSQL Global Development Group (no date) License. Available at: https://www.postgresql.org/about/licence/ (Accessed: 30 September 2026).

PostgreSQL JDBC Driver (no date) License. Available at: https://jdbc.postgresql.org/license/ (Accessed: 30 September 2026).

Project Lombok (no date) Lombok LICENSE. Available at: https://github.com/projectlombok/lombok/blob/master/LICENSE (Accessed: 30 September 2026).

Spring (2026a) Spring Boot 4.1.1 available now. Available at: https://spring.io/blog/2026/08/20/spring-boot-4-1-1-available-now/ (Accessed: 30 September 2026).

Spring (2026b) System Requirements :: Spring Boot 4.1. Available at: https://docs.spring.io/spring-boot/4.1/system-requirements.html (Accessed: 30 September 2026).

Spring (2026c) Database Initialization :: Spring Boot 4.1. Available at: https://docs.spring.io/spring-boot/4.1/how-to/data-initialization.html (Accessed: 30 September 2026).

Spring (no date a) Spring Boot LICENSE.txt. Available at: https://github.com/spring-projects/spring-boot/blob/main/LICENSE.txt (Accessed: 30 September 2026).

Spring (no date b) Spring Security LICENSE.txt. Available at: https://github.com/spring-projects/spring-security/blob/main/LICENSE.txt (Accessed: 30 September 2026).

Spring (no date c) Spring Framework Reference: Additional Capabilities of the ApplicationContext (standard and custom events). Available at: https://docs.spring.io/spring-framework/reference/core/beans/context-introduction.html (Accessed: 30 September 2026).

Spring (no date d) Spring Framework Reference: Transaction-bound Events. Available at: https://docs.spring.io/spring-framework/reference/data-access/transaction/event.html (Accessed: 30 September 2026).

Spring (no date e) Spring Security Reference: OAuth 2.0 Resource Server JWT. Available at: https://docs.spring.io/spring-security/reference/servlet/oauth2/resource-server/jwt.html (Accessed: 30 September 2026).

Supabase (2026a) Pricing & fees. Available at: https://supabase.com/pricing (Accessed: 30 September 2026).

Supabase (2026b) Connect to your database. Available at: https://supabase.com/docs/guides/database/connecting-to-postgres (Accessed: 30 September 2026).

Supabase (2026c) Self-hosted Supabase: upgrading from PG 15 to 17 (breaking change). Available at: https://supabase.com/changelog/46080-self-hosted-supabase-upgrading-from-pg-15-to-17-breaking-change (Accessed: 30 September 2026).

Supabase (2026d) supabase/postgres releases. Available at: https://github.com/supabase/postgres/releases (Accessed: 30 September 2026).